## Tasks
Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Alpha Draft (date) | Alpha Review (date) | At risk? (checkbox) | Beta Review (date) | Beta Revision (date) | Design Priority (drop down) | Developer (users) | Development Status (drop down) | Final Review & Sign off (date) | Final Revision Received (date) | Graphics/Design Request (checkbox) | ITC Phase (drop down) | L2 / Substream (drop down) | L3 (labels) | L3 Script Available (checkbox) | Modalities (labels) | Number of Screens (number) | Overall Due Date (date) | Overdue Status (drop down) | Progress Updates (text) | QA (users) | QA (date) | QA (LM) (users) | Ready to be Assigned (checkbox) | Release Status (drop down) | Roles (list relationship) | SME/Approver (labels) | Script Received (date) | Sign off Received (date) | Start Date (date) | Submit 1st draft (date) | T-Codes (labels) | Target Close Date (date) | TempArchived? (checkbox) | Value Stream (drop down) | Value Stream Lead (users)
868a2uwc9 | PLP Incurred Cost Claim: Incurred Cost Claim Reports & Reconciliation - OL | PAUSED |  |  | LOW | Update from Carmen & Dan: system is not yet configured, pause all ICC training temporarily. When we resume, this will be WBT instead of ILT. | 8 | 0 |  | 2024-09-17 | 2024-10-03 11:44 | 2025-08-24 23:55 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c01cd4 868c01ekr 868c01ey0 868c01f7t | https://app.clickup.com/t/868c01cd4 https://app.clickup.com/t/868c01ekr https://app.clickup.com/t/868c01ey0 https://app.clickup.com/t/868c01f7t | plp, cognitus, wbt | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC4 | Incurred Cost Claim | Incurred Cost Claim (Incurred Cost Claim) |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | PLP | Jenn Cooke, Trish Cortez
868a2uwf7 | PLP Incurred Cost Claim: Reconcile G/L Data - OL | PAUSED |  |  | LOW | Update from Carmen & Dan: system is not yet configured, pause all ICC training temporarily. When we resume, this will be WBT instead of ILT. | 4 | 0 |  | 2024-09-25 | 2024-10-03 11:44 | 2025-08-24 23:59 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | cognitus, plp, wbt | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC4 | Incurred Cost Claim | Incurred Cost Claim (Incurred Cost Claim) |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | PLP | Trish Cortez, Jenn Cooke
868a2uwfh | PLP Incurred Cost Claim: Preparing for Submission - OL | PAUSED |  |  | LOW | Update from Carmen & Dan: system is not yet configured, pause all ICC training temporarily. When we resume, this will be WBT instead of ILT. | 8 | 0 |  | 2025-03-24 | 2024-10-03 11:44 | 2025-08-24 23:56 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | cognitus, plp, wbt | Development | [7 empty] | 437 hours |  | 0 | 2025-03-24 |  |  | 2025-04-15 | 2025-04-14 |  |  | Paused | 2025-04-28 |  |  | ITC4 | Incurred Cost Claim | Incurred Cost Claim (Incurred Cost Claim) |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | PLP | Trish Cortez, Jenn Cooke
868a2uwfq | PLP Incurred Cost Claim: Completing Adjustments - OL | PAUSED |  |  | LOW | Update from Carmen & Dan: system is not yet configured, pause all ICC training temporarily. When we resume, this will be WBT instead of ILT. | 8 | 0 |  | 2024-11-25 | 2024-10-03 11:44 | 2025-08-24 23:53 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c013qx 868c015hj 868c0192n 868c01acv 868c01awa | https://app.clickup.com/t/868c013qx https://app.clickup.com/t/868c015hj https://app.clickup.com/t/868c0192n https://app.clickup.com/t/868c01acv https://app.clickup.com/t/868c01awa | cognitus, plp, wbt | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC4 | Incurred Cost Claim | Incurred Cost Claim (Incurred Cost Claim) |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | PLP | Trish Cortez, Jenn Cooke
868a2uwfv | PLP Incurred Cost Claim: Other Systems & Data Collection - OL | PAUSED |  |  | LOW | Update from Carmen & Dan: system is not yet configured, pause all ICC training temporarily. When we resume, this will be WBT instead of ILT. | 7 | 0 |  | 2025-05-14 | 2024-10-03 11:44 | 2025-08-24 23:55 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | cognitus, plp, wbt | Development | [7 empty] | 437 hours |  | 0 | 2025-05-13 |  |  | 2025-06-02 | 2025-05-14 |  |  | Paused | 2025-07-11 |  |  | ITC4 | Incurred Cost Claim | Incurred Cost Claim (Incurred Cost Claim) |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | PLP | Trish Cortez, Jenn Cooke
868a2uwuy | SUS SCDS Theory & Tool Use | DEVELOPMENT |  | David Rood | NORMAL | Marin has requested the Registered trademark appear in the course titles with "SCDS" - updates have been made. She requested the opportunity to add knowledge checks and a step action exercise. The plan date for her to turn those over to us is by EOW. | 5 | 0 |  | 2025-06-25 | 2024-10-03 11:44 | 2025-08-25 11:55 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | ilt, sus, scds | Development | [7 empty] | 1134 hours |  | 0 | [7 empty] | Final Review & Sign off (SME) |  |  |  | ITC3 | SCDS Theory & Tool Use | SCDS |  | ILT |  | 2025-08-29 | [16 empty] | SUS | Brice LeBlanc, Shannon Bagent
868a2uy93 | SUS Obsolescence Management Using CDATS Part 3 | DEVELOPMENT |  | Kristin Grappone, David Rood | HIGH | Revised and finalized based on review on 6/26. Link below. | 2 | 0 | 2025-07-04 | 2025-06-23 | 2024-10-03 11:45 | 2025-08-24 21:33 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2va1m 868a2v77w | https://app.clickup.com/t/868a2va1m https://app.clickup.com/t/868a2v77w | cdats, sus, ilt | Development | [7 empty] | 1514 hours |  | 0 | [7 empty] | Pending SIMs | 2025-07-03 |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | ILT |  | 2025-08-29 | Overdue | [10 empty] | 2025-05-01 |  |  |  |  | SUS | Brice LeBlanc, Shannon Bagent
868a2uyzh | SUS SCDS Introduction | COMPLETED | Video reel with introduction to SCDS tool for sustainment solution design. |  | NORMAL | This intro video is complete and has been shared with SME for final approval. FYI - Marin is on PTO until July 14 | 3 | 0 | 2025-07-18 | 2025-05-19 | 2024-10-03 11:46 | 2025-08-14 13:54 |  | 2025-07-16 09:23 | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | scds, sus | Development | [7 empty] | 966 hours |  | 0 |  |  |  |  | 2025-06-19 |  |  | Development Complete |  |  |  | ITC3 | SCDS Introduction | SCDS |  | WBT |  | 2025-07-18 | Overdue | [9 empty] | 2025-07-16 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868a2uzkq | SUS Obsolescence Management Using CDATS Part 1 | DEVELOPMENT |  | David Rood, Kristin Grappone | HIGH | Create a Program SIM is ready for QA | 7 | 0 | 2025-07-04 | 2025-06-23 | 2024-10-03 11:47 | 2025-08-25 01:10 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2v63w 868a2v8bv 868a2v5t7 868a38mxv 868ez06an | https://app.clickup.com/t/868a2v63w https://app.clickup.com/t/868a2v8bv https://app.clickup.com/t/868a2v5t7 https://app.clickup.com/t/868a38mxv https://app.clickup.com/t/868ez06an | cdats, ilt, sus | Development | [7 empty] | 1415 hours |  | 0 |  |  |  | 2025-07-03 |  |  |  | Pending SIMs | 2025-07-03 |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | ILT |  | 2025-08-29 | Overdue | [10 empty] | 2025-05-01 |  |  |  |  | SUS | Brice LeBlanc, Shannon Bagent
868a2v25w | SUS Obsolescence Management Using CDATS Part 2 | DEVELOPMENT |  | Kristin Grappone, David Rood | HIGH | This course has been socialized and shared for final review with Jessica A. Sim/QRG - SME is set to schedule time with the appropriate team member to set up CDATS test environment/data for the microlearning &/or ILT. Decision pending. | 3 | 0 | 2025-07-04 | 2025-06-23 | 2024-10-03 11:50 | 2025-08-24 21:33 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2vbr6 868a2vc2x 868a2v5qp | https://app.clickup.com/t/868a2vbr6 https://app.clickup.com/t/868a2vc2x https://app.clickup.com/t/868a2v5qp | cdats, sus, ilt | Development | [7 empty] | 1514 hours |  | 0 |  |  |  | 2025-07-03 |  |  |  | Pending SIMs | 2025-07-03 |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | ILT |  | 2025-08-29 | Overdue | [10 empty] | 2025-05-01 |  |  |  |  | SUS | Brice LeBlanc, Shannon Bagent
868a2v5gf | PTP Accounts Payable: Verify Credit Memo - OL | DEVELOPMENT |  |  | HIGH | @Jenn Cooke I am starting SL development on this today | 7 | 0 | 2025-08-19 | 2025-07-02 | 2024-10-03 11:54 | 2025-08-24 21:57 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | ptp, ot vim, wbt | Development | [7 empty] | 482 hours |  | 0 | 2025-08-15 | [5 empty] | Anya Toms | Alpha Draft (ISG) |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v630 | PTP A/P & Supply Chain: Expense Report Posting & Errors - OL | DEVELOPMENT |  | Kris Thayer | URGENT | This is started but have to pause and redirect to storyboard/sim/qrg dev for A2R. | 5 | 0 | 2025-08-25 | 2025-08-20 | 2024-10-03 11:55 | 2025-08-25 09:54 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868dwbnug | https://app.clickup.com/t/868dwbnug | ilt, sap concur, ptp | Development | [7 empty] | 127 hours |  | 0 | [6 empty] | Kris Thayer | Alpha Draft (ISG) |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card | TRUE | ILT |  | 2025-09-05 | Due | [8 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v66p | SUS IPASS Trace: Search for Part or End Item Maintenance History | COMPLETED |  |  | NORMAL | This course has been socialized and shared for final review with DeAndre & Allen K. | 5 | 0 | 2025-06-27 | 2025-05-07 | 2024-10-03 11:55 | 2025-08-14 13:54 |  | 2025-07-15 09:20 | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | ipass, sus, wbt | Development | [7 empty] | 990 hours |  | 0 | 2025-05-28 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3 | IPASS Trace | IPASS |  | WBT |  | 2025-06-27 | Overdue | [15 empty] | SUS | Brice LeBlanc
868a2v67p | PTP SCM Requisition to Procure: Purchase Order Monitoring - OL | OUTLINES |  |  | URGENT | Some additional changes captured in Beta Review - Juan is going to verify the Tcodes | 4 | 0 | 2025-07-13 | 2025-06-30 | 2024-10-03 11:55 | 2025-08-07 07:28 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c05052 868c052bp 868c0532w 868c053k3 868c05404 868c054mr 868c0553q 868c055e4 | https://app.clickup.com/t/868c05052 https://app.clickup.com/t/868c052bp https://app.clickup.com/t/868c0532w https://app.clickup.com/t/868c053k3 https://app.clickup.com/t/868c05404 https://app.clickup.com/t/868c054mr https://app.clickup.com/t/868c0553q https://app.clickup.com/t/868c055e4 | ilt, ptp | Development | [7 empty] | 1347 hours |  | 0 | 2025-07-01 | [5 empty] | Anya Toms | Beta Revision (ISG) |  |  |  | ITC4 | Supply Chain | PO Generation, Approval & Release Strategy | TRUE | ILT |  | 2025-08-29 | Overdue | [8 empty] | 2025-07-03 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v68z | PTP A/P & Supply Chain: P-Card Statement Invoice Reconciliation - OL | OUTLINES |  | Kris Thayer | URGENT | Paused for process rewrites | 1 | 0 |  |  | 2024-10-03 11:55 | 2025-08-25 00:53 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a3c359 | https://app.clickup.com/t/868a3c359 | ilt, sap concur, ptp | Development | [7 empty] | 249 hours |  | 0 | [6 empty] | Kris Thayer | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card |  | ILT |  | 2025-09-26 | [16 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v6bk | PTP SCM Requisition to Procure: PO Edit Checks - OL | DEVELOPMENT |  |  | URGENT | @Jessica Reed Matt approved changing this course to ILT as requested by Hala. We will need to shift the approved content into a facilitator guide and develop the SL component in the ILT template | 4 | 0 | 2025-08-02 | 2025-07-21 | 2024-10-03 11:55 | 2025-08-25 11:50 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868dp11wr 868dpxqem 868dpxqp4 868dpxqzy 868dpxrer 868dpxrtm 868dpxtgd | https://app.clickup.com/t/868dp11wr https://app.clickup.com/t/868dpxqem https://app.clickup.com/t/868dpxqp4 https://app.clickup.com/t/868dpxqzy https://app.clickup.com/t/868dpxrer https://app.clickup.com/t/868dpxrtm https://app.clickup.com/t/868dpxtgd | ptp, ilt | Development | [7 empty] | 440 hours |  | 0 | [7 empty] | Beta Revision (ISG) |  |  |  | ITC4 | Supply Chain | PO Generation, Approval & Release Strategy |  | ILT |  | 2025-08-29 | Overdue |  |  |  |  | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v6gq | PTP A/P & Supply Chain: Reconcile P-Card Purchase - Add Transactional Details - OL | DEVELOPMENT |  | Kris Thayer | URGENT | @Jenn Cooke , updates from VS Lead QA complete. Also, I cannot change the development status for this in ClickUp. Says I don't have permissions to set values for that field now. | 13 | 0 | 2025-08-14 | 2025-08-08 | 2024-10-03 11:55 | 2025-08-20 06:44 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1zjn5 868c1zjzg | https://app.clickup.com/t/868c1zjn5 https://app.clickup.com/t/868c1zjzg | ilt, sap concur, ptp | Development | [7 empty] | 294 hours |  | 0 | 2025-08-13 | [5 empty] | Kris Thayer | Beta Review (SME) |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card | TRUE | ILT |  | 2025-09-05 | Overdue | [8 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v6ky | PTP A/P & Supply Chain: Expense Report Approval - OL | DEVELOPMENT |  | Kris Thayer | URGENT | @Jenn Cooke all updates are made from internal and VS Lead QA and updated all KCs to be WBT style, added a Course Review section to the FG and matched to the WBT. I am unable to change the Development Status field in ClickUp. | 11 | 0 | 2025-08-18 | 2025-08-11 | 2024-10-03 11:55 | 2025-08-20 06:44 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1znd1 | https://app.clickup.com/t/868c1znd1 | ilt, sap concur, ptp | Development | [7 empty] | 287 hours |  | 0 | 2025-08-14 | [5 empty] | Kris Thayer | Beta Review (SME) |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card | TRUE | ILT |  | 2025-09-05 | Overdue | [8 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v6qh | PTP Supplier Quality: Create & Maintain ZQUAL - OL | DEVELOPMENT |  | Jessica Reed | URGENT | @Trish Cortez I incorporated your feedback and republished to review360 | 14 | 0 | 2025-08-23 | 2025-04-16 | 2024-10-03 11:55 | 2025-08-24 01:00 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868exmzgd 868a2v7z8 868a2vbct 868c1rcht | https://app.clickup.com/t/868exmzgd https://app.clickup.com/t/868a2v7z8 https://app.clickup.com/t/868a2vbct https://app.clickup.com/t/868c1rcht | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 1611 hours |  | 0 | 2025-07-23 |  | TRUE | 2025-08-15 | 2025-08-14 |  | Jessica Reed | Beta Review (SME) |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [7 empty] | Edward Newman | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v6re | PTP Supplier Quality: Approval Code Creation/Maintenance & Text Key Mapping | PAUSED |  |  | HIGH | Still need this test script from Edward | 2 | 0 |  |  | 2024-10-03 11:55 | 2025-08-15 13:54 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2v68n 868a2v6vm 868cbxdh2 868cbxfch | https://app.clickup.com/t/868a2v68n https://app.clickup.com/t/868a2v6vm https://app.clickup.com/t/868cbxdh2 https://app.clickup.com/t/868cbxfch | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 674 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3 | Supplier Quality | Supplier Approvals Certification |  | WBT |  | 2025-09-12 | [8 empty] | Edward Newman | [7 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v78c | PTP MCE: Contracts & Outline Agreements | DEVELOPMENT |  | Jenn Cooke | NORMAL | @Trish Cortez is there someone available to help us get the shell started in Storyline? | 4 | 0 | 2025-07-14 | 2025-07-10 | 2024-10-03 11:56 | 2025-08-06 11:08 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1mknh 868c1mmct | https://app.clickup.com/t/868c1mknh https://app.clickup.com/t/868c1mmct | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1113 hours |  | 0 | 2025-07-10 | [5 empty] | Jenn Cooke | Alpha Draft (ISG) |  |  |  | ITC4 | MCE | MCE Lifecycle Management & Reporting | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-06-03 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v7cy | PTP SCM: Sourcing Events (RFX Processing & Award) - OL | OUTLINES |  | Brice LeBlanc | URGENT |  | 0 | 0 | 2025-08-29 |  | 2024-10-03 11:56 | 2025-08-19 14:12 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2v7fq 868a2v8j8 868a2vbbw | https://app.clickup.com/t/868a2v7fq https://app.clickup.com/t/868a2v8j8 https://app.clickup.com/t/868a2vbbw | wbt, ptp | Development | [7 empty] | 993 hours |  | 0 | [6 empty] | Brice LeBlanc | Alpha Review (SME) |  |  |  | ITC4 | Supply Chain | Sourcing Events (RFX Processing & Award) |  | WBT |  | 2025-09-12 | [16 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v7v1 | PTP Accounts Payable: Process Payments | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-03 11:56 | 2025-08-07 10:59 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a37b6p 868a37beg 868a37bqb | https://app.clickup.com/t/868a37b6p https://app.clickup.com/t/868a37beg https://app.clickup.com/t/868a37bqb | wbt, ptp | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v7x8 | PTP MCE: MCE Inventory & Parts Reporting | DEVELOPMENT |  |  | NORMAL | Course wrapper approved by Steve Foley, still need to add QRGs before we can consider it complete | 9 | 0 | 2025-07-21 | 2025-06-03 | 2024-10-03 11:56 | 2025-08-06 11:07 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1mzwh 868c1n2qg | https://app.clickup.com/t/868c1mzwh https://app.clickup.com/t/868c1n2qg | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 605 hours |  | 0 | [7 empty] | Pending SIMs |  |  |  | ITC4 | MCE | MCE Lifecycle Management & Reporting | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-06-05 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v81g | PTP SCM Requisition to Procure: Create Purchase Order - OL | DEVELOPMENT |  |  | URGENT | @Jenn Cooke , QA is complete. @Anya Toms , nice work! Comments in R360 pane. | 8 | 0 | 2025-07-19 | 2025-06-25 | 2024-10-03 11:57 | 2025-08-18 10:21 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c04t62 868c04v0k | https://app.clickup.com/t/868c04t62 https://app.clickup.com/t/868c04v0k | ilt, ptp | Development | [7 empty] | 942 hours |  | 0 | [6 empty] | Anya Toms | QA Revision |  |  |  | ITC4 | Supply Chain | PO Generation, Approval & Release Strategy | TRUE | ILT |  | 2025-08-29 | Overdue | [8 empty] | 2025-06-25 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v87r | PTP SCM Requisition to Procure: Purchase Requisition Handover - OL | OUTLINES |  | Brice LeBlanc | URGENT |  | 0 | 0 |  | 2025-07-18 | 2024-10-03 11:57 | 2025-08-24 22:49 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868dp0b67 868dp0bme 868dp0bxk 868dp0eke | https://app.clickup.com/t/868dp0b67 https://app.clickup.com/t/868dp0bme https://app.clickup.com/t/868dp0bxk https://app.clickup.com/t/868dp0eke | ptp, wbt | Development | [7 empty] | 634 hours |  | 0 | [6 empty] | Brice LeBlanc | In QA |  |  |  | ITC4 | Supply Chain | Purchase Requisition Mgmt (MRP/Non-MRP) & Approval |  | WBT |  | 2025-09-26 |  |  |  | 2025-08-04 | Kameron Teal | [11 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v8me | PTP SCM Requisition to Procure: PO Expediting (Expedite Fee Process) - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2024-10-03 11:57 | 2025-08-25 10:49 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c0w342 868c0w3qn 868c0w40e 868c0w4j8 868c0w55v 868c0w650 | https://app.clickup.com/t/868c0w342 https://app.clickup.com/t/868c0w3qn https://app.clickup.com/t/868c0w40e https://app.clickup.com/t/868c0w4j8 https://app.clickup.com/t/868c0w55v https://app.clickup.com/t/868c0w650 | ptp, wbt | Development | [7 empty] | 993 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Supplier PO Communication, Acknowledgement, & Schedule Mgmt. |  | WBT |  | 2025-09-26 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v8qx | PTP Supplier Quality: Vendor Approvals | PAUSED |  |  | HIGH | Still need this test script from Edward | 2 | 0 |  |  | 2024-10-03 11:57 | 2025-08-15 13:54 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1rx8z 868c1rygb 868cbxjc4 | https://app.clickup.com/t/868c1rx8z https://app.clickup.com/t/868c1rygb https://app.clickup.com/t/868cbxjc4 | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 674 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3 | Supplier Quality | Supplier Approvals Certification |  | WBT |  | 2025-09-12 | [8 empty] | Edward Newman | [7 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v9g6 | PTP SCM Requisition to Procure: Purchase Order Close Out - OL | OUTLINES |  | Jessica Reed | URGENT | @Jessica Reed Matt approved the change to ILT for this course, as requested by Hala. We will need to move this content into a facilitator guide | 2 | 0 | 2025-08-10 | 2025-07-18 | 2024-10-03 11:58 | 2025-08-24 22:48 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c04wwr 868dpxw88 868dpxzx5 868dpy0h4 | https://app.clickup.com/t/868c04wwr https://app.clickup.com/t/868dpxw88 https://app.clickup.com/t/868dpxzx5 https://app.clickup.com/t/868dpy0h4 | ptp, ilt | Development | [7 empty] | 634 hours |  | 0 |  |  |  | 2025-08-15 | 2025-08-07 |  | Jessica Reed | Beta Review (SME) |  |  |  | ITC4 | Supply Chain | PO Generation, Approval, & Release Strategy II |  | ILT |  | 2025-09-05 | Overdue | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2v9ne | PTS Prod Ops: Review & Finalize Master Schedule - QRG | PAUSED |  |  | HIGH | Paused, process may be replaced in ITC3 | 4 | 0 |  |  | 2024-10-03 11:58 | 2025-08-25 00:38 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | p2s, qrg | Development | [7 empty] | 1445 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3 | Prod Ops | Perform Production Planning & Master Scheduling | TRUE | QRG |  | 2025-09-12 | [9 empty] | 2025-07-25 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868a2va5u | PTP Accounts Payable: Submit Debit/Credit Request to A/P - OL | DEVELOPMENT |  |  | HIGH | Updates captured in today's meeting, outline approved by Gina and Crystal for development | 4 | 0 | 2025-07-18 | 2025-07-02 | 2024-10-03 11:58 | 2025-08-24 21:50 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | ptp, ot vim, wbt | Development, ✍ Risk Register | [7 empty] | 293 hours |  | 0 |  |  | TRUE |  |  |  | Anya Toms | Ready for Development |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2va99 | PTP MCE: Purchasing Documents | DEVELOPMENT |  |  | NORMAL | Outline approved by Tori 7.9.25, zero changes needed | 7 | 0 | 2025-07-19 | 2025-07-03 | 2024-10-03 11:58 | 2025-08-06 11:08 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1mnu6 868c1mp7q 868c1mppw | https://app.clickup.com/t/868c1mnu6 https://app.clickup.com/t/868c1mp7q https://app.clickup.com/t/868c1mppw | ptp, wbt | Development | [7 empty] | 1130 hours |  | 0 | [6 empty] | Anya Toms | Ready for Development |  |  |  | ITC4 | MCE | MCE Lifecycle Management & Reporting | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-06-05 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2vbj9 | PTP SCM Requisition to Procure: Non-Consumable Property (Drop Shipping, BFM, GFE, CFE) - OL | PAUSED |  |  | NORMAL | QA completed 7.15.25, took directly to a SME meeting afterward and started Alpha Review | 2 | 0 | 2025-07-26 | 2025-07-08 | 2024-10-03 11:59 | 2025-08-15 13:53 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c175ec 868dq06q5 | https://app.clickup.com/t/868c175ec https://app.clickup.com/t/868dq06q5 | ptp, wbt | Development | [7 empty] | 578 hours |  | 0 | 2025-07-08 | [6 empty] | Paused |  |  |  | ITC3 | Supply Chain | Non-Consumable Property: Drop Shipping, BFM, GFE, CFE | TRUE | WBT |  | 2025-09-12 | Overdue | [7 empty] | Matt Berinato | 2025-06-05 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2vbm7 | PTP A/P & Supply Chain: Storing P-Card Packages - OL | OUTLINES |  | Kris Thayer | URGENT | Paused for process rewrites | 1 | 0 |  |  | 2024-10-03 11:59 | 2025-08-25 00:56 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1zqwr 868c1zrkm 868c1zt02 | https://app.clickup.com/t/868c1zqwr https://app.clickup.com/t/868c1zrkm https://app.clickup.com/t/868c1zt02 | ilt, ot xecm, sap concur, ptp | Development | [7 empty] | 463 hours |  | 0 | [6 empty] | Kris Thayer | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card | TRUE | ILT |  | 2025-09-26 | [9 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2vbw2 | PTP MCE: BOM Transactions - OL | DEVELOPMENT |  |  | NORMAL | Approved for development 7.1.25 | 7 | 0 | 2025-07-06 | 2025-06-18 | 2024-10-03 12:00 | 2025-08-15 09:48 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868c1n35e 868dqkuuw | https://app.clickup.com/t/868c1n35e https://app.clickup.com/t/868dqkuuw | ptp, wbt | Development | [7 empty] | 1322 hours |  | 0 | [6 empty] | Priscilla Holguin | Ready for Development |  |  |  | ITC4 | MCE | MCE Lifecycle Management & Reporting | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-06-05 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a2vbxu | A2R CLRP Capital: Capital Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2024-10-03 12:00 | 2025-08-24 22:16 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 1828 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | CLRP | No L3 Custom Content |  | WBT |  | 2025-09-26 | [16 empty] | A2R | Trish Cortez, Steve Hile
868a2vc2g | PTP MCE: Manage Purchase Info Records | DEVELOPMENT |  |  | NORMAL | Approved for development 7.1.25 | 6 | 0 | 2025-06-23 | 2025-06-10 | 2024-10-03 12:00 | 2025-08-06 11:07 |  |  | Keren Daniel | Lockheed Martin | Course Development | Development | 868a2vb3r 868c1mtyd | https://app.clickup.com/t/868a2vb3r https://app.clickup.com/t/868c1mtyd | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1322 hours |  | 0 | [7 empty] | Ready for Development |  |  |  | ITC4 | MCE | MCE Lifecycle Management & Reporting | TRUE | WBT |  | 2025-09-12 | Overdue | - [@Anya Toms](#81516068) started the outline and requested QA from [@Shannon Bagent](#32129693). - [@Shannon Bagent](#32129693) completed QA and sent edits to [@Anya Toms](#81516068). - Outline was posted for Alpha SME review by [@Jenn Cooke](#42510316) on 6/12/25. - Development status updated to Alpha Review (SME); due date set for 6/23/25. |  |  |  | TRUE |  |  |  | 2025-06-05 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a36nb0 | PTP Accounts Payable: Create Invoice using Spreadsheet Upload | OUTLINES |  |  | HIGH | @Jenn Cooke @Jessica Visser I can help. Sent the file path 🙂 | 10 | 0 | 2025-08-20 | 2025-08-20 | 2024-10-04 06:10 | 2025-08-25 16:05 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a36ng9 | https://app.clickup.com/t/868a36ng9 | wbt, ptp, ot vim | Development, ✍ Risk Register | [7 empty] | 81 hours |  | 0 |  |  | TRUE |  |  |  |  | Ready for QA |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-12 | Overdue | - [@Anya Toms](#81516068) confirmed the outline was ready for QA on 06/02. - [@Jenn Cooke](#42510316) completed QA and sent the outline for review on 06/03. - Task status was updated to 'Due' on 06/13. |  |  | Ashley Parker |  |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a3719f | PTP Accounts Payable: Submit/Approve Expedited Payment Requests, Pt. 1 (Submit Expedite Request Form) - SB | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:37 | 2025-08-24 21:52 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37228 | PTP Accounts Payable: Submit/Approve Expedited Payment Requests, Pt. 2 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:38 | 2025-08-24 21:54 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a371fg 868a371j7 868a371r2 | https://app.clickup.com/t/868a371fg https://app.clickup.com/t/868a371j7 https://app.clickup.com/t/868a371r2 | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a372rj | PTP Accounts Payable: Approve/Reject Expedited Payment Requests | OUTLINES |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:40 | 2025-08-06 11:20 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a373tm 868a373hd | https://app.clickup.com/t/868a373tm https://app.clickup.com/t/868a373hd | wbt, ptp | Development | [7 empty] | 1944 hours |  | 0 | [6 empty] | Anya Toms | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a372yd | PTP Accounts Payable: Process Hedge Payments, Pt. 1 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:40 | 2025-08-25 01:16 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a378p3 868a378yq | https://app.clickup.com/t/868a378p3 https://app.clickup.com/t/868a378yq | ptp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37378 | PTP Accounts Payable: Process Hedge Payments, Pt. 2 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:41 | 2025-08-25 01:17 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a3792j 868c1xdym | https://app.clickup.com/t/868a3792j https://app.clickup.com/t/868c1xdym | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-12 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a3748x | PTP Accounts Payable: Review & Block Automatic Payments | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:43 | 2025-08-25 01:24 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a3741k 868a374cz | https://app.clickup.com/t/868a3741k https://app.clickup.com/t/868a374cz | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37aw4 | PTP Accounts Payable: Process Exceptions | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 06:59 | 2025-08-07 10:58 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37akz 868a37atn | https://app.clickup.com/t/868a37akz https://app.clickup.com/t/868a37atn | wbt, ptp | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37bwj | PTP Accounts Payable: Process Escheatment Payments | OUTLINES |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 07:01 | 2025-08-06 11:21 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37crc 868a37cx9 868a37cgb 868a37cc3 | https://app.clickup.com/t/868a37crc https://app.clickup.com/t/868a37cx9 https://app.clickup.com/t/868a37cgb https://app.clickup.com/t/868a37cc3 | wbt, ptp | Development | [7 empty] | 1944 hours |  | 0 | [6 empty] | Anya Toms | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37d3x | PTP Accounts Payable: Process Supplier Refunds (Create & Clear Supplier Refunds) | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 07:04 | 2025-08-25 01:19 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37fep 868a37fkt 868a37fx1 | https://app.clickup.com/t/868a37fep https://app.clickup.com/t/868a37fkt https://app.clickup.com/t/868a37fx1 | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [5 empty] | TRUE |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37dfy | PTP Accounts Payable: Process Supplier Refunds (Create Credit Memo with SALT) | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 07:05 | 2025-08-07 11:01 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37evm 868a37f2u | https://app.clickup.com/t/868a37evm https://app.clickup.com/t/868a37f2u | wbt, ptp | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a37f89 | PTP Accounts Payable: Review Supplier Refunds (Clear Tax Correction Documents & Credit Memo) - SB | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2024-10-04 07:08 | 2025-08-24 21:26 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a3811p | PTP Accounts Payable: Process Direct Debit Payments - QRG | STORYBOARD |  |  | LOW | @Jenn Cooke ready for Alpha review | 4 | 0 | 2025-08-09 | 2025-06-20 | 2024-10-04 07:43 | 2025-08-10 01:00 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, dap, qrg | Development | [7 empty] | 1589 hours |  | 0 | 2025-06-20 | [6 empty] | Alpha Review (SME) |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | DAP |  | 2025-09-26 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868a4yd19 | PTS Prod Ops: Planning Execution - OL | DEVELOPMENT |  | Alisha Khan | HIGH | Few additional minor comments on second QA. Also still missing QA. Assigned the QRG to @Alisha Khan . | 20 | 0 | 2025-08-09 | 2025-05-12 | 2024-10-08 07:30 | 2025-08-25 00:31 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868b41hhe | https://app.clickup.com/t/868b41hhe | p2s, wbt | Development | [7 empty] | 604 hours |  | 0 | 2025-08-05 | [5 empty] | Alisha Khan | QA Revision |  |  |  | ITC3 | Prod Ops | Planning Execution | TRUE | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-06-13 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868auyu08 | PTS Prod Ops: Outbound Delivery Creation & Processing - OL | DEVELOPMENT |  | David Rood | URGENT | @Eugene Deloatch and @Alisha Khan David completed edits on this course, the SL file is in Process Outbound Shipping>Storyline >Draft folder ready for SME review. | 45 | 0 | 2025-08-10 | 2024-11-13 | 2024-11-15 07:39 | 2025-08-25 14:51 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2uwcw 868b46g2k 868b46gab 868b46gx4 868b46vu4 | https://app.clickup.com/t/868a2uwcw https://app.clickup.com/t/868b46g2k https://app.clickup.com/t/868b46gab https://app.clickup.com/t/868b46gx4 https://app.clickup.com/t/868b46vu4 | p2s, ilt, sen, mfc | Development, ✍ Risk Register | [7 empty] | 311 hours |  | 0 |  |  | TRUE |  |  |  | David Rood, Mary Beth Finigan | Ready for SME Review |  |  |  | ITC2 | Prod Ops | Process Outbound Shipping |  | ILT |  | 2025-09-19 | Overdue | - Development status updated to 'Final Review & Sign off (SME)' by [@Shannon Bagent](#32129693) on 6/12/25. - [@Mary Beth Finigan](#81509212) confirmed in the 5/27 SME meeting that no changes or updates were required. - Recent comments indicate all major steps and QA have been completed, with only final SME review pending. | [14 empty] | PTS | Shannon Bagent, Eugene Deloatch
868awzyaw | ALL AREAS SAP S/4HANA: Essentials & Navigation - OL | DEVELOPMENT |  | Eugene Deloatch | HIGH | 7/14: Received QA feedback from Shannon | 4 | 0 |  | 2024-11-01 | 2024-11-19 12:35 | 2025-08-25 00:48 |  |  | Erin Cooke | Lockheed Martin | Course Development | Development | 868f5wc5w 868f5wced 868f5wd0n | https://app.clickup.com/t/868f5wc5w https://app.clickup.com/t/868f5wced https://app.clickup.com/t/868f5wd0n | all users, wbt | Development | [7 empty] | 244 hours |  | 0 | [6 empty] | Eugene Deloatch | Beta Review (SME) |  |  |  | Not part of ITC |  |  |  | WBT |  | 2025-08-29 | [17 empty] | Trish Cortez, Shannon Bagent
868b3zqc6 | PTS Prod Ops: Create Material Master Record and Views - OL | OUTLINES |  | Alisha Khan | HIGH | @Alisha Khan This course is still in scope for R1. The one that's future release in the MC is Create Material Master. | 8 | 0 | 2025-07-25 | 2025-06-23 | 2024-12-02 10:10 | 2025-08-24 23:49 |  |  | Emilie Martin | Lockheed Martin | Course Development | Development | 868b3zyfd | https://app.clickup.com/t/868b3zyfd | p2s, wbt | Development | [7 empty] | 318 hours |  | 0 | 2025-06-23 |  |  |  | 2025-08-05 |  | Alisha Khan | Beta Revision (ISG) |  |  |  | ITC4 | Prod Ops | Complete & Manage Material Master | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-07-25 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868b41eng | PTS Prod Ops: Create Purchase Requisition - QRG | PREDEVELOPMENT |  | Jessica Visser | NORMAL |  | 0 | 0 |  |  | 2024-12-02 11:07 | 2025-08-24 23:51 |  |  | Emilie Martin | Lockheed Martin | Course Development | Development |  |  | p2s, qrg | Development | [7 empty] | 628 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC4 | Prod Ops | Fulfillment Management |  | QRG |  | 2025-09-26 | [16 empty] | PTS | Shannon Bagent, Eugene Deloatch
868b41f16 | PTS Prod Ops: Handover Purchase Requisition - QRG | PREDEVELOPMENT |  | Jessica Visser | NORMAL | Per SME: Changed from Release Requisition to Handover Purchase Requisition | 1 | 0 |  |  | 2024-12-02 11:07 | 2025-08-25 00:17 |  |  | Emilie Martin | Lockheed Martin | Course Development | Development |  |  | qrg, p2s | Development | [7 empty] | 628 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC4 | Prod Ops | Fulfillment Management |  | QRG |  | 2025-09-26 | [16 empty] | PTS | Shannon Bagent, Eugene Deloatch
868b45hfr | PTS Prod Ops: Perform Cycle Count - OL | DEVELOPMENT |  | Alisha Khan | HIGH | This is ready for first QA. Please note - I did not add in the slide for roles and also for the Signavio flow. I'd like to confirm the correct flow first as I can't find it in Signavio. (Both of these are in the welcome section) Note this is my first ILT dev so any feedback is appreciated if i missed a step, etc. File link uploaded to SharePoint Perform Cycle Count Folder. @Shannon Bagent @Eugene Deloatch | 20 | 0 | 2025-07-26 | 2025-06-12 | 2024-12-02 12:40 | 2025-08-25 00:28 |  |  | Emilie Martin | Lockheed Martin | Course Development | Development | 868cqqjqt 868e0rzu7 868ebjpy7 868b45vtr | https://app.clickup.com/t/868cqqjqt https://app.clickup.com/t/868e0rzu7 https://app.clickup.com/t/868ebjpy7 https://app.clickup.com/t/868b45vtr | p2s, ilt | Development | [7 empty] | 338 hours |  | 0 | [6 empty] | Alisha Khan | Ready for QA |  |  |  | ITC4 | Prod Ops | Warehouse Inbound Processing |  | ILT |  | 2025-09-19 | Overdue | - Outline draft started and updated for new ILT template changes. - QA completed by [@Alisha Khan](#81582372); updates made and file re-uploaded. - Final QA completed by [@Eugene Deloatch](#81458171). - Task moved to Alpha Review (SME) stage. | [14 empty] | PTS | Shannon Bagent, Eugene Deloatch
868b6enaq | PTP Accounts Payable: AP Analytics - OL | OUTLINES |  |  | LOW |  | 0 | 0 |  |  | 2024-12-05 10:11 | 2025-08-14 10:28 |  |  | Emilie Martin | Lockheed Martin | Course Development | Development |  |  | ilt, ptp, ot xecm | Development | [7 empty] | 1513 hours |  | 0 | [6 empty] | Anya Toms | Ready for OL Draft |  |  |  | ITC4 | Accounts Payable | Procurement & A/P Analytics | TRUE | ILT |  | 2025-09-19 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868bd3171 | PTS DYNSCH: Intro to Dynamic Scheduling - OL | COMPLETED |  |  | HIGH | Ian review and lock down 8/19 | 25 | 0 | 2025-07-25 | 2025-06-17 | 2024-12-17 06:57 | 2025-08-21 15:57 |  | 2025-08-14 07:04 | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | aps, p2s, wbt | Development | [7 empty] | 273 hours |  | 0 | 2025-06-29 |  |  |  | 2025-07-18 |  |  | Hand off to OCM Team | 2025-08-05 |  |  | Not part of ITC | DYNSCH | No L3 Custom Content | TRUE | WBT |  | 2025-08-12 | Overdue | [9 empty] | 2025-08-14 | [5 empty] | PTS | Shannon Bagent, Eugene Deloatch
868byrubk | R2R Tax Accounting: Defend Indirect Tax Audit | COMPLETED | 2/19 level set call with Adrienne: for all Indirect items, Ankine should review and sign off first, and then Adrienne Jade started outline 6/5 Ron signed off outline NOTE ON AT-RISK STATUS: sprint is scheduled to end 6/13 but as of 6/6 we do not have the information for the last two remaining items on extract sales transaction data. See those entries for more information; short story is that Adrienne and Ankine are both waiting on processes that currently have defects. 6/13 both extract sales transaction items have been approved! Only thing outstanding is the full WBT, which is in heavy development. Still marked at risk because technically over sprint deadline (I can't move sprints) 6/12 SG QA of development so far by Brenda and Dan; sent a round of edits; Dan completing Brenda made them and it's ready for a final QA 6/17 SG final QA and still some edits left to do 6/18 presented to client, who requested some changes (one small design change on a slide and some changed wording). SG asked Brenda to make these changes; she will reach out if she needs help--there is one design request that might take group effort. NOTE: Ankine also wants to review the course over the weekend, saying "I have some thoughts." SG sent via email 6/18. Go ahead and make changes and leave the comments unresolved so she can see--she likes to see our work shown. When she makes more comments, we will do another round of edits for her. 6/23 Brenda made Ankine's suggested changes; SG QA and sent back for a few more updates 6/24 final QA and sent back to SMEs for another review/signoff 6/25 went over the comments and got Ron's in today's call; now need developer to implement them 6/26 Dan responded to all comments; course sent back to Ron and Adrienne for signoff and then will go to Adrienne 6/30 Ron approved via email! And Adrienne did too |  | LOW | @Sarah Griffis all corrections fixed with the exception of the questions waiting for SME answers | 5 | 0 | 2025-06-30 | 2025-03-06 | 2025-01-14 11:17 | 2025-08-14 13:51 |  | 2025-08-14 11:07 | Trish Cortez | Lockheed Martin | Course Development | Development | 868a2v6uu 868dj3w3u 868dj3w7w | https://app.clickup.com/t/868a2v6uu https://app.clickup.com/t/868dj3w3u https://app.clickup.com/t/868dj3w7w | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-06-17 | 2025-06-18 | TRUE | 2025-06-24 | 2025-06-18 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Tax Accounting | Consolidations & Tax (Indirect Tax - Defend Audit L4) |  | WBT |  | 2025-06-30 | Overdue | - [@Jade Brown](#96013983) started the outline; [@Ron](#unknown) signed off on it. - Outline went through SME review; needs about 60 more minutes for full approval. - SL development started by [@Brenda Mayfield](#81508313). QA edits sent by Brenda and Dan on 6/12. - Task is at risk due to missing info for two sales transaction data items; Alpha Draft status set by [@Sarah Griffis](#42510312). | [8 empty] | 2025-06-30 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bytq3p | R2R Tax Accounting: Generate Ad Hoc Tax Fixed Asset Reports (Ad Hoc Reporting) | COMPLETED | Plan to review with SME 3/18. Dan will attend 3/11 meeting going over the SBs for lessons within the course and gather relevant material. 3/17 assigned to Jenn for QA. 3/17 Jenn completed QA and returned to Dan; passed to Kristin to review before presenting to client 3/18 SG QA of outline before presentation to client 3/18 Tammy and Adrienne signed off on outline 3/20 Jessica began development in Storyline 3/25 Kristin performed initial QA and returned request for edits to Jessica 3/26 Jessica responding to Kristin's QA 3/26 Edits are complete and ready for next review More edits by Jess in discussion with Kris, Shannon, Trish 4/3 SG QA and returned for edits; same 4/4 4/23 SG QA and returned to Dan for a few edits 4/24 sent to SME for final review/signoff by EOD 4/30 4/25 Adrienne signoff via email |  | HIGH | @Sarah Griffis Making updates this evening. Should be ready to go when I ping ya later this afternoon | 20 | 0 | 2025-04-25 | 2025-03-04 | 2025-01-14 11:40 | 2025-08-14 13:50 |  | 2025-08-14 11:09 | Trish Cortez | Lockheed Martin | Course Development | Development | 868a2vagk 868a2v5wq 868d13tjp 868a2vb6m 868a2vb3g 868a2v8jj 868a2v5kk 868a2v93e 868a2v6xd 868a2v91u | https://app.clickup.com/t/868a2vagk https://app.clickup.com/t/868a2v5wq https://app.clickup.com/t/868d13tjp https://app.clickup.com/t/868a2vb6m https://app.clickup.com/t/868a2vb3g https://app.clickup.com/t/868a2v8jj https://app.clickup.com/t/868a2v5kk https://app.clickup.com/t/868a2v93e https://app.clickup.com/t/868a2v6xd https://app.clickup.com/t/868a2v91u | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-04-23 | 2025-04-24 | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC2 | Tax Accounting | Consolidations & Tax: Indirect Taxes- Manage Tax Fixed Assets L4 |  | WBT |  | 2025-04-25 | Overdue | [9 empty] | 2025-04-25 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byukqg | R2R Tax Accounting: US Federal Tax | OUTLINES | 2/20 Ankine said they're unsure whether ITC3 or 4; repository data as of that data schedules it for 3B 5/27 Adrienne confirmed ITC3B is their cycle; says "still not closed due to many defects. Our new ECD for all defects to be closed is 6/6/2025. I will let you know if some finish earlier." 6/10 update email from Adrienne: "We are updating all direct test scripts this week. The State Provision interim script will be the first state script to get completed. I will send the test scripts as they are completed. we are targeting total completion by end of next week." Plan is to un-pause courses as we get the scripts and they look viable to start on 6/18 discussion with Adrienne Suber (Hala and Chris Fisher present for first 30 mins of hour long call); USE FOR DEVELOPMENT: Scripts still defective and cannot use yet; she will still get them to us as they become available Federal return has to go first. Make this the prerequisite to State Tax course US Federal Tax Return, US Federal Tax Provision, and Manage Global Tax Provision L3s are repetitive; we have reduced their redundancy and at Adrienne's request and approval designed 1 single Federal Tax course that has only the SAP tasks related to federal tax. See below on the relationship between these 3 L3s, which we will need to explain in the WBT: Just as with state, provision = a "dress rehearsal" to the actual tax return. Interim = just the quarter point provision calculation; this is what is reflected in the Manage Global Tax Provision L3. Note that the actual tasks of global tax provision on the quarterly basis are TRCS, which is why they do not appear here. 8/18 Alpha review with Adrienne, but drastically redrawn because she redefined the curriculum again (a third time) in the same call. 8/19 cleaned up from yesterday's call and sent for offline review; will resume review again as a team 8/26 and try to get written signoff. | Brenda Mayfield | LOW |  | 0 | 0 | 2025-08-28 | 2025-08-14 | 2025-01-14 11:55 | 2025-08-25 01:02 |  |  | Trish Cortez | Lockheed Martin | Course Development | Development | 868a2va5a 868a2vay1 868a2v66c 868eefxxw 868eefy14 868eefy5m 868eefy9a 868f85bze 868f85c9m | https://app.clickup.com/t/868a2va5a https://app.clickup.com/t/868a2vay1 https://app.clickup.com/t/868a2v66c https://app.clickup.com/t/868eefxxw https://app.clickup.com/t/868eefy14 https://app.clickup.com/t/868eefy5m https://app.clickup.com/t/868eefy9a https://app.clickup.com/t/868f85bze https://app.clickup.com/t/868f85c9m | r2r, wbt | Development | [7 empty] | 338 hours |  | 0 | 2025-08-14 | [5 empty] | Daniel Die, Brenda Mayfield | Beta Review (SME) |  |  |  | ITC4 | Tax Accounting | Consolidations & Tax (US Federal Tax Provision - Year End L4) |  | WBT |  | 2025-09-05 | [16 empty] | R2R | Sarah Griffis, Trish Cortez
868bywewc | R2R Tax Accounting: Withholding Tax on Procurement Invoices | COMPLETED | SL file QA by Sarah 2/3; only Adrian weighed in on a sim 2/13 Sarah requested Phil and Adrian comments by EOD 2/18 - we will make any edits and Adrienne confirmed she will review and sign off when they are done Phil and Adrian comments addressed and Ankine weighed in Escalation week ending 2/14 and again week ending 2/21 Team implemented Ankine's comments Re-sent courses 3/3 requesting final signoff by EOD 3/6; sent a corresponding escalation email to Sarah Gentry and Chris Applegate the same day 3/6 communication from Ankine in call: 3/13 followed up with Ankine requesting timeline for getting her feedback 3/17 she responded that she is immersed in defect resolution to complete testing deadlines and aims to get us feedback by 3/23 3/23 Ankine sent clear, actionable feedback. Trish and Sarah will evaluate 3/25 in a call. 3/24 told Ankine we would get edited material back to her by EOW next week (first week of April); putting on a brief hold as we finish our sprint to the ITC2 training deadline Withholding Tax Master Data Management is a prerequisite Goal to send Ankine all ITC1 courses by 4/4 4/10 sent all ITC1 courses to Ankine for review/signoff by 4/16 4/23 Ankine signed off; sent to Adrienne for final signoff 4/23 Adrienne final signoff |  | URGENT | Change this course title to "Withholding Tax on Procurement Invoices" | 7 | 0 | 2025-04-23 |  | 2025-01-14 12:42 | 2025-08-15 08:23 |  | 2025-08-15 08:23 | Erin Cooke | Lockheed Martin | Course Development | Development | 868aj55pc 868ahpf3p 868ar437y 868aprph1 868a2uwgm 868ahpfy3 | https://app.clickup.com/t/868aj55pc https://app.clickup.com/t/868ahpf3p https://app.clickup.com/t/868ar437y https://app.clickup.com/t/868aprph1 https://app.clickup.com/t/868a2uwgm https://app.clickup.com/t/868ahpfy3 | r2r, wbt | Development | [7 empty] | 247 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | ITC1 | Tax Accounting | Consolidations & Tax (Withholding Tax Payables Collection L4) |  | WBT |  | 2025-04-23 | Overdue | [9 empty] | 2025-04-24 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byybuu | R2R Financial Accounting: Revenue Recognition | COMPLETED | Outline is making halted progress--we require each SB to be approved before making changes to the outline. NOTE ON AT-RISK STATUS: Every SB takes a lot of time to complete--the process is extremely complicated and only just got approved, so the SMEs are not familiar with it and need to take a lot of time to explain it to us. Each SB has been averaging nearly a full hour of review time, there are a lot of them, and we need them complete before entering them into the outline in order to review the outline. 6/4 Misty said this process is changing. She will not be able to give us more specifics till next week. Due to news that the process will be rewritten, this course has been moved to Paused. 6/11 Misty and Billy let us know that there's a change to the PT2-RAP in this process, but it doesn't impact training--we can move ahead as planned! Moved out of Paused, but note that lag times in each individual item's timeline are due to this pause. Waiting to develop outline in order to avoid rework: 8 outstanding SBs/sims and want content firmed up first. 7/8 Jade drafted outline! 7/9 SG outline QA and passed to Dan to answer a couple of technical questions; queued up for SME review 7/9 reviewed with SMEs and got to page 6. We need an updated process flow and changes to the outline. We will then resume in next call by reviewing changes and continuing outline review. 7/16 continued reviewing outline; did not complete with SMEs due to needing to review 3 WBTs. Billy made a few changes to lesson 1. Brenda and Dan working together to implement. 7/22 Billy signed off during call! In dev already with Dan 7/23 SG QA and Dan back and forth addressing comments and getting ready for SME review 7/23 Billy approved course in SME call! NOTE "pending" status is not due to change impacts but to publishing the finalized flow. Update: correct flow is linked and in course; course is complete. |  | URGENT | @Daniel Die see my 7/9 note here from today for why it's in Alpha review. When you're finished editing I can plop it back to ready for SME review. | 7 | 0 | 2025-07-23 | 2025-05-15 | 2025-01-14 13:26 | 2025-08-14 13:54 |  | 2025-08-14 08:51 | Jade Brown | Lockheed Martin | Course Development | Development | 868dvnh86 868a482h5 868a481xa 868a480vg 868a47z89 868a47kpr 868a47d04 868e1b0kq 868e1b0n8 | https://app.clickup.com/t/868dvnh86 https://app.clickup.com/t/868a482h5 https://app.clickup.com/t/868a481xa https://app.clickup.com/t/868a480vg https://app.clickup.com/t/868a47z89 https://app.clickup.com/t/868a47kpr https://app.clickup.com/t/868a47d04 https://app.clickup.com/t/868e1b0kq https://app.clickup.com/t/868e1b0n8 | mfc, r2r, wbt | Development, ✍ Risk Register | [7 empty] | 271 hours |  | 0 |  |  | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC3B | Financial Accounting | Collect & Process Actuals (Update Project Finance Master Data L4) |  | WBT |  | 2025-07-23 | Overdue | [9 empty] | 2025-07-23 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byye4b | R2R Financial Accounting: Settle Costs/Revenues | COMPLETED | NOTE ON AT-RISK STATUS: Need to confirm SB content on complex process before outlining and have not gotten enough SME time to do so 6/13 Billy Cambers assembled a spreadsheet with all review items in backlog to distribute to appropriate SMEs for review. Since he is sending this out, all items are technically in Alpha review since handed off. Working with Billy to implement a signoff protocol with reviews being done this way. 6/18 Billy signed off outline! 7/2 WBT drafted and sent to SG for QA 7/2 SG WBT QA and sent back for light revisions 7/2 reviewed with SME in call who requested some changes. Dan will make then we will get back to Billy 7/7 SG WBT QA and sent back for revisions 7/7 SG WBT final QA; ready for SME Beta review on 7/9 7/9 reviewed in SME call a second time; a couple small changes requested--SL glitched and did not update the process flow slide. Dan made and emailed back to client for final review/signoff 7/16 Billy signed off in call! |  | NORMAL | This is ready for SME review | 6 | 0 | 2025-07-16 | 2025-05-15 | 2025-01-14 13:27 | 2025-08-14 13:54 |  | 2025-08-14 08:52 | Jade Brown | Lockheed Martin | Course Development | Development | 868a48cuf 868a48c3t 868a488va | https://app.clickup.com/t/868a48cuf https://app.clickup.com/t/868a48c3t https://app.clickup.com/t/868a488va | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 271 hours |  | 0 | 2025-07-07 |  | TRUE | 2025-07-07 |  |  |  | Hand off to OCM Team |  |  |  | ITC3 | Financial Accounting | Collect & Process Actuals (Settle Costs/ Revenues L4) |  | WBT |  | 2025-07-16 | Overdue | [9 empty] | 2025-07-16 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byygr4 | R2R Financial Accounting: Run Financial Reports | COMPLETED | Note that this course spans multiple L3s which lie in different ITC cycles. 1 L3 is in ITC2 so we started the course and outline in ITC2 Kristin drafted outline for Alpha review 3/6 - Outline structure with the following applicable info. is drafted: Lesson 1: General Ledger (G/L) Account Reports · Trial Balance · G/L Line Item · Financial Statement/Actual Comparison · Ledger Comparison Lesson 2: Analyze Profitability Report Lesson 3: Analyze Inventory Report Lesson 4: Analyze Net Investment Report Lesson 5: Analyze Orders, Sales, Profit and Backing Report 3/7 outline sent to Angie for initial QA Angie couldn't do so 3/11 sent to Jenn for QA and completed 3/12 SG final QA and found issues; returned to Kristin for revisions 3/12 sent to Billy and Misty for review, requesting signoff by EOD 3/18 3/18 started Brenda on creating the SL shell 4/7 Billy Cambers signed off on outline NOTE ON AT-RISK STATUS: 5/12 - Billy informed us the reports will likely be combined into one and only run one report with one t-code. Scripts are not yet updated to reflect the final decision on future state process. ETA pending Brenda started shell but waiting on dev since all internal contents are on pause 7/17 Misty confirmed this process is still being rewritten Contents descoped and multiple reports condensed into a new reporting process that will fall under one report, Net Investment (see notes for that deliverable). This report should be finished testing 7/25 or early the following week, at which point we will have what we need to create that storyboard as well as un-pause the course and continue working on the outline. 7/30 SG outline QA and returned for revision; revisions made by Brenda 7/31 began outline review but did not get far; resume 8/6 8/6 Billy signed off outline in weekly call 8/12 Brenda created and sent to Sarah/Dan for initial review; edits completed 8/13 SG QA and sent back for light revision 8/13 reviewed with Billy, slight changes, approved! |  | URGENT | Ian review and update 8/15 | 14 | 0 | 2025-08-13 |  | 2025-01-14 13:29 | 2025-08-15 12:39 |  | 2025-08-13 15:28 | Jade Brown | Lockheed Martin | Course Development | Development | 868a48vt6 868a48uv2 868a48x2h | https://app.clickup.com/t/868a48vt6 https://app.clickup.com/t/868a48uv2 https://app.clickup.com/t/868a48x2h | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 288 hours |  | 0 | 2025-08-13 | 2025-08-13 | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC3B | Financial Accounting | GL Close (Run Preliminary Reports L4) |  | WBT |  | 2025-08-13 | Overdue | [9 empty] | 2025-08-13 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byykmv | R2R Financial Accounting: Create and Manage Online Journal Entries | COMPLETED | SG QA 3/14 and discussed with Anya; passed to Kristin to familiarize herself to present to SME 4/16 Misty signed off in call 5/9 full course QA complete; just a few revisions outstanding 5/21 Billy signed off via Teams; saved in validations folder 7/22 Ankine emailed to say 2 sims are incorrect: Park Journal Entry and Post a JE to a Non-Leading Ledger. She was checking these because she hoped to link to some JE training in the Tax Corrections Overview course. We discussed with Financial Accounting team, who said the training wasn't incorrect, but her way of going through the steps for jurisdiction code and tax code were more thorough. We agreed to make the changes. Jade is in the process of changing SBs and sim steps for these 2 sims. Next step is to get them in front of Billy and Misty and probably Ankine to ensure they are aligned, then approve the sims as well. 5/21 Billy signed off full course |  | LOW | updated and ready for review. | 9 | 0 | 2025-05-21 | 2025-02-26 | 2025-01-14 13:31 | 2025-08-14 13:50 |  | 2025-08-14 09:00 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4a4p6 868a49km5 868a49j8b 868a49g0h 868a49epk 868a49d9n | https://app.clickup.com/t/868a4a4p6 https://app.clickup.com/t/868a49km5 https://app.clickup.com/t/868a49j8b https://app.clickup.com/t/868a49g0h https://app.clickup.com/t/868a49epk https://app.clickup.com/t/868a49d9n | r2r, wbt | Development | [7 empty] | 271 hours |  | 0 | 2025-05-07 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Create On-Line Journal Entries L4) |  | WBT |  | 2025-05-21 | Overdue | [9 empty] | 2025-05-21 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byyvc5 | R2R Financial Accounting: Electronic Bank Statement Processing | COMPLETED | 7/1 Jade contacted SME: scripts are still being updated and the person doing it is OOO this week (ending 7/4) 7/30 SG outline QA and returned for light revision; queued for SME review 7/30 Billy signed off outline and renamed course from "Cash Document Matching" Brenda created WBT and Dan reviewed 8/6 SG WBT QA and sent back for slight revision; Brenda edited and sent back for QA 8/12 SG QA complete and sent back for very small edits; edits complete; queued for reivew 8/13 8/13 Billy signed off in call! Approval saved in validation folder |  | HIGH | Ian updated and locked down 8/15 | 2 | 0 | 2025-08-13 |  | 2025-01-14 13:37 | 2025-08-15 13:03 |  | 2025-08-13 12:25 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4d5yk 868a4cx1p 868a4c6n2 868a4c61h | https://app.clickup.com/t/868a4d5yk https://app.clickup.com/t/868a4cx1p https://app.clickup.com/t/868a4c6n2 https://app.clickup.com/t/868a4c61h | r2r, wbt | Development | [7 empty] | 291 hours |  | 0 | 2025-08-12 | [6 empty] | Hand off to OCM Team |  |  |  | ITC4 | Financial Accounting | Consolidations & Tax (Cash Document Matching L4) |  | WBT |  | 2025-08-13 | Overdue | [9 empty] | 2025-08-13 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byywxb | R2R Financial Accounting: Process Open Items and Manage Periods | COMPLETED | 3/12 requested changes to outline alongside feedback being received on other outlines (Run Preliminary Reports, Manage Property Taxes) before SME review; Kristin to make one final change 3/17 3/18 final QA; ready for Alpha review by the client and queued up for presentation 3/19 presented in call; Misty reviewed most but confirmed she needs Billy to review the Process Flow Items and Closing Accounts. Sent to Billy via email requesting 3/25 signoff 3/26 Billy changed titles and organization of the class to represent contents better. Course includes 3 L3s and touches on processing open items as well as managing (opening and closing) new periods. -- we do not have his signoff still as of 3/27 when new outline was sent 3/26 Kristin changed outline to reflect and passed to Sarah for QA 3/27 Sarah QA and returned to Kristin for edits 3/27 edited by Kristin; assigned to Brenda for SL development NOTE to developer: please make a 3 lesson course. One lesson should contain the 3 new periods; one lesson should contain "Closing Periods" and one should contain the 2 clearing items. Finalized this org with SME on 3/26 when going through individual content items. 3/27 edited outline sent to SMEs for review and signoff by EOD 4/2; course has started development without signoff 4/1 SG QA and returned to Brenda/Kristin for discussion and revisions; same 4/4 4/9 Billy finally signed off on SB; CAVEAT: everything on material management is up in the air and he has to confirm 4/10 Dan taking over development 5/1 sent course to SMEs for review/signoff by EOD 5/6 for everything EXCEPT material management period, which we just decided on yesterday 5/12 signed off by Billy! |  | NORMAL | Signed off by Billy! | 9 | 0 | 2025-05-12 | 2025-02-05 | 2025-01-14 13:38 | 2025-08-14 13:49 |  | 2025-08-14 09:10 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4dca0 868a4d8j5 868a4d804 868baq0kq | https://app.clickup.com/t/868a4dca0 https://app.clickup.com/t/868a4d8j5 https://app.clickup.com/t/868a4d804 https://app.clickup.com/t/868baq0kq | r2r, wbt | Development | [7 empty] | 270 hours |  | 0 | 2025-04-09 | 2025-05-01 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Process Open Items L4), Open New Periods (GL Close L4), GL Close (Close Sub-ledgers L4) |  | WBT |  | 2025-05-02 | Overdue | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868byyyz1 | R2R Financial Accounting: G/L Account Clearing | COMPLETED | 2/5 OL draft v1 sent to SG for internal QA 2/6 SG sent back document with tracked changes 2/7 Kristin sent SG back with changes: ready for SME Alpha review of outline 2/17 Reformatting into new course wrap OL template by EOD 2/23 ILT Example 3/12 requested changes to outline alongside feedback being received on other outlines (Run Preliminary Reports, Manage Property Taxes) before SME review 3/13 SG QA complete; ready for Alpha review 3/19 reviewed and signed off by Misty in call 3/26 - JV beginning development in SL 4/1 - JV handed off course for review to Kris G for internal review 4/11 SG QA and sent revisions to Jess; now to Trish for tech review 4/14 SG QA again and feedback not implemented so sent back to Jess for revision 4/15 - JV made all SG requested edits and reviewed each to ensure they're complete 4/15 sent to client requesting review and signoff by EOD 4/17 4/30 post-shift to new template final QA and requested a few edits 5/1 sent to SMEs requesting review/signoff by EOD 5/6 5/7 Billy signed off on course in bonus call; approval saved in validations folder |  | NORMAL | JV made all SG requested edits and reviewed each to ensure they're complete @Trish Cortez @Sarah Griffis | 6 | 0 | 2025-05-07 | 2025-04-04 | 2025-01-14 13:40 | 2025-08-14 13:51 |  | 2025-08-14 08:55 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4da3v 868a4dbrz 868a4db5j | https://app.clickup.com/t/868a4da3v https://app.clickup.com/t/868a4dbrz https://app.clickup.com/t/868a4db5j | r2r, wbt | Development | [7 empty] | 271 hours |  | 0 | 2025-04-30 | 2025-05-01 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Close Sub-ledgers L4) |  | WBT |  | 2025-05-07 | Overdue | [9 empty] | 2025-05-07 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byz09n | R2R Financial Accounting: AR/AP Grouping | COMPLETED | 4/3 assigned Brenda creation of shell and Kristin creation of outline 4/9 Kristin created and sent off OL for QA; assigned to Mary Beth for QA 4/9 went over with Misty in call and she signed off on outline; ready to start dev Dan created course in new template 4/15 assigned to Kris for initial QA then SG will QA 4/28 SG QA complete and passed to Dan for revisions 4/29 sent to SMEs for review/signoff by EOD 5/1 4/30 Billy signed off full course in bonus call! Got signoff via Teams chat and saved in validation folder |  | HIGH | I couldn't find the shell or outline for this course so I made it from scratch, and it is now complete in the new template. | 6 | 0 | 2025-04-30 | 2025-04-04 | 2025-01-14 13:41 | 2025-08-14 13:53 |  | 2025-08-14 08:56 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4dfw2 | https://app.clickup.com/t/868a4dfw2 | wbt, r2r | Development | [7 empty] | 271 hours |  | 0 | 2025-04-28 | 2025-04-29 | [5 empty] | Hand off to OCM Team |  |  |  | ITC3 | Financial Accounting | GL Close (AR/AP Grouping L4) |  | WBT |  | 2025-04-30 | Overdue | [9 empty] | 2025-04-30 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byz2cz | R2R Financial Accounting: Year-End Close: Balance Carry Forward | COMPLETED | Jess completed the outline and is ready to be assigned out for QA 3/10 assigned to Jenn for QA 3/11 - JV completed QA except for a question on wording for the title 3/12 - JV completed outline and sent to Sarah for final QA 3/14 SG returned final QA to Jessica and requested edits 3/17 - JV completed edits from SG 3/18 SG final review complete; passed to Kristin for ownership 3/31 assigned Brenda creation of shell 4/2 outline discussed with Misty Clay who determined Billy is needed to confirm process she doesn't know. Sent outline to Billy same day requesting review and signoff; Misty confirmed all other content 4/8 sent to SMEs for offline review 4/28 Billy signed off outline in call with Chris Applegate 4/30 sent full WBT for review/signoff by EOD 5/6 4/30 Billy signed off full course |  | LOW | @Sarah Griffis We just reviewed this outline today and it has changed. Should I start this from scratch in new template or use Brenda's? Or dealers choice? | 11 | 0 | 2025-04-30 | 2025-03-04 | 2025-01-14 13:42 | 2025-08-14 13:51 |  | 2025-08-14 08:58 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4eubh | https://app.clickup.com/t/868a4eubh | r2r, wbt | Development | [7 empty] | 271 hours |  | 0 | 2025-04-30 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Year-End Close: Balance Carry-Forward L4) |  | WBT |  | 2025-04-30 | Overdue | [9 empty] | 2025-04-30 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byzd6q | R2R Financial Accounting: Perform Currency Valuation | COMPLETED | 2/27 Trish assigned Jenn to QA 3/3 Jenn returned QA notes to Kristin 3/3 Kristin completed QA changes and returned to Sarah for QA 3/4 Sarah completed QA and returned to Kris to make a few changes 3/4 Kristin completed QA changes; Sarah did a final review 3/5 Billy reviewed in regular call and signed off! 3/24 - WBT alpha draft ready to be assigned for initial QA. Review 360 link is in the 1LMX Organizational_Change_Mgt > Deliverables > WBT > Drafts > Alpha folder 3/25 Eugene performed initial QA; Kristin edited accordingly 3/26 SG final QA and returned to Kristin for revision; 3/27 Trish and Sarah reviewed again and requested revisions 3/31 Kristin revised and returned for final QA 4/1 SG final QA and returned for a few edits 4/3 Kristin passed to Sarah for final QA 4/4 SG final QA; Kris making 3 final changes 4/4 QA again after changes. Discovered with Dan course functionality is broken. Sending back for fix; Trish will supervise 4/15 SG QA of full course after Shannon's QA; sent to Kris for revisions 4/16 Revisions based on Shannon's QA are complete 4/17 Dan is going to check over 4/30 sent to SMEs requesting review/approval by EOD 5/6 4/30 Billy signed off full course! |  | HIGH | Completed course migration and let Dan know. | 13 | 0 | 2025-04-30 | 2025-02-17 | 2025-01-14 13:50 | 2025-08-14 13:49 |  | 2025-08-14 09:09 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4z9jr 868a4za1y | https://app.clickup.com/t/868a4z9jr https://app.clickup.com/t/868a4za1y | r2r, wbt | Development | [7 empty] | 270 hours |  | 0 | 2025-04-04 | 2025-04-30 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Perform Currency Valuation L4) |  | WBT |  | 2025-04-30 | Overdue | [9 empty] | 2025-04-30 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byzf1v | R2R Financial Accounting: Maintain Chart of Accounts | COMPLETED | NOTE ON AT-RISK STATUS: This course requires MDG access so we can't make more progress until we get that access. 6/6 update: still at risk because behind schedule due to 1) waiting for MDG access 2) backlog of materials to review due to lack of SME time 6/6 Jade received MDG access and used it to draft 1 SB. Will review with SMEs next week to ensure we're using the system correctly Waiting to develop outline in order to avoid rework: 8 outstanding SBs/sims and want content firmed up first. Dan started once we got the go-ahead for MDG, but internal content is uncertain; we will present it to SME and see what they see 7/1 Misty signed off outline in call 7/8 SG WBT QA and returned for some light revision 7/9 back and forth on QAs/edits with Dan; queued up for review with SME today 7/9 reviewed in SME call and SME requested small changes; Dan made; emailed back to client for review and approval 7/16 Billy signed off in call! |  | NORMAL | still paused for mdg | 4 | 0 | 2025-07-16 | 2025-05-15 | 2025-01-14 13:52 | 2025-08-14 13:54 |  | 2025-08-14 08:53 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4zcex 868a4zb61 868dw72jf 868dw7321 | https://app.clickup.com/t/868a4zcex https://app.clickup.com/t/868a4zb61 https://app.clickup.com/t/868dw72jf https://app.clickup.com/t/868dw7321 | mdg, r2r, wbt | Development, ✍ Risk Register | [7 empty] | 271 hours |  | 0 | 2025-07-08 |  | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC3 | Financial Accounting | GL Close (Maintain Charts of Accounts L4) |  | WBT |  | 2025-07-16 | Overdue | [9 empty] | 2025-07-16 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byzhda | R2R Financial Accounting: Review Financial Postings | COMPLETED | 3/6 passed outline QA to Jenn from Sarah while Sarah works on ITC2 high priority development 3/6 Jenn returned QA to Dan; Dan completing revision 3/20 Dan completed revisions 3/24 SG QA of outline and returned to Dan for light revision 3/25 Dan completed revisions and final QA complete 4/2 Misty Clay reviewed outline in call and signed off; with outline signed off focus attention on the WBT in progress with Dan 4/3 QA of outline with Misty's changes and returned to Kristin to incorporate them into the WBT. Kristin taking ownership of WBT from Dan, who is released from duty on this one 4/9 sent to Shannon for QA Shannon QA'ed and Dan responding to comments 4/30 sent to SMEs requesting review and signoff by EOD 5/6 5/5 Billy signed off via Teams and email saved in validations folder |  | LOW | @Sarah Griffis Jade is moving this one into the new template via our workshopping sessions. This is great experience for her. If it isn't done early next week, I can take it on and quickly get it across the finish line. | 15 | 0 | 2025-05-05 | 2025-03-04 | 2025-01-14 13:54 | 2025-08-14 13:50 |  | 2025-08-14 08:57 | Jade Brown | Lockheed Martin | Course Development | Development | 868a51e6r | https://app.clickup.com/t/868a51e6r | r2r, wbt | Development | [7 empty] | 271 hours |  | 0 | 2025-04-30 | 2025-04-30 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | Collect & Process Actuals (Review Financial Postings L4) |  | WBT |  | 2025-05-05 | Overdue | [9 empty] | 2025-05-06 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868byzkmp | R2R Financial Accounting: Review General Ledger Balances | COMPLETED | 6/5 SG outline review and sent to Dan for slight revision; ready for SME review week of 6/9 NOTE ON AT-RISK STATUS: Only due to need for adequate SME time, which is not currently scheduled. We need Chris Applegate to add the additional Financial Accounting time we've gotten the last month. If we do get this time, we may be able to meet the sprint deadline, as my team began WBT development early and, as long as there are no massive changes, will be able to turn the WBT around quickly for review. 6/11 Billy signed off on outline 6/13 Dan sent to SG for QA 6/13 SG QA and sent to Dan/Brenda for some light revision; they returned 6/17 SG QA and just a few more outstanding edits 6/18 Billy signed off! |  | LOW | Starting SL development | 2 | 0 | 2025-06-18 |  | 2025-01-14 13:56 | 2025-08-14 13:58 |  | 2025-06-18 12:33 | Jade Brown | Lockheed Martin | Course Development | Development | 868a4erk6 | https://app.clickup.com/t/868a4erk6 | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 1635 hours |  | 0 | 2025-06-13 |  | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC3 | Financial Accounting | GL Close (Review General Ledger Balances L4) |  | WBT |  | 2025-06-18 | Overdue | [9 empty] | 2025-06-18 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bz063a | R2R Product Costing: Introduction to PMMO | COMPLETED | NOTE ON AT-RISK STATUS: SME calls canceled two consecutive weeks; cannot get the time required to get reviews and approvals 6/9 SG outline QA and returned to Dan for light revision Outline ready for SME review and call set for this outline review alone on 6/26 6/26 started review with Seth and did not complete; will resume Monday 7/1 Seth signed off outline! 7/7 SG WBT QA and returned to Dan for revisions; same 7/11 and just about ready for SME review 7/14 SG final QA; ready for SME review on 7/15 7/15 SME review and Seth requested some pretty advanced changes. Dan and Ian worked these; SG QA; ready for SME review 7/22 7/22 in-call changes implemented and sent via email for final review and approval 7/23 Seth signed off after consultation with William and changes made with Dan! Email saved in approvals folder |  | HIGH | Fixing this outline is my prio for monday morning. Would like to get it ready in case we get through manage exceptions quickly. | 17 | 0 | 2025-07-23 | 2025-04-08 | 2025-01-14 14:12 | 2025-08-14 13:53 |  | 2025-07-23 08:34 | Jade Brown | Lockheed Martin | Course Development | Development | 868a2uwbe | https://app.clickup.com/t/868a2uwbe | r2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 799 hours |  | 0 | 2025-07-11 | 2025-07-07 | TRUE |  |  |  |  | Hand off to OCM Team | 2025-07-22 |  |  | Not part of ITC | Product Costing | No L3 Custom Content |  | WBT |  | 2025-07-23 | Overdue | [9 empty] | 2025-07-23 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bz079f | R2R Product Costing: Maintain PMMO Master Data | COMPLETED | NOTE: only 1 lesson is pertinent in this lesson for R1/MFC. Course for MFC will be complete with this 1 lesson. Remaining lessons will be for future releases. 4/8 Kristin created outline and sent to SG for QA 4/8 SG QA of outline and returned for revision 4/14 reviewed outline with team and did not complete; sent to Shauna-Kae to complete review requesting by EOD 4/17 4/17 Shauna-Kae returned with edits to implement and passed along to Seth as she is phasing out as functional lead for R1 4/30 Seth signed off outline via email saved in validation folder Dan and Brenda working in the SL file 5/5 SG course QA and sent back to Brenda for light revision 5/6 sent to SME requesting review/signoff by EOD 5/12 5/21 Seth signed off via email; saved in validation folder 6/13 NOTE ON AT-RISK STATUS: This course was put back into development from Completed when Seth asked for updates on a QRG (GRM4) that had been approved twice. Pending Seth's approval on that QRG, which was sent 6/12. 6/16 In weekly call, we were supposed to get final signoff on the QRG we changed after it was approved twice, because Seth didn't send it via email. Instead we spent the whole hour on it. Seth had two more sub-team people present, including Jeanette, who has worked with us in Angie/Brice areas. The two new people present, who are in higher positions than Seth, agreed that the QRG does not represent what needs to be trained and that they need to meet as a group to confirm future state processes before we can design training on it. They are going to try to meet internally 6/17 and meet with us 6/18. They did not meet so we canceled the 6/18 call. Instead I scheduled a call for 6/24 and they also canceled that one because they were not prepared to report on updates. Now Seth says he will talk to the MFC Product team 6/25 and get us information. 6/25 Seth let us know they discussed internally and agree to approve as-is for R1 and revisit for future releases |  | HIGH | Going to review this tomorrow with SMEs. Hopefully we get a completion. | 12 | 0 | 2025-06-25 |  | 2025-01-14 14:14 | 2025-08-14 13:59 |  | 2025-06-26 10:46 | Jade Brown | Lockheed Martin | Course Development | Development | 868b9uc4q 868a2vbuu 868a2v90k 868da7c3a 868da7d5x | https://app.clickup.com/t/868b9uc4q https://app.clickup.com/t/868a2vbuu https://app.clickup.com/t/868a2v90k https://app.clickup.com/t/868da7c3a https://app.clickup.com/t/868da7d5x | mfc, r2r, wbt | Development, ✍ Risk Register | [7 empty] | 1445 hours |  | 0 |  |  | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC3 | Product Costing | Maintain GPD Master Data (but GPD > PMMO in S/4) | TRUE | WBT |  | 2025-06-25 | Overdue | [8 empty] | 2025-06-02 | [6 empty] | R2R | Trish Cortez, Sarah Griffis
868bz0e5k | R2R Product Costing: Breakpoint | OUTLINES | 3/31 SMEs confirmed in call the scripts for this are not ready yet; still in testing NOTE ON AT-RISK STATUS: SME calls canceled two consecutive weeks; cannot get the time required to get reviews and approvals. In our last call with them, they confirmed we cannot move forward with this course's deliverables because scripts were not ready. 6/5 SG QA of outline and returned for light revision; Dan made; ready for SME review 6/16 we asked again about script readiness; they are not ready. We are going to try to present the outline when we can get it in front of them; we have so far not gotten the time to do so. It is possible that when we do they will tell us we can't move forward given the script situation, but we will try. All internal contents put on pause due to the script un-readiness. 6/23 in discussion with Seth: the course changed from Pegging & Distribution scope to just being about Breakpoint. It had breakpoint content already so we just made that the main focus--but since we're changing focus, the outline will need to change. Pegging and distribution are both done through batch processes and are the same in current to future state, so they do not require training. When Dan gets back he will adjust the course outline to reflect the new focus on breakpoint. Jade received materials from Seth via email to start on individual deliverables and will collab with Dan on outline content. 8/7 gathered sufficient information over time to resume work on this next week. 8/18 Seth has to check back with Kanda about breakpoint process. | Daniel Die | HIGH | @Daniel Die let's have this ready for Monday, 8/18 | 2 | 0 | 2025-08-18 | 2025-06-03 | 2025-01-14 14:19 | 2025-08-25 08:38 |  |  | Jade Brown | Lockheed Martin | Course Development | Development | 868efw1c5 868a2v8d3 | https://app.clickup.com/t/868efw1c5 https://app.clickup.com/t/868a2v8d3 | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-08-14 |  | TRUE |  |  |  | Daniel Die, Brenda Mayfield | Alpha Draft (ISG) |  |  |  | ITC3B | Product Costing | Collect & Process Actuals (Execute and Analyze Pegging L4) |  | WBT |  | 2025-09-12 | Overdue | - [@Sarah Griffis](#42510312) completed QA of the outline and returned it for revision on 6/5. - [@Daniel Die](#44154500) made the requested revisions; outline is now ready for SME review. - Scripts required for progress are still not ready, as confirmed by SMEs; this is blocking further work. - Task remains at risk due to repeated SME call cancellations and lack of required reviews and approvals. | [14 empty] | R2R | Trish Cortez, Sarah Griffis
868bz0g2b | R2R Product Costing: Manage Exceptions | OUTLINES | 5/7 Dan did a first review of the outline and requested some additions that are in progress 5/27 SG outline QA complete 6/2 sent Seth outline to review offline before viewing together in person next week NOTE ON AT-RISK STATUS: SME calls canceled two consecutive weeks; cannot get the time required to get reviews and approvals. Now (6/13) see below on Paused status, continuing to put it at risk 6/9 changed status to Paused: The manage exceptions process requires a signavio flow update with additional exceptions (recursive and underpeg) added (to excess, scrap, loss). We can't move forward because these additional exceptions require definitions that Seth needs to write before we apply them to a course. 7/11 emailed Chris to check on status of the two above items as he has not updated us Multiple check-ins with Seth since and requests for the information, which he keeps promising but has not sent 8/18 Seth says he wrote definitions and got them to Kanda, whose approval he wants before we finalize them; also did get to keep reviewing this outline in the meantime. Need to start here next time and 1) get Seth's definitions in 2) do a brief run-through of the outline and get signoff. Should be quick. 8/20 got definitions from Seth on the exceptions! (After more prompting.) Brenda put into outline and sent outline to SG for review. 8/20 SG QA and returned to Brenda for revision 8/22 Sarah and Dan reviewed revised version; ready for SME review |  | NORMAL | Seth is making adjustments. still in SME review | 7 | 0 | 2025-09-04 |  | 2025-01-14 14:21 | 2025-08-25 08:38 |  |  | Jade Brown | Lockheed Martin | Course Development | Development | 868a2v8ma 868b5u17u | https://app.clickup.com/t/868a2v8ma https://app.clickup.com/t/868b5u17u | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 123 hours |  | 0 | 2025-08-20 |  | TRUE |  |  |  | Brenda Mayfield | Ready for SME Review |  |  |  | ITC3 | Product Costing | Collect & Process Actuals (Manage Exceptions) | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-06-02 | [6 empty] | R2R | Trish Cortez, Sarah Griffis
868bz0j3r | R2R Product Costing: Reporting | OUTLINES | ITC phase is 3/4 because this course is one we created with SMEs that represents the reports area accountants need to run; it does not correspond to any one L3. Some reports are in ITC3B (pegging) and inventory report is ITC4. We will assess with SMEs what we can start now or if we must pause. NOTE ON AT-RISK STATUS: SME calls canceled two consecutive weeks; cannot get the time required to get reviews and approvals. In our last call with them, they confirmed we cannot move forward with this course's deliverables because scripts were not ready. 6/5 SG QA of outline and returned for light revision; 6/6 Dan made revisions; outline ready for review 6/16 we asked again about script readiness; they are not ready. We are going to try to present the outline when we can get it in front of them; we have so far not gotten the time to do so. It is possible that when we do they will tell us we can't move forward given the script situation, but we will try. All internal contents put on pause due to the script un-readiness. 8/7 gathered sufficient information over time to resume work on this next week 8/15 - received Information from Kanda and worked with Dan to apply this into the OL. Ready for QA. 8/15 SG outline QA. Ready and queued up for SME review 8/18. | Jade Brown | NORMAL | @Sarah Griffis I looked it over. I think we can use this OL to discuss with the SME's. Seth might need to provide better context into what the reports actually do and why they generate them. Only information we have is what is generated on the reports which is pretty consistent across all of them. I added the QRG links to the OL. | 2 | 0 | 2025-08-18 | 2025-06-03 | 2025-01-14 14:22 | 2025-08-25 00:57 |  |  | Jade Brown | Lockheed Martin | Course Development | Development | 868a2v7ew 868a2v7u6 868a2v7me 868a2vaa9 868a2vbez 868a2v6r2 868a2v9nz 868a2v92y 868a2v8dw 868em74hp | https://app.clickup.com/t/868a2v7ew https://app.clickup.com/t/868a2v7u6 https://app.clickup.com/t/868a2v7me https://app.clickup.com/t/868a2vaa9 https://app.clickup.com/t/868a2vbez https://app.clickup.com/t/868a2v6r2 https://app.clickup.com/t/868a2v9nz https://app.clickup.com/t/868a2v92y https://app.clickup.com/t/868a2v8dw https://app.clickup.com/t/868em74hp | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-08-14 |  | TRUE |  |  |  | Daniel Die, Brenda Mayfield | Ready for SME Review |  |  |  | ITC3 | Product Costing | No L3 Custom Content |  | WBT |  | 2025-09-05 | Overdue | - Outline was QA reviewed by [@Sarah Griffis](#42510312) on 6/5 and revised by [@Daniel Die](#44154500) on 6/6; now ready for SME review. - SME calls have been canceled for two weeks, delaying reviews and approvals. - SMEs confirmed scripts are not ready, so deliverables cannot move forward yet. | [14 empty] | R2R | Trish Cortez, Sarah Griffis
868bz4uju | R2R Tax Accounting: Withholding Tax for Accounts Receivable | COMPLETED | SL file QA by Sarah 2/3 In conversation with Tax about training scope. Ankine will get feedback to us by EOD 2/18. Ankine got us feedback and we addressed it. The outstanding item was the one shared with AR (O2C) sent by Sarah for feedback 2/21. Re-sent courses 3/3 requesting final signoff by EOD 3/6; sent a corresponding escalation email to Sarah Gentry and Chris Applegate the same day 3/6 communication from Ankine in call: 3/13 followed up with Ankine requesting timeline for getting her feedback 3/17 she responded that she is immersed in defect resolution to complete testing deadlines and aims to get us feedback by 3/23 3/23 Ankine sent clear, actionable feedback. Trish and Sarah will evaluate 3/25 in a call. 3/24 told Ankine we would get edited material back to her by EOW next week (first week of April); putting on a brief hold as we finish our sprint to the ITC2 training deadline 3/25 changed name from "Withholding Tax Receivable Collection" per Ankine's 3/23 comment Goal to send Ankine all ITC1 courses by 4/4 4/10 sent all ITC1 courses to Ankine for review and signoff by 4/16 4/23 Ankine signed off; sent to Adrienne for final signoff 4/23 Adrienne signoff |  | URGENT | Updated audio and addressed Ankine's comments. This is NOT in final review. This has been on hold due to perform billing missing content. | 4 | 0 | 2025-04-23 | 2025-01-15 | 2025-01-14 18:56 | 2025-08-14 13:48 |  | 2025-08-14 11:13 | Trish Cortez | Lockheed Martin | Course Development | Development | 868a2uwbk 868a2uwby 868a2uwcg | https://app.clickup.com/t/868a2uwbk https://app.clickup.com/t/868a2uwby https://app.clickup.com/t/868a2uwcg | wbt, r2r | Development | [7 empty] | 268 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | ITC1 | Tax Accounting | Consolidations & Tax (Withholding Tax Receivables Collection L4) |  | WBT |  | 2025-04-23 | Overdue | [9 empty] | 2025-04-24 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bzh1bb | PLP PS: Create Internal Projects | OUTLINES |  |  | URGENT | Update 7.1.25: Dina said this design is still in progress, finalization estimated in 2-3 weeks. Screens may not be ready to record until August. | 2 | 0 |  |  | 2025-01-15 08:31 | 2025-08-25 00:36 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2vbc2 868a2v7h1 868a2v7x0 | https://app.clickup.com/t/868a2vbc2 https://app.clickup.com/t/868a2v7h1 https://app.clickup.com/t/868a2v7x0 | wbt, plp | Development | [7 empty] | 459 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868bzhq2e | PLP PS: Create FEA | OUTLINES |  |  | URGENT | Update 7.1.25: Dina said this design is still in progress, finalization estimated in 2-3 weeks. Screens may not be ready to record until August. | 2 | 0 |  |  | 2025-01-15 08:35 | 2025-08-06 12:23 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2v9h6 868a2v8e7 868a2v5j2 868a2v7ma 868a2v9q2 868bzhy35 | https://app.clickup.com/t/868a2v9h6 https://app.clickup.com/t/868a2v8e7 https://app.clickup.com/t/868a2v5j2 https://app.clickup.com/t/868a2v7ma https://app.clickup.com/t/868a2v9q2 https://app.clickup.com/t/868bzhy35 | wbt, plp | Development | [7 empty] | 459 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-19 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868bzj218 | PLP PS: Create Account Assignment Charge Numbers | OUTLINES |  |  | URGENT | Update 7.1.25: Dina said this design is still in progress, finalization estimated in 2-3 weeks. Screens may not be ready to record until August. | 2 | 0 |  |  | 2025-01-15 08:42 | 2025-08-06 12:24 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868bzj30p 868bzj988 868bzjzef | https://app.clickup.com/t/868bzj30p https://app.clickup.com/t/868bzj988 https://app.clickup.com/t/868bzjzef | plp, wbt | Development | [7 empty] | 459 hours |  | 0 | [7 empty] | Ready for SB draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-19 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868bzm6pz | PLP PS: Create Customer Projects | OUTLINES |  | Brice LeBlanc | URGENT | Now ready for draft, per Dina | 3 | 0 |  | 2025-07-29 | 2025-01-15 08:55 | 2025-08-25 00:35 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2v7gu 868a2v5rr 868a2v8gy 868a2v674 868a2vc34 868a2vbr1 868bzn4pr | https://app.clickup.com/t/868a2v7gu https://app.clickup.com/t/868a2v5rr https://app.clickup.com/t/868a2v8gy https://app.clickup.com/t/868a2v674 https://app.clickup.com/t/868a2vc34 https://app.clickup.com/t/868a2vbr1 https://app.clickup.com/t/868bzn4pr | wbt, plp | Development | [7 empty] | 585 hours |  | 0 | [6 empty] | Brice LeBlanc | In QA |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-12 |  |  |  | 2025-08-01 | Anya Toms | [6 empty] | 2025-07-24 |  |  |  |  | PLP | Jenn Cooke, Trish Cortez
868bzngtq | PLP PS: Create Account Assignment Charge Numbers for Customer Projects | OUTLINES |  | Brice LeBlanc | URGENT | Update 7.1.25: Dina said this design is still in progress, finalization estimated in 2-3 weeks. Screens may not be ready to record until August. | 2 | 0 |  | 2025-07-31 | 2025-01-15 09:00 | 2025-08-08 14:17 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868bzngvc 868bzngvh 868bzngvm 868bzngyc | https://app.clickup.com/t/868bzngvc https://app.clickup.com/t/868bzngvh https://app.clickup.com/t/868bzngvm https://app.clickup.com/t/868bzngyc | plp, wbt | Development | [7 empty] | 585 hours |  | 0 | 2025-08-01 | [5 empty] | Brice LeBlanc | Alpha Draft (ISG) |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-19 | Overdue | [10 empty] | 2025-07-24 |  |  |  |  | PLP | Jenn Cooke, Trish Cortez
868bzq53m | PLP PS: Create the Program Common ID for LRP, Proposals, and Contracts - OL | DEVELOPMENT |  | Jenn Cooke | URGENT | QA in progress | 16 | 0 | 2025-04-04 | 2025-03-21 | 2025-01-15 09:08 | 2025-08-12 06:06 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868bzqr5a 868bzq9va 868bzx1pd 868bzx6t2 868bzx8e7 868bzx9d1 868f8erz1 | https://app.clickup.com/t/868bzqr5a https://app.clickup.com/t/868bzq9va https://app.clickup.com/t/868bzx1pd https://app.clickup.com/t/868bzx6t2 https://app.clickup.com/t/868bzx8e7 https://app.clickup.com/t/868bzx9d1 https://app.clickup.com/t/868f8erz1 | ilt, plp, mdg | Development | [7 empty] | 322 hours |  | 0 | [6 empty] | Anya Toms | In QA |  |  |  | ITC4 | Project Systems | Create Program Common ID (Project Systems) |  | ILT |  | 2025-08-29 | Overdue |  |  |  | Jenn Cooke | [11 empty] | PLP | Jenn Cooke, Trish Cortez
868bzt8py | PLP PS: Manage PCID for LRP Item, Proposal, or Contract - OL | OUTLINES |  |  | URGENT | @Jenn Cooke I updated the Facilitator Guide for Create PCID as per our conversation w/Dina and sent it out via email for review by 4pm EST on July 8th | 6 | 0 | 2025-07-11 | 2025-06-02 | 2025-01-15 09:17 | 2025-08-06 12:11 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868bzu0z1 868bztyqe 868bzu0cd 868dymc6r | https://app.clickup.com/t/868bzu0z1 https://app.clickup.com/t/868bztyqe https://app.clickup.com/t/868bzu0cd https://app.clickup.com/t/868dymc6r | ilt, plp, mdg | Development | [7 empty] | 2458 hours |  | 0 | 2025-06-25 | 2025-07-01 |  | 2025-07-01 | 2025-07-01 |  |  | Final Review & Sign off (SME) | 2025-07-09 |  |  | ITC4 | Project Systems | Create Program Common ID (Project Systems) |  | ILT |  | 2025-08-29 | Overdue | [15 empty] | PLP | Jenn Cooke, Trish Cortez
868bzwb0b | R2R Tax Accounting: Review Withholding Tax Information on Business Partner (BP) Records | COMPLETED | Format changed to QRG in conversation with Ankine and Adrienne 11/16 Ankine signed off on content QRG created; Emilie and Sarah QA-ed 1/20 2/13 requested Adrienne's comments by EOD 2/18 Awaiting final signoff Re-sent courses 3/3 requesting final signoff by EOD 3/6; sent a corresponding escalation email to Sarah Gentry and Chris Applegate the same day 3/6 communication from Ankine in call: 3/13 followed up with Ankine requesting timeline for getting her feedback 3/17 she responded that she is immersed in defect resolution to complete testing deadlines and aims to get us feedback by 3/23 3/23 Ankine sent clear, actionable feedback. Trish and Sarah will evaluate 3/25 in a call. 3/24 told Ankine we would get edited material back to her by EOW next week (first week of April); putting on a brief hold as we finish our sprint to the ITC2 training deadline Goal to send Ankine all ITC1 courses by 4/4 4/10 sent all ITC1 courses to Ankine for review/signoff by 4/16 4/23 Ankine signed off; sent to Adrienne for final signoff 4/23 Adrienne final signoff |  | URGENT | This course is updated with re-done audio and updates from Ankine's review. Link has been republished and it needs her sign off or any additional updates. | 2 | 0 | 2025-04-23 |  | 2025-01-15 10:09 | 2025-08-14 13:58 |  | 2025-04-24 09:03 | Jade Brown | Lockheed Martin | Course Development | Development | 868a2uwcq | https://app.clickup.com/t/868a2uwcq | qrg, r2r | Development | [7 empty] | 2959 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | ITC1 | Tax Accounting | Consolidations & Tax (Withholding Tax Master Data Management L4) |  | WBT |  | 2025-04-23 | Overdue | [9 empty] | 2025-04-24 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bzx1ac | R2R Tax Accounting: Indirect Taxes: Manage Property Taxes | COMPLETED | 3/5 sent to Jenn C. for QA Review 1 3/5 Jenn completed QA and returned form to Kristin for edits 3/5 Kristin completed Jenn's edits and sent to Sarah for QA 3/6 Sarah QA and returned for revision 3/10 SG QA; 3/12 requested for outline to reflect naming changes decided up on in yesterday's call with Tammy 3/13: Outline naming convention updated to match the dev process style guide (removed version number) 3/13 reviewed with Jessica in call; did not complete review. Sent via email to both her and Tammy requesting offline review prior to 3/17 joint call in which we plan to complete review and get signoff 3/17 presented in call and did not complete; Jade and Kristin aligning content in outline to content in sims. Waiting for SMEs to return offline review of Asset Acquisitions Report so we can revise both outline and sim to their edits. At that point we will send them the outline for review again. 3/24 presented in call with Tammy and Jessica; got through the end with Jessica but Tammy had to drop. Requested final signoff from both 3/24 Jessica and Tammy signed off outline; 3/26 Adrienne signed off 3/25 Emilie started development; 4/1 passed on to Kristin to complete 4/3 Kristin finished and passed to Eugene for initial QA 4/28 sent to Adrienne for final review/signoff by EOD 5/1 4/30 Adrienne signed off via email |  | HIGH | @Sarah Griffis Ready for your review before we send to SMEs | 16 | 0 | 2025-04-30 | 2025-02-25 | 2025-01-15 10:26 | 2025-08-14 13:50 |  | 2025-08-14 11:11 | Jade Brown | Lockheed Martin | Course Development | Development | 868b45tmg 868a2v63d 868a2vbvb 868a2v613 868ax49kn | https://app.clickup.com/t/868b45tmg https://app.clickup.com/t/868a2v63d https://app.clickup.com/t/868a2vbvb https://app.clickup.com/t/868a2v613 https://app.clickup.com/t/868ax49kn | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-04-09 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Tax Accounting | Consolidations & Tax: Indirect Taxes - Manage Property Taxes L4 |  | WBT |  | 2025-04-30 | Overdue | [9 empty] | 2025-04-30 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bzx9bf | R2R Tax Accounting: Indirect Taxes: Manage Tax Fixed Assets Reporting | COMPLETED | Notes: 3/5 Sent to Jenn C. for QA Review 1 3/6 Jenn completed QA and sent to Kristin to make changes 3/6 Kristin made changes and sent to Sarah for QA Sent back to Kristin for edits 3/10 SG QA and sent back to Kristin for a few revisions 3/12 SG final QA. Ready for SME review Outline naming convention updated to match the dev process style guide (removed version number) 3/18 course outline sent to SMEs for review; signoff requested by EOD 3/21 3/24 Adrienne and Tammy signed off outline; ready to be developed 3/25 assigned to Brenda for development; completed 3/26 3/26 assigned to Kristin for WBT initial QA 3/31 Kristin meeting with Brenda to discuss adding in Notes 4/1 Kristin completed QA and gave to SG for final QA 4/1 SG completed final QA and requested a few small edits 4/2 Kristin and Brenda resolved comments 4/2 SG final QA and 2 edits to resolve in the KC before sending to client 4/2 sent to client for review requesting signoff by EOD 4/8 5/1 Adrienne signed off via email Brenda transitioned to new template with VO; SG QA 5/1 |  | HIGH | @Sarah Griffis implemented comments and ready for a final look. | 6 | 0 | 2025-05-01 | 2025-02-26 | 2025-01-15 10:33 | 2025-08-14 13:50 |  | 2025-08-14 11:10 | Jade Brown | Lockheed Martin | Course Development | Development | 868a2vbfx | https://app.clickup.com/t/868a2vbfx | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 268 hours |  | 0 | 2025-04-01 | 2025-04-02 | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC2 | Tax Accounting | Consolidations & Tax: Indirect Taxes- Manage Tax Fixed Assets L4 |  | WBT |  | 2025-05-01 | Overdue | [9 empty] | 2025-05-01 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bzxqfm | R2R Tax Accounting: US State Tax | OUTLINES | Unclear whether this will be 3 or 3B NOTE ON AT-RISK STATUS: 5/27 Adrienne confirmed ITC3B is their cycle; says "still not closed due to many defects. Our new ECD for all defects to be closed is 6/6/2025. I will let you know if some finish earlier." 6/10 update email from Adrienne: "We are updating all direct test scripts this week. The State Provision interim script will be the first state script to get completed. I will send the test scripts as they are completed. we are targeting total completion by end of next week." Plan is to un-pause courses as we get the scripts and they look viable to start on 6/18 advised by Adrienne to cut State Tax Return/Provision difference and just do one State Tax course. And they're ITC4. NOTES FOR DEVELOPMENT: L3 for State Tax Return: return = actuals; L3 for State Tax Provision = provision is when they're doing an estimate: it's provisional, a "dress rehearsal" for actuals. So teach the same context here that we need to in the federal course. Different L3s because they're done differently BA mostly does SAP; corporate gets it from them and puts in TRCS. We need both accountant types as audience. Tax Analyst security role to take this and federal 7/28 discussion with Adrienne Suber: this whole course will likely contain only 2 deliverables for R1: R&D Reports; State Sum which will include both of the items currently listed as distinct items here in Clickup. Need to analyze scripts and get clarity before finalizing in our structure. 8/5 Soonthree added Tax Fixed Assets report to this course as well as federal. So deliverables include that, R&D Reports, and likely just State Sum in addition - but we need more info from Adrienne on how to condense the remaining into one State Sum deliverable. There is a SB made; will discuss with team next week. 8/7 Brenda started outline 8/11 reviewed in weekly call and Anayka Hendricks requested to complete review offline. Dan refined based on in-call edit requests and 8/13 sent back to her via Teams requesting offline review. Plan to keep reviewing in call next week (doubt she will get to this, and we need Adrienne Suber as well, who is currently OOO) 8/19 reviewed again with total reformulation of curriculum and got nearly through; sent for offline review to complete. Plan to get formal written approval either offline or in next call on 8/26. | Daniel Die | LOW | In SME review for offline. Meanwhile Dan will fill more info in to help with Anayka's review. | 1 | 0 |  |  | 2025-01-15 10:45 | 2025-08-25 01:04 |  |  | Jade Brown | Lockheed Martin | Course Development | Development | 868a2v9q8 868a2vbnb 868a2v781 868a2va7n 868f29xw0 868f8mz8f 868f8mze1 868f8n4fx | https://app.clickup.com/t/868a2v9q8 https://app.clickup.com/t/868a2vbnb https://app.clickup.com/t/868a2v781 https://app.clickup.com/t/868a2va7n https://app.clickup.com/t/868f29xw0 https://app.clickup.com/t/868f8mz8f https://app.clickup.com/t/868f8mze1 https://app.clickup.com/t/868f8n4fx | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 481 hours |  | 0 | 2025-08-07 | 2025-08-14 | TRUE |  |  |  | Brenda Mayfield, Daniel Die | Beta Review (SME) |  |  |  | ITC4 | Tax Accounting | Consolidations & Tax (US State Tax Return L4) |  | WBT |  | 2025-09-05 | Overdue | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868bzy4cu | R2R Tax Accounting: SAP/Vertex-Americas: US Sales/Use Tax Compliance and Reporting | COMPLETED | Future releases' course description: "...participants should learn practical skills for managing sales/use tax liabilities that ensures all financial translations align with tax reporting requirements." R1 is reduced scope so different from this for now. 4/14 confirmed by Ankine: This L3 is slated ITC3, but only ONE of all of the lessons is different from current state and requires training; all other releases will require the full slate of training. Details: future state requires a reconfiguration of Vertex software, but they were not able to do that reconfiguration right now; future releases will have the software reconfigured and thus will change in future state and require training. Generate Detail Reports for Tax Engine is the only item for R1 and is a QRG. 4/17 integrated the above one lesson into the previously independent Vertex course for a single course on Sales/Use Tax that includes both Vertex and SAP. We will take the outline Kris started (see below) and use for this combined course. 4/4 assigned Brenda creation of shell Kris and Brenda worked on outline 4/14 presentation of outline in SME call and linked in chat for signoff 4/14 assigned Kris to start developing in OL/SL. NOTE ON AT-RISK STATUS: Other courses are taking so long to review that we have not gotten to this outline, which waited on because we needed to have Vertex anyway. My team received Vertex earlier this week (week ending 6/6) and used it to draft one of the required SBs; now we need SME time to review the material. 6/13 update: reviewed the storyboard within with Katie; she just needs to provide us with one document number and then sign off on the SB. We will then look at the outline content with her and get her signoff. 6/26 kept working through outline; review is not complete. 7/7 reviewed in SME call. Katie and Ankine requested a few small changes. Changes were complete and requested Katie's approval via email. Sent again requesting approval on 7/10 7/11 Katie signed off outline! Sent Adrienne request for her approval as well 7/16 SG WBT QA after Brenda's first draft; sent back for some revision. Dan will work these prior to 7/17 SME call. More back and forth QA; course nearly ready for SME review pending a graphic update Dan will do. 7/21 graphic done, QA complete, last changes implemented. Ready for SME review. 7/22 Alpha review demo-ed with SMEs in call; a few changes requested and both Katie and Ankine requested to review offline 7/24 Katie and Ankine gave verbal approval and then formal approval via email from Katie and Adrienne |  | LOW | Same status - ready for SME review | 4 | 0 | 2025-07-24 | 2025-05-05 | 2025-01-15 10:53 | 2025-08-14 13:53 |  | 2025-07-24 09:56 | Jade Brown | Lockheed Martin | Course Development | Development | 868a2v9fg 868aakc2n 868aakaq5 868aakb61 868aakbka 868aakeck 868aakf0c 868aakgu0 868aakhmv 868aakh6r 868aakj4q 868aakjjh 868aakjxt 868aakk94 868aakm55 868aakmdk 868aakmr8 868aakmz8 868aakn66 | https://app.clickup.com/t/868a2v9fg https://app.clickup.com/t/868aakc2n https://app.clickup.com/t/868aakaq5 https://app.clickup.com/t/868aakb61 https://app.clickup.com/t/868aakbka https://app.clickup.com/t/868aakeck https://app.clickup.com/t/868aakf0c https://app.clickup.com/t/868aakgu0 https://app.clickup.com/t/868aakhmv https://app.clickup.com/t/868aakh6r https://app.clickup.com/t/868aakj4q https://app.clickup.com/t/868aakjjh https://app.clickup.com/t/868aakjxt https://app.clickup.com/t/868aakk94 https://app.clickup.com/t/868aakm55 https://app.clickup.com/t/868aakmdk https://app.clickup.com/t/868aakmr8 https://app.clickup.com/t/868aakmz8 https://app.clickup.com/t/868aakn66 | americas, r2r, vertex, wbt | Development, ✍ Risk Register | [7 empty] | 774 hours |  | 0 | 2025-07-16 |  | TRUE |  |  |  |  | Hand off to OCM Team | 2025-07-24 |  |  | ITC3 | Tax Accounting | Consolidations & Tax (US Sales/Use Tax Compliance & Reporting L4) |  | WBT |  | 2025-07-24 | Overdue | [9 empty] | 2025-07-24 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868bzy7pa | R2R Tax Accounting: Vertex O Series: Indirect Tax Determination Engine | OUTLINES | 7/31 this is the only Vertex course that can be started now. Katie wants to start with demo-ing an orientation to Vertex; will do 8/7 8/7 Katie and Ankine decided they will likely combine this with the RoW courses to create one Determination Engine course. They decided they need to see how development goes, though, so this will be a work in progress. We will likely be descoping the tasks within and transitioning this to more of a custom course, although the lift is easier: they are wanting a lot of screenshots, not newly created conceptual material. Katie designed an outline she and Ankine are refining. Next week we will go through the process in Vertex with Katie and this will guide us further. 8/14 in demo of Vertex by Katie with Ankine and Ron present: 3 courses needed for R1, and not organized on the criterion of Americas/RoW as the L3s are organized (NOTE that this means the L3 identified as associated to the course is loose--we're not following L3 organization strictly speaking, but we're still in ITC4 because the Determination Engine L3 is). Instead organized by tool: SAP, Vertex O Series, Vertex Accelerator. Directive is to include components in all 3 courses of both Americas/Row. We will need to mark which items are international. These courses used to have roughly 15 individual step-based deliverables; Ankine and Katie agree that is too low-level and the course should be custom and higher level. In the future we may add simulations to show step-based tasks, and if we do that we will mark them individually as Americas or RoW. For R1, just ILTs with no step-based individual tasks. As we go through the outline with Katie we will add lessons; they are not finalized right now. Note that the courses will need to be delivered twice: to two different audiences (Americas, RoW), for a total of 6 deliveries (3 courses x 2 audiences). Note on Outline status: It's in this status because an outline has been started, but it's Katie's and Ankine's. Dan will enter a start date when he picks up their outline and starts to adapt it into deliverable format. | Daniel Die | NORMAL |  | 0 | 0 |  |  | 2025-01-15 10:55 | 2025-08-25 01:06 |  |  | Jade Brown | Lockheed Martin | Course Development | Development |  |  | r2r, americas, vertex, ilt, row | Development | [7 empty] | 269 hours |  | 0 | 2025-08-14 | [5 empty] | Daniel Die | Alpha Draft (ISG) |  |  |  | ITC4 | Tax Accounting | Consolidations & Tax (Indirect Tax Determination Engine) |  | ILT |  | 2025-09-12 | [16 empty] | R2R | Trish Cortez, Sarah Griffis
868c00xax | O2C AR: Collect Cash for DFAS Customers | OUTLINES |  | Ashley Parker | HIGH | @Angie Paxton Format and content updates from SME meeting | 4 | 0 | 2025-08-24 | 2025-07-17 | 2025-01-15 11:51 | 2025-08-25 12:03 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v6j1 868euhb3f | https://app.clickup.com/t/868a2v6j1 https://app.clickup.com/t/868euhb3f | ilt, o2c | Development | [7 empty] | 824 hours |  | 0 | 2025-07-24 |  |  |  | 2025-08-25 |  | Ashley Parker, Kaye Perrota | Beta Revision (ISG) |  |  |  | ITC3 | Accounts Receivable | Collect Cash |  | ILT |  | 2025-09-26 | Overdue | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868c0137q | O2C AR: Collect Cash | DEVELOPMENT |  | Ashley Parker | URGENT | FG sent for SME approval 8/13. | 11 | 0 | 2025-08-03 | 2025-06-20 | 2025-01-15 11:55 | 2025-08-14 11:51 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868e7nuv5 868e7nuhr 868e7nud4 868a2v8a8 868e7ntdw 868e7nua7 868evenfw 868exg6ct | https://app.clickup.com/t/868e7nuv5 https://app.clickup.com/t/868e7nuhr https://app.clickup.com/t/868e7nud4 https://app.clickup.com/t/868a2v8a8 https://app.clickup.com/t/868e7ntdw https://app.clickup.com/t/868e7nua7 https://app.clickup.com/t/868evenfw https://app.clickup.com/t/868exg6ct | o2c, ilt | Development | [7 empty] | 1153 hours |  | 0 | 2025-07-14 | 2025-07-24 |  | 2025-08-14 | 2025-08-14 |  | Ashley Parker | Beta Review (SME) |  |  |  | ITC3 | Accounts Receivable | Collect Cash |  | ILT |  | 2025-09-19 | Overdue | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868c013rg | O2C AR: S4 HANA for AR Managers, Team Leads, and Delegates | PREDEVELOPMENT |  | Ashley Parker | HIGH |  | 0 | 0 |  |  | 2025-01-15 11:56 | 2025-08-24 22:38 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868drjd9t 868a2v658 868a2vbh4 868a2v6eq | https://app.clickup.com/t/868drjd9t https://app.clickup.com/t/868a2v658 https://app.clickup.com/t/868a2vbh4 https://app.clickup.com/t/868a2v6eq | ilt, o2c | Development | [7 empty] | 1636 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Accounts Receivable | No L3 Custom Content |  | ILT |  | 2025-09-12 | [16 empty] | O2C | Angie Paxton
868c01f57 | O2C Billing: Generate and Attach Invoices | DEVELOPMENT |  |  | HIGH | FG & CW approved by Hayden 8/24 | 10 | 0 |  | 2025-06-03 | 2025-01-15 12:04 | 2025-08-25 05:09 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v87a 868a2v8wn 868a2v61w 868a2vc1c | https://app.clickup.com/t/868a2v87a https://app.clickup.com/t/868a2v8wn https://app.clickup.com/t/868a2v61w https://app.clickup.com/t/868a2vc1c | ilt, o2c, ot | Development | [7 empty] | 338 hours |  | 0 | [7 empty] | Pending SIMs |  |  |  | ITC3B | Billing | Issue Output Create Billing Documents |  | ILT |  | 2025-09-26 | Overdue | - Alpha draft was completed and shared with [@Angie Paxton](#81508310) via email; draft also saved to Teams for QA 1. - Outline v2 draft was sent to [@Ashley Parker](#42484518) for QA. - [@Ashley Parker](#42484518) confirmed the outline is complete and notified [@Angie Paxton](#81508310). | [14 empty] | O2C | Angie Paxton
868c01fzy | O2C Billing: Transmit Invoices and Back-Up | DEVELOPMENT |  |  | HIGH | Holding until after Simulation September. Need FG and CW | 5 | 0 |  | 2025-06-03 | 2025-01-15 12:05 | 2025-08-25 09:59 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2vave 868a2v77a | https://app.clickup.com/t/868a2vave https://app.clickup.com/t/868a2v77a | ilt, o2c | Development | [7 empty] | 75 hours |  | 0 | [7 empty] | Beta Revision (ISG) |  |  |  | ITC3 | Billing | Issue Output Manage Billing Documents |  | ILT |  | 2025-09-19 | Overdue | - Outline draft was completed and shared with [@Angie Paxton](#81508310) and [@Ashley Parker](#42484518) for review and QA. - [@Ashley Parker](#42484518) was recently assigned to the task. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868c01gmq | O2C Billing: Cancel Billing Document or Issue Credit Memo | DEVELOPMENT |  |  | URGENT | FG & CW approved by Hayden 7/19. | 8 | 0 | 2025-08-24 | 2025-06-04 | 2025-01-15 12:05 | 2025-08-25 01:00 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v8b0 868a2v6bc 868em8m62 | https://app.clickup.com/t/868a2v8b0 https://app.clickup.com/t/868a2v6bc https://app.clickup.com/t/868em8m62 | ilt, o2c | Development | [7 empty] | 311 hours |  | 0 | [7 empty] | Pending SIMs |  |  |  | ITC3 | Billing | Issue Output Manage Billing Documents |  | ILT |  | 2025-09-19 | Overdue | - [@Angie Paxton](#81508310) sent the content outline to [@Ashley Parker](#42484518) on 6/9/25. - Task was reassigned from [@Kristin Grappone](#81485796) to [@Ashley Parker](#42484518) on 6/12/25. | [14 empty] | O2C | Angie Paxton
868c01j8v | O2C Billing: Confirm Billing Eligibility | OUTLINES |  | Ashley Parker | HIGH | Tasks in Paused status because we are awaiting passed test scripts. Moving forward with course outline and wrapper development. | 1 | 0 | 2025-09-04 | 2025-08-19 | 2025-01-15 12:07 | 2025-08-25 12:03 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2vajt 868a2v6t9 868a2v9pu 868a2vbwy | https://app.clickup.com/t/868a2vajt https://app.clickup.com/t/868a2v6t9 https://app.clickup.com/t/868a2v9pu https://app.clickup.com/t/868a2vbwy | ilt, o2c | Development | [7 empty] | 147 hours |  | 0 | 2025-08-25 | 2025-08-25 |  |  | 2025-08-25 |  | Ashley Parker | Beta Revision (ISG) |  |  |  | ITC3 | Billing | Confirm Billing Eligibility |  | ILT |  | 2025-09-12 | Overdue | [15 empty] | O2C | Angie Paxton
868c01k8d | O2C Billing: Perform Fixed-Price Billing | DEVELOPMENT |  | Ashley Parker, Kaye Perrota | URGENT | @Angie Paxton @Kaye Perrota Sent FG and set up meeting to get CW started | 5 | 0 | 2025-08-18 | 2025-05-28 | 2025-01-15 12:08 | 2025-08-25 05:08 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v7uf 868a2v8qa 868a2vbzd 868a2v817 868drd9gv 868ent4ej 868ent4k5 868ent53h 868ent5t8 868ent6my 868ent6w4 | https://app.clickup.com/t/868a2v7uf https://app.clickup.com/t/868a2v8qa https://app.clickup.com/t/868a2vbzd https://app.clickup.com/t/868a2v817 https://app.clickup.com/t/868drd9gv https://app.clickup.com/t/868ent4ej https://app.clickup.com/t/868ent4k5 https://app.clickup.com/t/868ent53h https://app.clickup.com/t/868ent5t8 https://app.clickup.com/t/868ent6my https://app.clickup.com/t/868ent6w4 | ilt, o2c | Development | [7 empty] | 1636 hours |  | 0 | 2025-08-14 | [6 empty] | Final Review & Sign off (SME) |  |  |  | ITC3 | Billing | Perform Fixed-Cost Billing |  | ILT |  | 2025-09-19 | Overdue | - Outline was sent to [@Ashley Parker](#42484518) for review. - Converted WBT outline draft to ILT per SME request and shared with [@Angie Paxton](#81508310) and [@Ashley Parker](#42484518) for QA. - [@Trish Cortez](#50219539) notified that the task is ready for QA. - Recently reassigned to [@Ashley Parker](#42484518) for further action. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868c01kzg | O2C Billing: Perform Billing with Financing | OUTLINES |  | Ashley Parker | URGENT | @Angie Paxton sent FG 8/20 | 4 | 0 | 2025-09-04 | 2025-08-19 | 2025-01-15 12:08 | 2025-08-25 12:03 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v9vq 868a2v76f 868a2v9bp | https://app.clickup.com/t/868a2v9vq https://app.clickup.com/t/868a2v76f https://app.clickup.com/t/868a2v9bp | ilt, o2c | Development | [7 empty] | 147 hours |  | 0 | 2025-08-22 | 2025-08-25 |  | 2025-07-02 | 2025-08-25 |  | Ashley Parker | Beta Revision (ISG) | 2025-07-02 |  |  | ITC3 | Billing | Perform Cost-Based Billing |  | ILT |  | 2025-09-12 | Due | - [@Angie Paxton](#81508310) assigned the task to [@Ashley Parker](#42484518) on 06/12/2025. - No further progress or updates have been made since the assignment. | [14 empty] | O2C | Angie Paxton
868c01p1c | O2C Billing: Post Invoice | OUTLINES |  | Ashley Parker | URGENT | @Kaye Perrota please add this WBT development to your list behind Legacy Rate Year Interface and Planned Version Upload. | 1 | 0 |  |  | 2025-01-15 12:10 | 2025-08-24 23:26 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v9up | https://app.clickup.com/t/868a2v9up | o2c, wbt | Development | [7 empty] | 627 hours |  | 0 | 2025-06-02 | [5 empty] | Kaye Perrota | Ready for OL Draft |  |  |  | ITC3 | Billing | Post Invoice |  | WBT |  | 2025-09-12 | Overdue | [15 empty] | O2C | Angie Paxton
868c01rhv | O2C Billing: Perform Cost-Based Billing | DEVELOPMENT |  | Ashley Parker | URGENT | @Angie Paxton Various changes made to CW as this is the sample course | 20 | 0 |  | 2025-05-19 | 2025-01-15 12:12 | 2025-08-19 06:59 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2vbuh 868a2v94z 868a2v7vz 868a2v8rh 868a2v6u1 868a2vadv | https://app.clickup.com/t/868a2vbuh https://app.clickup.com/t/868a2v94z https://app.clickup.com/t/868a2v7vz https://app.clickup.com/t/868a2v8rh https://app.clickup.com/t/868a2v6u1 https://app.clickup.com/t/868a2vadv | ilt, o2c | Development | [7 empty] | 1636 hours |  | 0 | 2025-06-19 | 2025-07-01 |  |  | 2025-07-08 |  |  | Pending SIMs |  |  |  | ITC3B | Billing | Perform Cost-Based Billing |  | ILT |  | 2025-09-19 | Overdue | - Outline was converted to ILT and reviewed by [@Angie Paxton](#81508310) and [@Ashley Parker](#42484518). - QA was completed by [@Anya Toms](#81516068) with tracked changes and comments; edits made based on feedback. - Most recent activity: [@Mac Thomas](#81561899) has been assigned to develop the course wrapper. | [7 empty] | 2025-06-17 | [6 empty] | O2C | Angie Paxton, Shannon Bagent
868c01t4m | O2C Billing: Perform Time & Material Billing | DEVELOPMENT |  | Ashley Parker | HIGH | FG and CW on hold until after Simulation September | 2 | 0 |  |  | 2025-01-15 12:12 | 2025-08-25 12:05 |  |  | Brice LeBlanc | Lockheed Martin | Course Development | Development | 868a2v92g 868a2v6dd 868a2v8mw 868a2v5t2 868a2v9tv 868drhtzz | https://app.clickup.com/t/868a2v92g https://app.clickup.com/t/868a2v6dd https://app.clickup.com/t/868a2v8mw https://app.clickup.com/t/868a2v5t2 https://app.clickup.com/t/868a2v9tv https://app.clickup.com/t/868drhtzz | ilt, o2c | Development | [7 empty] | 75 hours |  | 0 | [6 empty] | Ashley Parker | Ready for OL Draft |  |  |  | ITC3B | Billing | Perform Cost-Based Billing |  | ILT |  | 2025-09-26 | Overdue | [15 empty] | O2C | Angie Paxton
868c02ej2 | A2R Lease Lifecycle Management: Create Manual Catch Up Journal Entry | DEVELOPMENT | The string tests we were given support an automated process where some of it has not been built in the system yet. Tammy had tried to show us the manual process but the manual way to do it was not working in the system. |  | NORMAL | @Steve Hile and @Veronica Massey , updated the Process Flow diagram slide for better readability and flow. | 14 | 0 | 2025-08-28 | 2025-07-15 | 2025-01-15 12:29 | 2025-08-25 13:13 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868axyb8k 868eqw1cy | https://app.clickup.com/t/868axyb8k https://app.clickup.com/t/868eqw1cy | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 |  |  | TRUE |  |  |  |  | Final Review & Sign off (SME) |  |  |  | ITC3B | Lease Lifecycle Management | Real Estate Lease Lifecycle | TRUE | WBT |  | 2025-08-29 | Due | [8 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c02kbb | A2R Lease Lifecycle Management: Run Integration Job for Payment Inbound File to LMBuildings | COMPLETED |  |  | URGENT | @Trish Cortez , the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360. | 10 | 0 | 2025-01-31 | 2025-01-23 | 2025-01-15 12:33 | 2025-08-13 08:20 |  | 2025-03-12 13:17 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2uwdz | https://app.clickup.com/t/868a2uwdz | a2r, wbt, mfc | Development | [7 empty] | 3986 hours |  | 0 |  | 2025-02-07 |  |  | 2025-01-31 |  |  | Hand off to OCM Team | 2025-02-12 |  |  | ITC1 | Lease Lifecycle Management | Real Estate Lease Lifecycle | TRUE | WBT |  | 2025-01-31 | Overdue | [8 empty] | 2025-04-10 | 2025-02-27 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c02mmv | A2R Lease Lifecycle Management: View Monthly Journal Entries | COMPLETED |  |  | URGENT | @Trish Cortez , the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360. | 9 | 0 | 2025-01-31 | 2025-01-23 | 2025-01-15 12:34 | 2025-08-13 08:20 |  | 2025-03-12 10:01 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2uwe8 | https://app.clickup.com/t/868a2uwe8 | wbt, a2r, mfc | Development | [7 empty] | 3990 hours |  | 0 |  |  |  |  | 2025-01-31 |  |  | Hand off to OCM Team | 2025-02-07 |  |  | ITC1 | Lease Lifecycle Management | Equipment OR Lease Lifecycle--process is common to both | TRUE | WBT |  | 2025-01-31 | Overdue | [8 empty] | 2025-04-10 | 2025-02-27 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c033tx | A2R Asset Accounting: Capitalizing Assets | COMPLETED | updated all recent changes: next buttons, non essential objects and closing screen. also playback and menu locked. |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 27 | 0 | 2025-04-11 | 2025-02-19 | 2025-01-15 12:44 | 2025-08-13 08:20 |  | 2025-04-03 12:57 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2va09 868a2v8xc 868a2v9ua 868a2v8ej 868a2v784 | https://app.clickup.com/t/868a2va09 https://app.clickup.com/t/868a2v8xc https://app.clickup.com/t/868a2v9ua https://app.clickup.com/t/868a2v8ej https://app.clickup.com/t/868a2v784 | a2r, wbt, mfc | Development | [7 empty] | 3459 hours |  | 0 | 2025-03-28 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Commissioning Assets | TRUE | WBT |  | 2025-04-11 | Overdue | [8 empty] | 2025-04-10 | 2025-04-03 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c03882 | A2R Asset Accounting: Depreciation Adjustments | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 30 | 0 | 2025-04-12 | 2025-02-22 | 2025-01-15 12:47 | 2025-08-13 08:21 |  | 2025-04-08 07:52 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v82z 868a2v606 868a2v83h 868a2v6r6 | https://app.clickup.com/t/868a2v82z https://app.clickup.com/t/868a2v606 https://app.clickup.com/t/868a2v83h https://app.clickup.com/t/868a2v6r6 | a2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 3344 hours |  | 0 | 2025-04-01 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-11 | Overdue | [8 empty] | 2025-04-10 | 2025-04-08 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c03qur | A2R Asset Accounting: Intra-Company Asset Transfer | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 41 | 0 | 2025-04-12 | 2025-02-26 | 2025-01-15 12:58 | 2025-08-13 08:21 |  | 2025-04-03 14:53 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vanu 868cmd801 868a2v6dm | https://app.clickup.com/t/868a2vanu https://app.clickup.com/t/868cmd801 https://app.clickup.com/t/868a2v6dm | a2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 3457 hours |  | 0 | 2025-04-01 | 2025-04-02 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-11 | Overdue | [8 empty] | 2025-04-10 | 2025-04-03 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c03rxt | A2R Asset Accounting: Asset Sales | COMPLETED | removed non essential text boxes throughout; added next button functionality; fixed course complete. |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 23 | 0 | 2025-04-14 | 2025-02-26 | 2025-01-15 12:59 | 2025-08-13 08:21 |  | 2025-04-08 14:37 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vbn7 868a2v9f0 868a2v735 | https://app.clickup.com/t/868a2vbn7 https://app.clickup.com/t/868a2v9f0 https://app.clickup.com/t/868a2v735 | a2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 3337 hours |  | 0 | 2025-03-28 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-14 | Overdue | [8 empty] | 2025-04-10 | 2025-04-08 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c03z42 | A2R Asset Accounting: Retire Assets | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 26 | 0 | 2025-04-06 | 2025-02-27 | 2025-01-15 13:04 | 2025-08-13 08:22 |  | 2025-03-31 13:37 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vb48 868a2vbv6 868a2v8m0 868a2v8qg 868a2v6jr 868a2v6g1 868a2vbak | https://app.clickup.com/t/868a2vb48 https://app.clickup.com/t/868a2vbv6 https://app.clickup.com/t/868a2v8m0 https://app.clickup.com/t/868a2v8qg https://app.clickup.com/t/868a2v6jr https://app.clickup.com/t/868a2v6g1 https://app.clickup.com/t/868a2vbak | a2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 3530 hours |  | 0 | 2025-03-21 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-04 | Overdue | [9 empty] | 2025-03-31 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0428w | A2R Asset Accounting: Asset Reinstatement | COMPLETED | all updates have been completed; pending change impacts slide only. |  | URGENT | @Trish Cortez , the final What's Changing in 1LMX slide is added. I reset all Player settings to our template standards and tested the full course. | 24 | 0 | 2025-04-14 | 2025-02-26 | 2025-01-15 13:07 | 2025-08-13 08:21 |  | 2025-04-08 10:44 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vb7b 868a2v9z7 868a2v8pv | https://app.clickup.com/t/868a2vb7b https://app.clickup.com/t/868a2v9z7 https://app.clickup.com/t/868a2v8pv | a2r, wbt, mfc | Development, ✍ Risk Register | [7 empty] | 3341 hours |  | 0 | 2025-03-28 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-14 | Overdue | [8 empty] | 2025-04-10 | 2025-04-08 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c043t3 | A2R Asset Accounting: Depreciation/Amortization Job Run & Review | COMPLETED | Removed all PDFs from this course. Updated Notes to be Transcript Updated VO on all slides - will need Murf when ready |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 22 | 0 | 2025-04-03 | 2025-02-19 | 2025-01-15 13:08 | 2025-08-13 08:21 |  | 2025-03-26 10:33 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6nr 868b0n58q 868a2v6a5 868b0n61m 868a2vax8 868a2v7ch 868a2v70d 868a2v7b0 | https://app.clickup.com/t/868a2v6nr https://app.clickup.com/t/868b0n58q https://app.clickup.com/t/868a2v6a5 https://app.clickup.com/t/868b0n61m https://app.clickup.com/t/868a2vax8 https://app.clickup.com/t/868a2v7ch https://app.clickup.com/t/868a2v70d https://app.clickup.com/t/868a2v7b0 | a2r, wbt, mfc | Development | [7 empty] | 3653 hours |  | 0 | 2025-03-18 | 2025-03-24 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Depreciate or Amortize Assets | TRUE | WBT |  | 2025-04-03 | Overdue | [8 empty] | 2025-04-10 | 2025-03-26 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c04kmx | PTP SCM Requisition to Procure: Non-MRP Request and Approval - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-01-15 13:21 | 2025-08-07 06:04 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dp0hpq 868dp0k7v 868dp0mkv 868dp0ng3 868dp0p68 868dp0pqu | https://app.clickup.com/t/868dp0hpq https://app.clickup.com/t/868dp0k7v https://app.clickup.com/t/868dp0mkv https://app.clickup.com/t/868dp0ng3 https://app.clickup.com/t/868dp0p68 https://app.clickup.com/t/868dp0pqu | ptp, wbt, lean request | Development | [7 empty] | 442 hours |  | 0 | [6 empty] | Anya Toms | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Purchase Requisition Mgmt (MRP/Non-MRP) & Approval |  | WBT |  | 2025-08-29 | [16 empty] | PTP | Jenn Cooke, Shannon Bagent
868c053xr | A2R Asset Accounting: Inter-Company Asset Transfer | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 32 | 0 | 2025-04-12 | 2025-02-26 | 2025-01-15 13:35 | 2025-08-13 08:21 |  | 2025-04-03 14:46 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v70x 868c18qwt 868c0urzw 868a2v8x0 868d47wq8 | https://app.clickup.com/t/868a2v70x https://app.clickup.com/t/868c18qwt https://app.clickup.com/t/868c0urzw https://app.clickup.com/t/868a2v8x0 https://app.clickup.com/t/868d47wq8 | a2r, wbt, mfc | Development | [7 empty] | 3457 hours |  | 0 | 2025-04-01 | 2025-04-02 | [5 empty] | Hand off to OCM Team |  |  |  | ITC2 | Asset Accounting | Disposition, Decommission, and Miscellaneous Transactions | TRUE | WBT |  | 2025-04-11 | Overdue | [8 empty] | 2025-04-10 | 2025-04-03 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c05dh1 | A2R Asset Management: Create Equipment | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 32 | 0 | 2025-05-10 | 2025-04-17 | 2025-01-15 13:42 | 2025-08-13 08:22 |  | 2025-05-15 09:50 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v8zc 868bdht92 868bdhy20 868bdhy3h 868bdhy51 868bdhy74 | https://app.clickup.com/t/868a2v8zc https://app.clickup.com/t/868bdht92 https://app.clickup.com/t/868bdhy20 https://app.clickup.com/t/868bdhy3h https://app.clickup.com/t/868bdhy51 https://app.clickup.com/t/868bdhy74 | wbt, a2r, mfc | Development | [7 empty] | 2454 hours |  | 0 | 2025-04-29 |  |  | 2025-05-05 | 2025-05-05 |  |  | Hand off to OCM Team | 2025-05-06 |  |  | ITC3B | Asset Management | Create and Maintain Master Records | TRUE | WBT |  | 2025-05-09 | Overdue | [8 empty] | 2025-04-08 | 2025-05-15 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c07d42 | A2R Asset Management: Change Equipment | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 25 | 0 | 2025-07-25 | 2025-04-15 | 2025-01-15 14:26 | 2025-08-13 08:22 |  | 2025-05-15 05:34 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vade 868a2v82m | https://app.clickup.com/t/868a2vade https://app.clickup.com/t/868a2v82m | a2r, wbt, mfc | Development | [7 empty] | 2458 hours |  | 0 | 2025-05-12 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | Asset Management | Create and Maintain Master Records | TRUE | WBT |  | 2025-07-25 | Overdue | [8 empty] | 2025-04-08 | 2025-05-15 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0egxp | A2R Asset Management: Display Equipment | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 29 | 0 | 2025-05-15 | 2025-04-18 | 2025-01-15 17:10 | 2025-08-13 08:22 |  | 2025-05-15 05:35 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vabk 868a2vbej | https://app.clickup.com/t/868a2vabk https://app.clickup.com/t/868a2vbej | a2r, wbt, mfc | Development | [7 empty] | 2458 hours |  | 0 | 2025-05-06 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | Asset Management | Create and Maintain Master Records | TRUE | WBT |  | 2025-05-15 | Overdue | [8 empty] | 2025-04-08 | 2025-05-15 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0ejxa | A2R Asset Management: Inventory Counts | DEVELOPMENT |  | Kris Thayer | HIGH | @Steve Hile , updates complete and republished. Ready for SME Review. | 20 | 0 | 2025-09-05 | 2025-06-09 | 2025-01-15 17:12 | 2025-08-22 12:16 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v8p2 | https://app.clickup.com/t/868a2v8p2 | a2r, wbt | Development | [7 empty] | 1661 hours |  | 0 | 2025-06-25 | [5 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3 | Asset Management | Perform Asset Inventory |  | WBT |  | 2025-08-29 | Due | - Course outline was prepared and sent for internal QA and VS QA. - [@David Rood](#75423976) completed QA with minor punctuation edits, and the document was updated accordingly. - File was moved to SME review area and status updated to 'Ready for SME review' by [@Veronica Massey](#57129402). - On 06/12, [@Steve Hile](#81539658) set the task status to Paused. | [7 empty] | 2025-04-08 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0enzz | A2R Asset Management: Review a Custodian Transfer | DEVELOPMENT |  | Bailey Petty | URGENT | Edits complete, ready for SME review! @Steve Hile | 12 | 0 | 2025-08-22 |  | 2025-01-15 17:14 | 2025-08-24 22:10 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vaca 868a2v64q | https://app.clickup.com/t/868a2vaca https://app.clickup.com/t/868a2v64q | a2r, wbt, mfc | Development | [7 empty] | 820 hours |  | 0 | 2025-08-01 | [5 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | Asset Management | Disposition Asset |  | WBT |  | 2025-08-29 | Overdue | - [@Kris Thayer](#44142438) created the course outline and shared it for internal QA with [@Trish Cortez](#50219539) and [@Steve Hile](#81539658). - [@Anya Toms](#81516068) completed QA and provided feedback, which was acknowledged by [@Kris Thayer](#44142438). - The outline was then sent to [@Steve Hile](#81539658) for VS Lead QA. - Development status was set to Paused by [@Steve Hile](#81539658) on 06/12. | [7 empty] | 2025-04-08 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0euff | A2R Asset Management: Create a Custodian Transfer | DEVELOPMENT |  | Bailey Petty | URGENT | @Shannon Bagent Are you able to QA this one too? TY @Bailey Petty please send us the link. TY | 13 | 0 | 2025-08-22 |  | 2025-01-15 17:18 | 2025-08-23 01:00 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v8jp 868a2vaxe 868a2vbkf 868a2v7b5 | https://app.clickup.com/t/868a2v8jp https://app.clickup.com/t/868a2vaxe https://app.clickup.com/t/868a2vbkf https://app.clickup.com/t/868a2v7b5 | a2r, wbt, mfc | Development | [7 empty] | 820 hours |  | 0 | 2025-07-29 | [5 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | Asset Management | Disposition Asset |  | WBT |  | 2025-08-29 | Overdue | - [@Kris Thayer](#44142438) notified [@Trish Cortez](#50219539) and [@Steve Hile](#81539658) that the course outline was ready for internal QA. - [@Ashley Parker](#42484518) completed internal QA and left comments in the document. - [@Steve Hile](#81539658) was notified that the outline was ready for VS Lead QA. - Development status was set to "Paused" by [@Steve Hile](#81539658). | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0ewgt | A2R Asset Management: Preparing for an Equipment Transfer | DEVELOPMENT |  | Bailey Petty | URGENT | OL SME approved and ready for SL development. | 9 | 0 | 2025-08-22 |  | 2025-01-15 17:20 | 2025-08-24 22:09 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v7xz | https://app.clickup.com/t/868a2v7xz | a2r, wbt, mfc | Development | [7 empty] | 265 hours |  | 0 | [6 empty] | Bailey Petty | Ready for Development |  |  |  | ITC3B | Asset Management | Disposition Asset | TRUE | WBT |  | 2025-08-29 | Overdue | - [@Steve Hile](#81539658) updated the Development Status to Paused on 06/12/2025. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0ex67 | A2R Asset Management: Disposition Equipment Self-Service | DEVELOPMENT |  | Bailey Petty | URGENT | OL SME approved and ready for SL development. | 9 | 0 | 2025-08-22 |  | 2025-01-15 17:21 | 2025-08-24 21:45 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v5um 868a2v7m2 868a2v88c | https://app.clickup.com/t/868a2v5um https://app.clickup.com/t/868a2v7m2 https://app.clickup.com/t/868a2v88c | a2r, wbt, mfc | Development | [7 empty] | 265 hours |  | 0 | [6 empty] | Bailey Petty | Ready for Development |  |  |  | ITC3B | Asset Management | Disposition Asset |  | WBT |  | 2025-08-29 | Overdue | - Development status was changed to Paused by [@Steve Hile](#81539658). - [@Steve Hile](#81539658) suggested possibly rolling this up to the new Loss/Retirement condensed courses. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0ey9j | A2R Asset Management: Manage Loss Reports | DEVELOPMENT |  | Bailey Petty | URGENT | QA Complete @Steve Hile | 11 | 0 | 2025-08-29 | 2025-08-18 | 2025-01-15 17:23 | 2025-08-25 07:55 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v7yn 868a2v8a1 868a2v8w3 | https://app.clickup.com/t/868a2v7yn https://app.clickup.com/t/868a2v8a1 https://app.clickup.com/t/868a2v8w3 | a2r, wbt, mfc | Development | [7 empty] | 175 hours |  | 0 | [6 empty] | Bailey Petty | Ready for QA |  |  |  | ITC3B | Asset Management | Disposition Asset | TRUE | WBT |  | 2025-09-05 | Overdue | - [@Steve Hile](#81539658) updated the Development Status to 'Paused'. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0f042 | A2R Asset Management: Disposition an Asset Prepare a Loss Report | DEVELOPMENT |  | Bailey Petty | URGENT | @Bailey Petty this storyline course is ready for you to develop as well. It goes along with the SIM you are finishing. | 8 | 0 | 2025-08-29 |  | 2025-01-15 17:25 | 2025-08-24 21:43 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6ua | https://app.clickup.com/t/868a2v6ua | a2r, wbt, mfc | Development | [7 empty] | 309 hours |  | 0 | [6 empty] | Bailey Petty | Ready for Development |  |  |  | ITC3B | Asset Management | Disposition Asset | TRUE | WBT |  | 2025-09-05 | Overdue | - [@Steve Hile](#81539658) set the task status to Paused. - [@Steve Hile](#81539658) commented that all Loss Report courses and tasks will be rolled up. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0f20b | A2R Asset Management: Equipment Disposition Final User Statuses and Post-Disposition | DEVELOPMENT |  |  | URGENT | SME approved OL 8/19. Ready for Dev | 11 | 0 | 2025-08-29 |  | 2025-01-15 17:27 | 2025-08-22 14:12 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v919 868a2v7vd 868a2v89v | https://app.clickup.com/t/868a2v919 https://app.clickup.com/t/868a2v7vd https://app.clickup.com/t/868a2v89v | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [7 empty] | Beta Revision (ISG) |  |  |  | ITC3B | Asset Management | Disposition Asset |  | WBT |  | 2025-08-29 | Overdue | - SMEs recommended combining three related tasks for final disposition tracking. - [@Brice LeBlanc](#75334455) was offered a new outline; [@Veronica Massey](#57129402) confirmed support. - [@Steve Hile](#81539658) paused AM courses and removed [@Brice LeBlanc](#75334455) from the task. - Development status was updated to Paused. | [7 empty] | 2025-04-08 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0f41w | A2R Asset Management: Equipment Disposition Records, Requirements, and Notifications | DEVELOPMENT |  | Bailey Petty | URGENT | @Steve Hile @Bailey Petty QA complete, just a couple of minor comments | 17 | 0 | 2025-08-29 |  | 2025-01-15 17:30 | 2025-08-24 21:58 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vaqw 868a2v8k1 | https://app.clickup.com/t/868a2vaqw https://app.clickup.com/t/868a2v8k1 | a2r, wbt, mfc | Development | [7 empty] | 798 hours |  | 0 | [6 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | Asset Management | Disposition Asset | TRUE | WBT |  | 2025-09-05 | Overdue | - Course outline was drafted and internal QA completed by [@Brice LeBlanc](#75334455) with minor edits. - VS Lead QA was finished by [@Steve Hile](#81539658), with edits added and comments for [@Veronica Massey](#57129402). - All edits were implemented and the outline is now parked in the SME review folder. - Development is currently paused, pending SME review and status update. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0f7ea | A2R Controlled Tooling: Provide Disposition | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready to upload to the LMS. The final SL file and URL are in the Teams' Deliverables > WBT subfolders. | 17 | 0 | 2025-06-14 | 2025-05-05 | 2025-01-15 17:35 | 2025-08-13 08:23 |  | 2025-08-07 12:38 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vbb3 | https://app.clickup.com/t/868a2vbb3 | a2r, mfc, wbt | Development | [7 empty] | 435 hours |  | 0 | 2025-06-04 |  |  |  | 2025-06-05 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) |  | WBT |  | 2025-07-14 | Overdue | - Internal QA was completed by [@Eugene Deloatch](#81458171) with minor edits, which were implemented. - VS Lead QA was completed by [@Steve Hile](#81539658), and the course outline was approved for development. - SME alpha WBT review was completed and approved by [@Steve Hile](#81539658). - Course is ready for final WBT review with tasks as the next step. | [7 empty] | 2025-05-01 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0f92c | A2R Controlled Tooling: Hard/Durable Tooling: Work Order Flow for Preventative Maintenance | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready to upload to the LMS. The final SL file and URL are located in the Teams Deliverables > WBT subfolders. | 22 | 0 | 2025-06-21 | 2025-05-05 | 2025-01-15 17:38 | 2025-08-13 08:23 |  | 2025-08-07 12:38 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vbf5 868a2vbn1 868a2v7t1 | https://app.clickup.com/t/868a2vbf5 https://app.clickup.com/t/868a2vbn1 https://app.clickup.com/t/868a2v7t1 | a2r, mfc, wbt | Development | [7 empty] | 435 hours |  | 0 | 2025-06-03 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) |  | WBT |  | 2025-07-21 | Overdue | [8 empty] | 2025-05-01 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0fcvf | A2R Controlled Tooling: Hard/Durable Tooling: Handling | COMPLETED | / |  | URGENT | @Trish Cortez , this course is ready for upload to the LMS. The final SL file and URL are posted in the Teams Deliverables > WBT subfolders. | 29 | 0 | 2025-06-10 | 2025-05-21 | 2025-01-15 17:41 | 2025-08-13 08:24 |  | 2025-08-04 07:53 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v80m | https://app.clickup.com/t/868a2v80m | a2r, mfc, wbt | Development | [7 empty] | 512 hours |  | 0 | 2025-05-27 |  |  |  | 2025-06-04 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) |  | WBT |  | 2025-07-10 | Overdue | [8 empty] | 2025-04-21 | 2025-08-04 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0fe1w | A2R Controlled Tooling: Hard/Durable Tooling: Inspection | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready for LMS upload. The final SL file and URL are located in the Teams Deliverables > WBT subfolders. | 20 | 0 | 2025-06-13 | 2025-04-22 | 2025-01-15 17:42 | 2025-08-13 08:22 |  | 2025-08-04 09:06 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6v9 | https://app.clickup.com/t/868a2v6v9 | a2r, wbt, mfc | Development | [7 empty] | 511 hours |  | 0 | 2025-05-29 |  |  |  | 2025-06-04 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) |  | WBT |  | 2025-06-13 | Overdue | [8 empty] | 2025-04-21 | 2025-08-04 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0fg88 | A2R Controlled Tooling: Hard/Durable Tooling: Maintenance Part A | DEVELOPMENT |  | Kris Thayer | URGENT | SME approved course -- development complete from a storyline perspective, but still awaiting defect resolution for one sim: Create Tooling Action Request. Defect prevents us from recording the sim/finalizing the content. | 22 | 0 |  | 2025-04-10 | 2025-01-15 17:45 | 2025-08-22 14:11 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vb0u 868a2v5kr 868a2v7wg | https://app.clickup.com/t/868a2vb0u https://app.clickup.com/t/868a2v5kr https://app.clickup.com/t/868a2v7wg | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [6 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) | TRUE | WBT |  | 2025-09-19 | Due | [8 empty] | 2025-04-10 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0fpq7 | A2R Controlled Tooling: Hard/Durable Tooling: Location Management | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready for LMS upload. The final SL file and URL are located in the Teams Deliverables > WBT subfolders. | 18 | 0 | 2025-06-07 | 2025-04-28 | 2025-01-15 17:51 | 2025-08-13 08:23 |  | 2025-08-04 09:07 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6aa 868a2va6h | https://app.clickup.com/t/868a2v6aa https://app.clickup.com/t/868a2va6h | a2r, mfc, wbt | Development | [7 empty] | 510 hours |  | 0 | 2025-05-19 |  |  | 2025-05-30 | 2025-05-29 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) | TRUE | WBT |  | 2025-07-07 | Overdue | [8 empty] | 2025-04-09 | 2025-08-04 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0fqu7 | A2R Controlled Tooling: Preliminary Tasks for Hard/Durable Tooling | COMPLETED |  |  | NORMAL | @Trish Cortez , this course is ready to upload to the LMS. The final SL and URL are located in the Teams Deliverables > WBT subfolders. | 31 | 0 | 2025-06-07 | 2025-05-08 | 2025-01-15 17:53 | 2025-08-13 08:23 |  | 2025-08-07 12:38 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v7fa | https://app.clickup.com/t/868a2v7fa | a2r, mfc, wbt | Development | [7 empty] | 435 hours |  | 0 | 2025-05-21 |  |  | 2025-05-30 | 2025-05-30 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) | TRUE | WBT |  | 2025-07-07 | Overdue | [8 empty] | 2025-04-09 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0g1dr | A2R Asset Management: Asset Acquisition SAP and PIEE Interface | DEVELOPMENT |  | Bailey Petty | URGENT | @Steve Hile Edits applied, ready fo VS QA | 14 | 0 | 2025-08-29 |  | 2025-01-15 18:02 | 2025-08-24 21:34 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vbnt 868a2vbqr | https://app.clickup.com/t/868a2vbnt https://app.clickup.com/t/868a2vbqr | a2r, wbt, mfc | Development | [7 empty] | 819 hours |  | 0 | 2025-07-29 | [5 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | Asset Management | Acquire Assets | TRUE | WBT |  | 2025-08-29 07:55 | Overdue | - Course outline was developed and sent to [@Brice LeBlanc](#75334455) for drafting. - Internal QA by [@Veronica Massey](#57129402) completed with minor edits implemented. - VS QA by [@Veronica Massey](#57129402) and [@Brice LeBlanc](#75334455) finished; edits added and document moved to SME review. - Development status set to Paused as of 06/12/2025. | [7 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0qr9k | A2R CLRP Capital: Create Plan Item and Enter Financial and Labor Plan | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 21 | 0 | 2025-06-16 | 2025-05-19 | 2025-01-16 06:52 | 2025-08-13 08:23 |  | 2025-07-24 06:50 | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddpgu1 868ddph2j 868ddph6h 868ddphcm 868ddphjn | https://app.clickup.com/t/868ddpgu1 https://app.clickup.com/t/868ddph2j https://app.clickup.com/t/868ddph6h https://app.clickup.com/t/868ddphcm https://app.clickup.com/t/868ddphjn | a2r, mfc, wbt | Development | [7 empty] | 777 hours |  | 0 | 2025-06-11 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-07-16 | Overdue | - Course is ready for internal QA; Kris Thayer notified Trish Cortez and Steve Hile. - Trish Cortez assigned QA to [@Ashley Parker](#42484518) and provided instructions. - Kris Thayer sent the Review 360 link to [@Ashley Parker](#42484518) for review. | [7 empty] | 2025-04-14 | 2025-07-24 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0qunf | A2R Metrology: Limitation Requests | DEVELOPMENT |  | Bailey Petty | URGENT | SME approved OL 8/5. Ready for SL Dev. @Veronica Massey | 6 | 0 | 2025-09-05 | 2025-07-09 | 2025-01-16 06:56 | 2025-08-15 10:59 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v5w5 868a2v8wt 868a2vbg2 868a2v9zk | https://app.clickup.com/t/868a2v5w5 https://app.clickup.com/t/868a2v8wt https://app.clickup.com/t/868a2vbg2 https://app.clickup.com/t/868a2v9zk | a2r, wbt, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Bailey Petty | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration |  | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-04-18 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tgdv | A2R Metrology: IndySoft: Quality Controls | DEVELOPMENT |  | Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL dev. @Veronica Massey | 6 | 0 | 2025-09-05 | 2025-07-07 | 2025-01-16 07:54 | 2025-08-15 10:54 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2va0z 868a2v6fp | https://app.clickup.com/t/868a2va0z https://app.clickup.com/t/868a2v6fp | a2r, wbt, indysoft, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration | TRUE | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-04-30 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tkqd | A2R Metrology: IndySoft: Logistics | DEVELOPMENT |  | Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL dev. @Veronica Massey | 6 | 0 | 2025-09-05 | 2025-07-09 | 2025-01-16 07:57 | 2025-08-25 00:37 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2va1x 868a2v5uw 868a2v85p | https://app.clickup.com/t/868a2va1x https://app.clickup.com/t/868a2v5uw https://app.clickup.com/t/868a2v85p | a2r, wbt, indysoft, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-04-30 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tpmz | A2R Metrology: IndySoft: External Vendors | DEVELOPMENT |  | Bailey Petty, Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL Dev. @Veronica Massey | 6 | 0 | 2025-09-05 | 2025-07-08 | 2025-01-16 07:59 | 2025-08-19 09:07 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6ak 868a2v8n8 | https://app.clickup.com/t/868a2v6ak https://app.clickup.com/t/868a2v8n8 | a2r, wbt, indysoft, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Bailey Petty | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration |  | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-04-30 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tqp1 | A2R Metrology: IndySoft: Calibration Event | DEVELOPMENT |  | Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL dev. @Veronica Massey | 5 | 0 | 2025-09-05 | 2025-07-07 | 2025-01-16 08:01 | 2025-08-15 10:55 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vbxm | https://app.clickup.com/t/868a2vbxm | a2r, wbt, indysoft, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration | TRUE | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-04-30 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tt5m | A2R CLRP Capital: Capital Forecast Depreciation Model SAC | PREDEVELOPMENT |  | Veronica Massey | LOW | Per SMEs F2F meeting 7/21. Keep this course. It is normal priority so dev can happen after all high-priority tasks are completed. | 2 | 0 |  |  | 2025-01-16 08:02 | 2025-08-24 22:16 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v9t5 868ddu71d 868ddu75g 868ddu78d 868ddu7mk 868ddu7te 868ddu7w0 | https://app.clickup.com/t/868a2v9t5 https://app.clickup.com/t/868ddu71d https://app.clickup.com/t/868ddu75g https://app.clickup.com/t/868ddu78d https://app.clickup.com/t/868ddu7mk https://app.clickup.com/t/868ddu7te https://app.clickup.com/t/868ddu7w0 | a2r, wbt | Development | [7 empty] | 1828 hours |  | 0 | [6 empty] | Veronica Massey | Course Package Not Started |  |  |  | ITC3B | CLRP | Forecasting Depreciation |  | WBT |  | 2025-09-26 | [9 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tu34 | A2R CLRP Capital: Capital Project Closeout | DEVELOPMENT |  | Kris Thayer | URGENT | @Steve Hile , updates from today's SME Review and additional steps slide for Manually Updating Settlement Rules is ready for your review. | 27 | 0 | 2025-08-25 | 2025-06-13 | 2025-01-16 08:03 | 2025-08-24 22:17 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddnzqk 868ddp3pe 868ddp4j9 | https://app.clickup.com/t/868ddnzqk https://app.clickup.com/t/868ddp3pe https://app.clickup.com/t/868ddp4j9 | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [7 empty] | Final Review & Sign off (SME) |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-08-29 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tw8v | A2R CLRP Overhead: Overhead Project Closeout | DEVELOPMENT |  | Bailey Petty | NORMAL | QA complete @Steve Hile | 13 | 0 | 2025-09-05 | 2025-06-13 | 2025-01-16 08:05 | 2025-08-24 23:55 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddug1y | https://app.clickup.com/t/868ddug1y | a2r, wbt, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Capital Project Closeout L4), Planning Strategy |  | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0tybt | A2R CLRP Capital: Change Request Workflow | COMPLETED |  |  | URGENT | Ian lockdown complete 8/21 | 20 | 0 | 2025-08-22 | 2025-06-23 | 2025-01-16 08:06 | 2025-08-25 11:33 |  | 2025-08-21 05:43 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6t1 868a2v5jg | https://app.clickup.com/t/868a2v6t1 https://app.clickup.com/t/868a2v5jg | a2r, mfc, wbt | Development | [7 empty] | 106 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | ITC3B | CLRP | Execute CLRP (Manage Project Performance L4) |  | WBT |  | 2025-08-22 | Overdue | [9 empty] | 2025-08-21 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0tzq4 | A2R CLRP Capital: Change Requests | DEVELOPMENT |  | Kris Thayer | URGENT | @Shannon Bagent thanks! @Steve Hile this course is ready for SME Review. We need content for one lesson (Change Request Process details) besides the simulation for the other lesson. | 13 | 0 | 2025-08-29 | 2025-06-19 | 2025-01-16 08:08 | 2025-08-24 22:12 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v6au | https://app.clickup.com/t/868a2v6au | a2r, wbt, mfc | Development | [7 empty] | 1111 hours |  | 0 | 2025-07-10 | [5 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Manage Project Performance L4) |  | WBT |  | 2025-09-19 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0u5nk | A2R CLRP Capital: Prioritize Plan Items Inputs | DEVELOPMENT |  | Kris Thayer | URGENT | Thanks @Brice LeBlanc for the review! @Steve Hile updates from QA completed. This course is ready for SME Review. | 18 | 0 | 2025-08-29 | 2025-06-19 | 2025-01-16 08:15 | 2025-08-24 23:01 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddun6b 868ddunch 868ddunh0 868ddunjn | https://app.clickup.com/t/868ddun6b https://app.clickup.com/t/868ddunch https://app.clickup.com/t/868ddunh0 https://app.clickup.com/t/868ddunjn | a2r, wbt, mfc | Development | [7 empty] | 1302 hours |  | 0 | 2025-07-02 | [5 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Develop CLRP (Prioritize Plan Item Inputs L4) |  | WBT |  | 2025-09-19 | Due | [8 empty] | 2025-04-21 | [6 empty] | A2R | Trish Cortez, Steve Hile
868c0u6gn | A2R CLRP Capital: Update Capital Plan Items | COMPLETED |  |  | URGENT | @Trish Cortez ,the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 28 | 0 | 2025-05-24 | 2025-05-02 | 2025-01-16 08:16 | 2025-08-13 08:23 |  | 2025-05-22 14:18 | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2vc3d 868a2v67h | https://app.clickup.com/t/868a2vc3d https://app.clickup.com/t/868a2v67h | a2r, mfc, wbt | Development | [7 empty] | 2281 hours |  | 0 | 2025-05-09 |  |  |  | 2025-05-15 |  |  | Hand off to OCM Team |  |  |  | ITC3B | CLRP | Develop CLRP (Manage Plan Financials L4) | TRUE | WBT |  | 2025-05-23 | Overdue | [8 empty] | 2025-06-02 | 2025-05-22 | [5 empty] | A2R | Trish Cortez, Steve Hile
868c0uctc | A2R CLRP Capital: Approval Workflow | DEVELOPMENT |  | Kris Thayer | URGENT | Thanks @Brice LeBlanc ! @Steve Hile this is ready for SME Review. | 18 | 0 | 2025-08-29 | 2025-06-17 | 2025-01-16 08:22 | 2025-08-24 22:13 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddmzxg 868ddn6v7 | https://app.clickup.com/t/868ddmzxg https://app.clickup.com/t/868ddn6v7 | a2r, wbt | Development | [7 empty] | 1179 hours |  | 0 | 2025-07-09 | [5 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-12 | Due | [15 empty] | A2R | Trish Cortez, Steve Hile
868c0vw6a | PTP SCM Requisition to Procure: Source Inspections & Monitoring - OL | OUTLINES |  | Jessica Reed | LOW | Per Matt today, this is now a Low-priority course | 2 | 0 | 2025-08-10 | 2025-07-15 | 2025-01-16 09:08 | 2025-08-24 22:55 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c0vynd 868c0vz60 | https://app.clickup.com/t/868c0vynd https://app.clickup.com/t/868c0vz60 | ptp, wbt | Development | [7 empty] | 634 hours |  | 0 |  |  |  | 2025-08-15 | 2025-08-14 |  | Jessica Reed | Beta Review (SME) |  |  |  | ITC4 | Supply Chain | PO Generation, Approval & Release Strategy |  | WBT |  | 2025-09-05 | Overdue | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868c0wh7b | A2R CLRP Capital: Capital EPPM Administrative Tasks | PREDEVELOPMENT |  | Veronica Massey | LOW | Per SMEs F2F meeting 7/21. Keep this course. It is normal priority so dev can happen after all high-priority tasks are completed. | 1 | 0 |  |  | 2025-01-16 09:27 | 2025-08-24 22:15 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868a2v8fc 868a2v5tw | https://app.clickup.com/t/868a2v8fc https://app.clickup.com/t/868a2v5tw | wbt, a2r | Development | [7 empty] | 1828 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | CLRP | No L3 Custom Content |  | WBT |  | 2025-09-26 | [16 empty] | A2R | Trish Cortez, Steve Hile
868c190nq | PTP SCM Supplier Lifecycle Mgmt: Supplier Qualification & Onboarding - OL | OUTLINES |  | Jessica Reed | NORMAL | Per Matt today, this can be WBT instead of ILT - @Jessica Reed , we'll just need to shift the content we have into an outline template | 3 | 0 | 2025-08-07 | 2025-08-01 | 2025-01-16 14:50 | 2025-08-20 13:43 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2vbdq 868a2vbpn 868a2vanz 868a2vbdx 868a2v8r3 868a2v895 868a2vbkd | https://app.clickup.com/t/868a2vbdq https://app.clickup.com/t/868a2vbpn https://app.clickup.com/t/868a2vanz https://app.clickup.com/t/868a2vbdx https://app.clickup.com/t/868a2v8r3 https://app.clickup.com/t/868a2v895 https://app.clickup.com/t/868a2vbkd | ptp, wbt | Development | [7 empty] | 634 hours |  | 0 | 2025-07-01 | [5 empty] | Jessica Reed | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Supplier Qualification & Onboarding |  | WBT |  | 2025-09-12 | Overdue | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1960a | PTP SCM Requisition to Procure: Create Fieldglass Worker User Profile | OUTLINES |  |  | NORMAL |  | 0 | 0 |  |  | 2025-01-16 14:56 | 2025-08-25 10:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1960h 868c1960f | https://app.clickup.com/t/868c1960h https://app.clickup.com/t/868c1960f | ptp, fieldglass, wbt | Development | [7 empty] | 1184 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Supply Chain | Service Procurement (Inc. Contingent Labor) |  | WBT |  | 2025-09-12 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868c198db | PTP SCM Requisition to Procure: Fieldglass Time and Expense Entry/Costing/Payment | OUTLINES |  |  | NORMAL |  | 0 | 0 |  |  | 2025-01-16 15:00 | 2025-08-25 10:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c198df 868c198dh 868c198dj | https://app.clickup.com/t/868c198df https://app.clickup.com/t/868c198dh https://app.clickup.com/t/868c198dj | qrg, fieldglass, ptp | Development | [7 empty] | 1184 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Supply Chain | Service Procurement (Inc. Contingent Labor) |  | QRG |  | 2025-09-12 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1rhqk | PTP Supplier Quality: Quality Clause Groups - OL | COMPLETED |  |  | URGENT | Full course approved by Dave Thompson, ready for Teresa Scanlan | 13 | 0 | 2025-08-17 | 2025-05-05 | 2025-01-17 09:10 | 2025-08-25 11:44 |  | 2025-08-25 11:44 | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1rhqx 868c1rhqy 868c1rt38 868f3mpj4 | https://app.clickup.com/t/868c1rhqx https://app.clickup.com/t/868c1rhqy https://app.clickup.com/t/868c1rt38 https://app.clickup.com/t/868f3mpj4 | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 4 hours |  | 0 | 2025-08-04 |  | TRUE |  |  |  |  | Sign off Received | 2025-08-14 |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-05-02 | 2025-08-25 | [5 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1rzhq | PTP Supplier Quality: Program Group Codes | DEVELOPMENT |  | Jenn Cooke | URGENT | @Jenn Cooke Edits/updates complete in SL file. Course wrapper is pending updated QRG. Ready for SME Review. | 8 | 0 | 2025-08-17 | 2025-07-14 | 2025-01-17 09:24 | 2025-08-24 23:39 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1rzj3 868c1rzhz 868c1rzhy | https://app.clickup.com/t/868c1rzj3 https://app.clickup.com/t/868c1rzhz https://app.clickup.com/t/868c1rzhy | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 846 hours |  | 0 |  |  | TRUE |  | 2025-08-07 |  | Jenn Cooke | Final Review & Sign off (SME) | 2025-08-11 |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wdmh | PTP Supplier Quality: Plant Overrides | DEVELOPMENT |  | Jessica Reed | URGENT | @Jenn Cooke starting SL development | 5 | 0 | 2025-08-19 | 2025-05-06 | 2025-01-17 11:13 | 2025-08-20 01:00 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1wdmx 868c1wdn0 | https://app.clickup.com/t/868c1wdmx https://app.clickup.com/t/868c1wdn0 | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1348 hours |  | 0 | 2025-08-15 |  | TRUE |  |  |  | Jessica Reed | Alpha Draft (ISG) |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wej1 | PTP Supplier Quality: Corporate Overrides | DEVELOPMENT |  | Jenn Cooke | URGENT | @Mac Thomas @Anya Toms I've completed a QA of this as well - some comments added to Review360 | 10 | 0 | 2025-07-25 | 2025-03-29 | 2025-01-17 11:15 | 2025-08-21 12:56 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1wejh 868c1wejf 868c1weje | https://app.clickup.com/t/868c1wejh https://app.clickup.com/t/868c1wejf https://app.clickup.com/t/868c1weje | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1928 hours |  | 0 |  |  | TRUE | 2025-08-11 | 2025-07-31 |  | Jenn Cooke | Beta Review (SME) |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [7 empty] | Edward Newman | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wfzz | PTP Supplier Quality: Override Selection Report (Run the ZOVERRIDE Report) - QRG | COMPLETED |  |  | URGENT | QRG approved by Dave Thompson, ready for Teresa Scanlan | 16 | 0 | 2025-08-17 | 2025-06-02 | 2025-01-17 11:16 | 2025-08-25 11:47 |  | 2025-08-25 11:44 | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, qrg | Development, ✍ Risk Register | [7 empty] | 4 hours |  | 0 | 2025-07-14 |  | TRUE | 2025-08-11 | 2025-08-07 |  |  | Sign off Received | 2025-08-14 |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | QRG |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-29 | 2025-08-25 | [5 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wncb | PTP Accounts Payable: Recurring Invoice Process | DEVELOPMENT |  |  | HIGH | Outline approved for development 7.22.25 | 6 | 0 | 2025-06-16 | 2025-06-04 | 2025-01-17 11:20 | 2025-08-25 01:19 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2v8pe | https://app.clickup.com/t/868a2v8pe | ptp, wbt, ot xecm | Development, ✍ Risk Register | [7 empty] | 801 hours |  | 0 | [6 empty] | Anya Toms | Ready for Development |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wx09 | PTP Accounts Payable: Verify Vendor | OUTLINES |  | Priscilla Holguin | HIGH |  | 0 | 0 |  |  | 2025-01-17 11:26 | 2025-08-06 13:10 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a36np0 868dryu24 868c1wxwd | https://app.clickup.com/t/868a36np0 https://app.clickup.com/t/868dryu24 https://app.clickup.com/t/868c1wxwd | wbt, ptp, ot vim, mdg | Development | [7 empty] | 1281 hours |  | 0 | [6 empty] | Priscilla Holguin | Ready for OL Draft |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-05 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wy6n | PTP Accounts Payable: Run A/P Invoice Audit Review | DEVELOPMENT |  |  | HIGH | Outline approved for development by Gina Garvey | 12 | 0 | 2025-07-04 | 2025-05-28 | 2025-01-17 11:28 | 2025-08-24 21:35 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1wzcv 868c1wzt8 | https://app.clickup.com/t/868c1wzcv https://app.clickup.com/t/868c1wzt8 | ptp, wbt, ot vim | Development, ✍ Risk Register | [7 empty] | 986 hours |  | 0 |  |  | TRUE |  |  |  |  | Ready for Development |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-12 | Overdue |  |  |  |  | TRUE |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1wydk | PTP Accounts Payable: Reject Invoice to Supplier | OUTLINES |  | Jessica Visser | HIGH | @Kameron Teal can you please QA this one? @Jessica Visser can provide the link on the LM side | 10 | 0 | 2025-08-23 | 2025-08-15 | 2025-01-17 11:29 | 2025-08-25 01:20 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a36xx0 868a36rjp | https://app.clickup.com/t/868a36xx0 https://app.clickup.com/t/868a36rjp | ptp, wbt, ot vim | Development, ✍ Risk Register | [7 empty] | 163 hours |  | 0 | 2025-08-19 |  | TRUE |  |  |  | Jessica Visser | Ready for QA |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-12 | Overdue |  |  |  | Kameron Teal |  |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1x051 | PTP Accounts Payable: Small Business Payment Acceleration | COMPLETED |  |  | HIGH | Course fully approved by Teresa Scanlan | 16 | 0 | 2025-07-19 | 2025-07-15 | 2025-01-17 11:31 | 2025-08-21 08:11 |  | 2025-07-30 10:43 | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ot vim, ptp, wbt | Development, ✍ Risk Register | [7 empty] | 629 hours |  | 0 | 2025-07-15 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-08-01 | Overdue | - [@Anya Toms](#81516068) started the outline and marked it ready for QA. - [@Jenn Cooke](#42510316) completed QA and sent it for review. - Feedback from Garvey was incorporated; awaiting her clarification on unposted invoice processing in VIM. - Initial delays were due to team illness, but progress has resumed. | [7 empty] | 2025-05-02 | 2025-07-30 | [5 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1x1dj | PTP Accounts Payable: Supplier Remedy & Retention Process - OL | DEVELOPMENT |  | Jessica Visser | HIGH | Outline approved for development by Gina Garvey | 5 | 0 | 2025-06-14 | 2025-06-03 | 2025-01-17 11:33 | 2025-08-24 21:56 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 986 hours |  | 0 |  |  | TRUE |  |  |  | Jessica Visser | Ready for Development |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-05 | Overdue | - [@Jenn Cooke](#42510316) noted team delays due to illness and requested help with the outline. - [@Anya Toms](#81516068) completed the outline and sent it to [@Jenn Cooke](#42510316) for QA. - QA was completed by [@Jenn Cooke](#42510316) and the outline was sent for SME review. | [7 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1x2u7 | PTP Accounts Payable: GR/IR Reconciliation | DEVELOPMENT |  |  | HIGH | Outline approved for development by Gina Garvey | 6 | 0 | 2025-06-28 | 2025-05-29 | 2025-01-17 11:34 | 2025-08-25 01:09 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt, ot vim | Development, ✍ Risk Register | [7 empty] | 986 hours |  | 0 |  |  | TRUE |  |  |  | Anya Toms | Ready for Development |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1x5gm | PTP Accounts Payable: Process Aged ERS Receipts | OUTLINES |  | Jessica Reed | HIGH | @Jenn Cooke I just received some edits from Gina Garvey on this. There are some discussions between her and Crystal Thompson about what should be included and what should be included. I can show you what I received. | 10 | 0 | 2025-07-07 | 2025-06-02 | 2025-01-17 11:37 | 2025-08-25 01:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a36pwk 868a36nzy | https://app.clickup.com/t/868a36pwk https://app.clickup.com/t/868a36nzy | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 2167 hours |  | 0 | 2025-06-02 |  | TRUE |  | 2025-07-16 |  | Jessica Reed | Beta Revision (ISG) |  |  |  | ITC3B | Accounts Payable | Invoice & Credit Processing | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Shannon Bagent, Jenn Cooke
868c1xftu | PTP Accounts Payable: Run Ad hoc Payments | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2025-01-17 11:45 | 2025-08-24 21:36 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a379ab 868a379ff 868a379t0 868a37a1b 868a37a8w | https://app.clickup.com/t/868a379ab https://app.clickup.com/t/868a379ff https://app.clickup.com/t/868a379t0 https://app.clickup.com/t/868a37a1b https://app.clickup.com/t/868a37a8w | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1xvfw | PTP Accounts Payable: Submit/Approve Expedited Payment Requests, Pt. 3 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2025-01-17 11:53 | 2025-08-24 21:55 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a372b2 868c1xwgf | https://app.clickup.com/t/868a372b2 https://app.clickup.com/t/868c1xwgf | wbt, ptp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1xxud | PTP Accounts Payable: Review Supplier Refunds, Pt. 1 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2025-01-17 11:56 | 2025-08-24 21:27 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37e01 868a37eer 868c1xztk | https://app.clickup.com/t/868a37e01 https://app.clickup.com/t/868a37eer https://app.clickup.com/t/868c1xztk | ptp, wbt | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1y08n | PTP Accounts Payable: Review Supplier Refunds, Pt. 2 | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2025-01-17 11:58 | 2025-08-24 21:29 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1y097 868c1y095 | https://app.clickup.com/t/868c1y097 https://app.clickup.com/t/868c1y095 | wbt, ptp | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | [9 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1y56t | PTP Accounts Payable: Process Certified Checks | OUTLINES |  | Brice LeBlanc | LOW |  | 0 | 0 | 2025-07-28 | 2025-07-10 | 2025-01-17 12:02 | 2025-08-11 15:20 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a37yfg 868a37y8g | https://app.clickup.com/t/868a37yfg https://app.clickup.com/t/868a37y8g | ptp, wbt | Development | [7 empty] | 634 hours |  | 0 | [6 empty] | Brice LeBlanc | Ready for OL Draft |  |  |  | ITC3 | Accounts Payable | Payment Processing | TRUE | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1y98y | PTP Accounts Payable: Perform Reconciliations, Pt. 1 | OUTLINES |  |  | LOW | @Jenn Cooke QA changes incorporated, this is ready for SME review | 4 | 0 | 2025-07-07 | 2025-06-23 | 2025-01-17 12:05 | 2025-08-06 11:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a38ner 868a38nt9 868c1yb2v | https://app.clickup.com/t/868a38ner https://app.clickup.com/t/868a38nt9 https://app.clickup.com/t/868c1yb2v | wbt, ptp | Development | [7 empty] | 1518 hours |  | 0 | 2025-06-23 | [5 empty] | Anya Toms | Alpha Review (SME) |  |  |  | ITC3 | Accounts Payable | Bank Integrations | TRUE | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1ybpr | PTP Accounts Payable: Perform Reconciliations, Pt. 2 | OUTLINES |  |  | LOW | QA complete, one minor revision needed. Please see track changes within the word document. @Anya Toms @Jenn Cooke | 3 | 0 | 2025-06-27 | 2025-06-23 | 2025-01-17 12:06 | 2025-08-06 11:16 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a38p59 868a38pgg | https://app.clickup.com/t/868a38p59 https://app.clickup.com/t/868a38pgg | wbt, ptp | Development | [7 empty] | 1518 hours |  | 0 | 2025-06-23 | [5 empty] | Anya Toms | In QA |  |  |  | ITC3 | Accounts Payable | Bank Integrations | TRUE | WBT |  | 2025-09-26 | Overdue |  |  | 2025-06-24 | Priscilla Holguin |  |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1ydpp | PTP Accounts Payable: Bank Integrations | OUTLINES |  |  | LOW | @Jenn Cooke this OL is ready for SME review, edits are made | 3 | 0 | 2025-07-07 | 2025-06-18 | 2025-01-17 12:08 | 2025-08-11 15:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2v6gf 868b6fpbe 868c1yexm 868c1yfd2 | https://app.clickup.com/t/868a2v6gf https://app.clickup.com/t/868b6fpbe https://app.clickup.com/t/868c1yexm https://app.clickup.com/t/868c1yfd2 | ptp, wbt | Development | [7 empty] | 1944 hours |  | 0 | 2025-06-18 | [5 empty] | Anya Toms | Alpha Review (SME) |  |  |  | ITC3 | Accounts Payable | Bank Integrations | TRUE | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1ykkw | PTP Accounts Payable: Setup of Supplier Financed POs - OL | DEVELOPMENT |  |  | URGENT | Course wrapper approved by Nathan Hodges, sending to Steve Foley next | 24 | 0 | 2025-07-10 | 2025-04-07 | 2025-01-17 12:14 | 2025-08-24 21:41 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a38r2h 868a38rf9 | https://app.clickup.com/t/868a38r2h https://app.clickup.com/t/868a38rf9 | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 311 hours |  | 0 |  |  | TRUE |  |  |  |  | Pending SIMs |  |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-05-09 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1yq6p | PTP Accounts Payable: Process Down Payments on Financed POs, Pt. 1 | DEVELOPMENT |  | Kris Thayer | URGENT | Outline approved by Nathan Hodges | 10 | 0 | 2025-06-01 | 2025-05-12 | 2025-01-17 12:16 | 2025-08-18 06:04 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a38uun 868a38v3r 868dwh8md 868dwh98k 868dwh9ek | https://app.clickup.com/t/868a38uun https://app.clickup.com/t/868a38v3r https://app.clickup.com/t/868dwh8md https://app.clickup.com/t/868dwh98k https://app.clickup.com/t/868dwh9ek | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 178 hours |  | 0 |  |  | TRUE |  |  |  | Kris Thayer | Ready for Development |  |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-08-29 | Overdue | [7 empty] | Nathan Hodges | 2025-05-09 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1yrjp | PTP Accounts Payable: Process Down Payments on Financed POs, Pt. 2 | OUTLINES |  |  | URGENT | Outline partially reviewed by Gina on 5.15.25, Alpha review not complete by end of meeting. We will implement the revisions we know about so far. | 6 | 0 | 2025-05-23 | 2025-05-13 | 2025-01-17 12:17 | 2025-08-19 09:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c1yx3e 868dwha7a 868dwhaca 868dwhb5f 868dwhbjh | https://app.clickup.com/t/868c1yx3e https://app.clickup.com/t/868dwha7a https://app.clickup.com/t/868dwhaca https://app.clickup.com/t/868dwhb5f https://app.clickup.com/t/868dwhbjh | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 2506 hours |  | 0 |  |  | TRUE | 2025-08-19 | 2025-08-18 |  |  | Beta Review (SME) |  |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-08-29 | Overdue | [7 empty] | Nathan Hodges | 2025-05-12 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1yy91 | PTP Accounts Payable: Processing Down Payments on Financed POs for Buyers - OL | OUTLINES |  |  | URGENT | @Emilie Martin , please email a copy of this to @Jessica Reed for QA | 5 | 0 | 2025-07-24 |  | 2025-01-17 12:22 | 2025-08-19 09:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a38xxh 868dwhhr6 | https://app.clickup.com/t/868a38xxh https://app.clickup.com/t/868dwhhr6 | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 2506 hours |  | 0 | 2025-06-23 |  | TRUE | 2025-08-19 | 2025-08-18 |  |  | Beta Review (SME) |  |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-05-12 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1z0a0 | PTP Accounts Payable: Process Cost-Reimbursable Exceptions for Buyers - OL | DEVELOPMENT |  | Brenda Mayfield | URGENT | @Jenn Cooke Course wrapper is ready for Final Review and Sign Off. @Brenda Mayfield inserted the SIM and QRG for Review Goods and Unliquidated Balance, and removed the launch slide for SIM/QRG that was descoped. | 19 | 0 | 2025-08-15 | 2025-05-23 | 2025-01-17 12:24 | 2025-08-25 01:16 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dwhr6z | https://app.clickup.com/t/868dwhr6z | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 966 hours |  | 0 | 2025-07-17 |  | TRUE | 2025-08-07 | 2025-08-06 |  |  | Final Review & Sign off (SME) | 2025-08-20 |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-05-12 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1z0xy | PTP Accounts Payable: Process Cost-Reimbursable Exceptions for Accounts Payable - OL | DEVELOPMENT |  | Priscilla Holguin | URGENT | @Jenn Cooke Edit to KC question 2 complete in SL. Ready for Final Review and Sign Off. | 19 | 0 | 2025-08-24 | 2025-05-15 | 2025-01-17 12:24 | 2025-08-25 11:53 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 1470 hours |  | 0 | 2025-07-21 |  | TRUE |  |  |  | Priscilla Holguin | Final Review & Sign off (SME) | 2025-08-25 |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-12 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1z18m | PTP Accounts Payable: Errors within the Financing Process - OL | DEVELOPMENT |  | Priscilla Holguin | URGENT | @Jenn Cooke Edit made to KC #4 in SL. | 15 | 0 | 2025-08-16 | 2025-05-28 | 2025-01-17 12:25 | 2025-08-25 01:09 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 1302 hours |  | 0 | 2025-07-17 |  | TRUE |  | 2025-08-14 |  |  | Final Review & Sign off (SME) |  |  |  | ITC3 | Accounts Payable | PO Contract Financing | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-12 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1zgrd | PTP A/P & Supply Chain: Initiate Procurement Request | OUTLINES |  |  | URGENT | QA complete - corrected a typo and sent to SME review | 4 | 0 | 2025-08-30 |  | 2025-01-17 12:35 | 2025-08-25 10:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a3c0q1 868c1zm0t | https://app.clickup.com/t/868a3c0q1 https://app.clickup.com/t/868c1zm0t | wbt, ptp, lean request | Development | [7 empty] | 657 hours |  | 0 | 2025-08-14 | [6 empty] | Alpha Review (SME) |  |  |  | ITC4 | Accounts Payable | P-Cards, Meeting Card, Fleet Card | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c1zq6a | PTP A/P & Supply Chain: Delegation of Authority - OL | OUTLINES |  | Kris Thayer | URGENT | Paused for process rewrites | 1 | 0 |  |  | 2025-01-17 12:41 | 2025-08-14 09:31 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dwbpqr 868dwbq4e 868dwbq93 | https://app.clickup.com/t/868dwbpqr https://app.clickup.com/t/868dwbq4e https://app.clickup.com/t/868dwbq93 | sap concur, ptp, ilt | Development | [7 empty] | 463 hours |  | 0 | [6 empty] | Kris Thayer | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | P-Cards, Meeting Card, Fleet Card | TRUE | ILT |  | 2025-09-05 | [9 empty] | 2025-08-14 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868c20ft9 | PTS Prod Ops: Generate Approval Workflows - OL | DEVELOPMENT |  | Alisha Khan | HIGH | Lynette not done with editing, additional meeting scheduled for 8/12 to continue going through content. | 9 | 0 | 2025-08-04 | 2025-07-22 | 2025-01-17 13:05 | 2025-08-25 14:56 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868b40td6 | https://app.clickup.com/t/868b40td6 | p2s, wbt | Development | [7 empty] | 269 hours |  | 0 | [6 empty] | Alisha Khan | Ready for Development |  |  |  | ITC4 | Prod Ops | Complete & Manage Material Master |  | WBT |  | 2025-09-12 | Overdue | [15 empty] | PTS | Shannon Bagent, Eugene Deloatch
868c22er9 | PTS Prod Ops: Perform Production Planning & Master Scheduling-OL | PAUSED |  |  | HIGH | LM Teams message from SME Taylor Mayhue 1.16.25: "That L3 is replaced with something else as of ITC3B and those are what we would want training on and I cannot confirm that training until ITC4 timing as we are going to learn a lot and have to update scripts for what you all need [sic]." | 1 | 0 |  |  | 2025-01-17 14:07 | 2025-08-25 00:30 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868b48ykk 868b48yxy 868b48zg0 868ebh5f9 | https://app.clickup.com/t/868b48ykk https://app.clickup.com/t/868b48yxy https://app.clickup.com/t/868b48zg0 https://app.clickup.com/t/868ebh5f9 | p2s, wbt | Development | [7 empty] | 2353 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3B | Prod Ops | Perform Production Planning & Master Scheduling | TRUE | WBT |  | 2025-09-19 | [9 empty] | 2025-06-13 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868c394z2 | A2R Asset Management: Print Property Tags | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 31 | 0 | 2025-04-24 | 2025-03-06 | 2025-01-20 13:08 | 2025-08-13 08:22 |  | 2025-04-15 13:22 | Kris Thayer | Lockheed Martin | Course Development | Development | 868c395md 868d47dyh 868d7g8pk | https://app.clickup.com/t/868c395md https://app.clickup.com/t/868d47dyh https://app.clickup.com/t/868d7g8pk | wbt, a2r, mfc | Development, ✍ Risk Register | [7 empty] | 3170 hours |  | 0 | 2025-03-26 |  | TRUE | 2025-04-15 | 2025-04-15 |  |  | Hand off to OCM Team | 2025-04-15 |  |  | ITC2 | Asset Management | Acquire Assets | TRUE | WBT |  | 2025-04-24 | Overdue | [8 empty] | 2025-04-08 | 2025-04-15 | [5 empty] | A2R | Trish Cortez, Steve Hile
868ca0z4d | PTS Prod Ops: Perform Customer Selloff - OL | DEVELOPMENT | 4/7 - JV began outlining for the course. 6/19 - There is a Wrapper started for this course. It is in the older format and not complete. Contact Jessica for it when developing. | David Rood | URGENT | @Eugene Deloatch and @Alisha Khan David Rood completed final edits, we still need to add Knowledge Checks and the Signavio flow to the process page, and probably the sim link, otherwise it's good to go to the SME. he put the .story file in the Sharepoint Drafts folder under Perform Customer Selloff > Drafts. | 38 | 0 | 2025-08-16 | 2025-08-12 | 2025-01-30 08:55 | 2025-08-25 14:48 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868ewpf3j 868chn5a9 | https://app.clickup.com/t/868ewpf3j https://app.clickup.com/t/868chn5a9 | ilt, ot xecm, p2s, mfc | Development | [7 empty] | 265 hours |  | 0 | 2025-08-12 | [5 empty] | David Rood | Ready for SME Review |  |  |  | ITC3 | Prod Ops | Perform Customer Selloff | TRUE | ILT |  | 2025-09-19 | Overdue | [8 empty] | 2025-06-18 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868cca0rn | PTP Supplier Quality: Purchase Requisition Change Module | OUTLINES |  |  | URGENT | Per Ed, this is no longer paused | 4 | 0 | 2025-08-11 | 2025-03-27 | 2025-02-03 13:23 | 2025-08-21 12:57 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868cca0t1 868e1a9ht 868c1rbdy | https://app.clickup.com/t/868cca0t1 https://app.clickup.com/t/868e1a9ht https://app.clickup.com/t/868c1rbdy | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 586 hours |  | 0 |  |  | TRUE |  |  |  | Anya Toms | Alpha Review (SME) |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-09-05 | Overdue | [7 empty] | Edward Newman | 2025-05-15 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868cca3rv | PTP Supplier Quality: Maintain WF User Assignment | COMPLETED |  |  | URGENT | Ian update and review 8/15 | 15 | 0 | 2025-08-17 | 2025-05-06 | 2025-02-03 13:25 | 2025-08-21 11:15 |  | 2025-08-14 07:20 | Jenn Cooke | Lockheed Martin | Course Development | Development | 868cca3tb | https://app.clickup.com/t/868cca3tb | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 272 hours |  | 0 | 2025-07-21 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-08 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868cca5mt | PTP Supplier Quality: Workflow Settings - OL | DEVELOPMENT |  | Jessica Reed | URGENT | Outline approved by Ed 6.26.25 | 6 | 0 | 2025-05-30 | 2025-05-08 | 2025-02-03 13:27 | 2025-08-24 23:42 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868cca5n8 | https://app.clickup.com/t/868cca5n8 | wbt, ptp | Development, ✍ Risk Register | [7 empty] | 1443 hours |  | 0 |  |  | TRUE |  |  |  | Jessica Reed | Ready for Development |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-09-05 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868cca7d1 | PTP Supplier Quality: Current Approvals Report | DEVELOPMENT |  |  | URGENT | Outline approved by Ed 6.26.25 | 5 | 0 | 2025-06-09 | 2025-05-30 | 2025-02-03 13:29 | 2025-08-14 07:23 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868cca7db | https://app.clickup.com/t/868cca7db | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1443 hours |  | 0 |  |  | TRUE |  |  |  | Anya Toms | Ready for Development |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868cca9yb | PTP Supplier Quality: Quality Record Queue Report (Run the ZMMQR Report) -QRG | COMPLETED |  |  | URGENT | Approved by Teresa Scanlan | 12 | 0 | 2025-07-25 | 2025-06-06 | 2025-02-03 13:32 | 2025-08-21 11:15 |  | 2025-08-04 09:21 | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, qrg | Development | [7 empty] | 510 hours |  | 0 | [7 empty] | Development Complete |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | QRG |  | 2025-08-08 | Overdue | [8 empty] | 2025-05-29 | 2025-08-04 | 2025-07-10 |  |  |  |  | PTP | Jenn Cooke, Shannon Bagent
868ccafpp | PTP Supplier Quality: Inspection Relevance Determination Program | PAUSED |  |  | NORMAL | Update: this belongs to FUT 271, which we have not yet received. Putting this under Paused. | 2 | 0 |  |  | 2025-02-03 13:39 | 2025-08-15 13:55 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 674 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3 | Supplier Quality | No L3 Custom Content |  | WBT |  | 2025-09-12 | [8 empty] | Edward Newman | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868ccajuu | PTP Supplier Quality: ASN Controls & Quality Notification (QNote) - OL | DEVELOPMENT |  | Jessica Reed | URGENT | Outline Approved by SMEs 7.3.25 | 7 | 0 | 2025-06-28 | 2025-05-09 | 2025-02-03 13:43 | 2025-08-24 23:24 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868ccajuy | https://app.clickup.com/t/868ccajuy | ptp, wbt | Development, ✍ Risk Register | [7 empty] | 1274 hours |  | 0 |  |  | TRUE |  |  |  | Jessica Reed | Ready for Development |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868cjxf2u | PTS Prod Ops: Order Creation & Release-OL | DEVELOPMENT |  | Alisha Khan | URGENT | Starting SL dev 8/22 | 13 | 0 | 2025-08-26 | 2025-06-27 | 2025-02-12 08:36 | 2025-08-25 07:23 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2uwd5 | https://app.clickup.com/t/868a2uwd5 | p2s, wbt | Development | [7 empty] | 122 hours |  | 0 | 2025-08-22 | [5 empty] | Alisha Khan | Alpha Draft (ISG) |  |  |  | ITC4 | Prod Ops | Order Creation & Release | TRUE | WBT |  | 2025-09-12 | Due | [8 empty] | 2025-06-11 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868cktqar | A2R Asset Accounting: Commissioning Assets | COMPLETED | all requested updates complete. |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 17 | 0 | 2025-03-10 | 2025-02-13 | 2025-02-13 12:44 | 2025-08-13 08:20 |  | 2025-03-20 12:57 | Trish Cortez | Lockheed Martin | Course Development | Development | 868a2var3 868a2va26 868a2v7kb 868a2v7xm 868a2v665 | https://app.clickup.com/t/868a2var3 https://app.clickup.com/t/868a2va26 https://app.clickup.com/t/868a2v7kb https://app.clickup.com/t/868a2v7xm https://app.clickup.com/t/868a2v665 | a2r, wbt, mfc | Development | [7 empty] | 3795 hours |  | 0 | 2025-03-05 | 2025-03-17 | [5 empty] | Hand off to OCM Team | 2025-03-20 |  |  | ITC2 | Asset Accounting | Commissioning Assets |  | WBT |  | 2025-03-10 | Overdue | [8 empty] | 2025-04-10 | 2025-03-20 | [5 empty] | A2R | Trish Cortez, Steve Hile
868ckw8e1 | PTS Prod Ops: Managing Exception Messages - OL | COMPLETED |  |  | NORMAL | Ian reviewed an updated 8/15 | 13 | 0 | 2025-05-23 | 2025-03-17 | 2025-02-13 14:17 | 2025-08-15 10:46 |  | 2025-07-08 11:43 | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c20pm5 868a2uwpb 868c20r8e 868c20rve | https://app.clickup.com/t/868c20pm5 https://app.clickup.com/t/868a2uwpb https://app.clickup.com/t/868c20r8e https://app.clickup.com/t/868c20rve | wbt, p2s | Development, ✍ Risk Register | [7 empty] | 1156 hours |  | 0 |  |  |  |  | 2025-05-20 |  |  | Hand off to OCM Team |  |  |  | ITC2 | Prod Ops | Exception Management |  | WBT |  | 2025-05-23 | Overdue | [9 empty] | 2025-07-08 | [5 empty] | PTS | Shannon Bagent, Eugene Deloatch
868d4cvm3 | R2R Tax Accounting: SAP: Indirect Tax Determination Engine | OUTLINES | 7/31 as of today, pivoting away from some of the calculation on AR side with VAT determination. Based on that conversation, may have to table some of this because working toward manual process. Need input from Ankine about how far they're pushing this--into another release or keeping in this one. So far Ankine confirmed this is staying here; could change. 8/7 Katie and Ankine decided they will likely combine this with the Americas courses to create one Determination Engine course. They decided they need to see how development goes, though, so this will be a work in progress. We will likely be descoping the tasks within and transitioning this to more of a custom course, although the lift is easier: they are wanting a lot of screenshots, not newly created conceptual material. Katie designed an outline she and Ankine are refining. Next week we will go through the process in Vertex with Katie and this will guide us further. 8/14 in demo of Vertex by Katie with Ankine and Ron present: 3 courses needed for R1, and not organized on the criterion of Americas/RoW as the L3s are organized (NOTE that this means the L3 identified as associated to the course is loose--we're not following L3 organization strictly speaking, but we're still in ITC4 because the Determination Engine L3 is). Instead organized by tool: SAP, Vertex O Series, Vertex Accelerator. Directive is to include components in all 3 courses of both Americas/Row. We will need to mark which items are international. These courses used to have roughly 15 individual step-based deliverables; Ankine and Katie agree that is too low-level and the course should be custom and higher level. In the future we may add simulations to show step-based tasks, and if we do that we will mark them individually as Americas or RoW. For R1, just ILTs with no step-based individual tasks. As we go through the outline with Katie we will add lessons; they are not finalized right now. Note that the courses will need to be delivered twice: to two different audiences (Americas, RoW), for a total of 6 deliveries (3 courses x 2 audiences). Note on Outline status: It's in this status because an outline has been started, but it's Katie's and Ankine's. Dan will enter a start date when he picks up their outline and starts to adapt it into deliverable format. | Daniel Die | NORMAL |  | 0 | 0 |  |  | 2025-03-18 15:21 | 2025-08-25 01:01 |  |  | Sarah Griffis | Lockheed Martin | Course Development | Development |  |  | r2r, row, ilt, americas | Development | [7 empty] | 269 hours |  | 0 | 2025-08-14 | [5 empty] | Daniel Die | Alpha Draft (ISG) |  |  |  | ITC4 | Tax Accounting | Consolidations & Tax (Indirect Tax Determination Engine) |  | ILT |  | 2025-09-12 | On-time | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868ddgthj | A2R CLRP Capital: Distribute Targets | DEVELOPMENT |  | Kris Thayer | HIGH | @Brice LeBlanc thanks! @Steve Hile this is ready for SME Review when the simulation is ready. | 14 | 0 | 2025-08-29 | 2025-06-23 | 2025-04-07 08:52 | 2025-08-24 22:22 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868dguu2g | https://app.clickup.com/t/868dguu2g | a2r, wbt, mfc | Development | [7 empty] | 1447 hours |  | 0 | 2025-06-26 | [5 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-09-19 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddh3a9 | A2R CLRP Overhead: Prioritize Plan Items Inputs | DEVELOPMENT |  | Kris Thayer | URGENT | VS QA complete. Ready for SME final approval. @Kris Thayer | 16 | 0 | 2025-08-29 | 2025-06-18 | 2025-04-07 09:01 | 2025-08-24 23:58 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddupk1 868dduppp 868ddupvn 868dduq0t 868dduq4n 868dduq9k | https://app.clickup.com/t/868ddupk1 https://app.clickup.com/t/868dduppp https://app.clickup.com/t/868ddupvn https://app.clickup.com/t/868dduq0t https://app.clickup.com/t/868dduq4n https://app.clickup.com/t/868dduq9k | wbt, a2r, mfc | Development | [7 empty] | 1107 hours |  | 0 | 2025-07-28 |  |  | 2025-08-12 |  |  |  | Final Review & Sign off (SME) | 2025-08-22 |  |  | ITC3B | CLRP | Develop CLRP (Prioritize Plan Item Inputs L4) |  | WBT |  | 2025-09-26 | Due | [8 empty] | 2025-04-18 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddhb41 | A2R CLRP Capital: Monthly Capital Plan Item Financial and Asset Review | DEVELOPMENT |  | Kris Thayer | URGENT | Thanks @Brice LeBlanc ! Updates from QA completed. @Steve Hile this course is ready for SME Review (final change impacts slide added). | 17 | 0 | 2025-09-05 | 2025-06-16 | 2025-04-07 09:09 | 2025-08-25 05:41 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddu9a8 868ddu9eb 868ddu9pp | https://app.clickup.com/t/868ddu9a8 https://app.clickup.com/t/868ddu9eb https://app.clickup.com/t/868ddu9pp | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [7 empty] | Final Review & Sign off (SME) |  |  |  | ITC3B | CLRP | Execute CLRP (Manage Project Performance L4) |  | WBT |  | 2025-09-19 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddhk2p | A2R CLRP Capital: Project Approval Request Submission | DEVELOPMENT |  | Kris Thayer | URGENT | @Steve Hile , this course is ready for SME Review. The new change impacts slide is added. | 17 | 0 | 2025-10-03 | 2025-06-17 | 2025-04-07 09:18 | 2025-08-24 23:10 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868dduu32 868dduu45 868dduu6g 868dduu72 | https://app.clickup.com/t/868dduu32 https://app.clickup.com/t/868dduu45 https://app.clickup.com/t/868dduu6g https://app.clickup.com/t/868dduu72 | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [6 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddhuc3 | A2R CLRP Overhead: Project Approval Request Submission (Non-Stat Emergent) | DEVELOPMENT |  | Bailey Petty | URGENT | @Steve Hile This is the current status of this course....The thread in the sim task underneath this course was accidental. | 12 | 0 |  | 2025-06-13 | 2025-04-07 09:25 | 2025-08-25 00:13 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868dduvx9 868dduw39 868dduwa5 | https://app.clickup.com/t/868dduvx9 https://app.clickup.com/t/868dduw39 https://app.clickup.com/t/868dduwa5 | a2r, wbt, mfc | Development | [7 empty] | 674 hours |  | 0 | [6 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-26 | Overdue | - [@Brice LeBlanc](#75334455) completed the draft for this item. - [@Veronica Massey](#57129402) performed internal QA and confirmed it is ready for VS Lead QA. - The item is now marked as 'In QA' and is available in the designated folder for review. - [@Steve Hile](#81539658) has been notified that the item is ready for VS Lead QA. | [7 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddhurb | A2R CLRP Overhead: Project Approval Request Submission (Stat) | DEVELOPMENT |  | Bailey Petty | URGENT | QA Complete @Steve Hile | 14 | 0 |  | 2025-06-02 | 2025-04-07 09:25 | 2025-08-25 00:17 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddux7c | https://app.clickup.com/t/868ddux7c | a2r, wbt, mfc | Development | [7 empty] | 1014 hours |  | 0 | [6 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-19 | Overdue | - Course outline was sent for QA and reviewed by [@Alisha Khan](#81582372). - QA was completed and the document was sent to [@Veronica Massey](#57129402). - [@Veronica Massey](#57129402) implemented edits and confirmed readiness for VS Lead QA. - [@Alisha Khan](#81582372) was unassigned after QA completion. | [7 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddhxa4 | A2R CLRP Overhead: Approval Workflow | DEVELOPMENT |  | Kris Thayer | URGENT | Thanks @Brice LeBlanc !! @Steve Hile , this course is ready for SME Review. | 14 | 0 |  | 2025-06-17 | 2025-04-07 09:28 | 2025-08-24 23:33 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddneu0 868ddng1r 868ddngem | https://app.clickup.com/t/868ddneu0 https://app.clickup.com/t/868ddng1r https://app.clickup.com/t/868ddngem | a2r, wbt, mfc | Development | [7 empty] | 73 hours |  | 0 | [6 empty] | Kris Thayer | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-26 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddj1td | A2R CLRP Capital: Post Approval Request Automations | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready for upload to the LMS. | 23 | 0 | 2025-07-04 | 2025-06-19 | 2025-04-07 09:32 | 2025-08-13 08:24 |  | 2025-08-04 12:25 | Kris Thayer | Lockheed Martin | Course Development | Development | 868dduh7h 868dduhb8 868dduhd7 | https://app.clickup.com/t/868dduh7h https://app.clickup.com/t/868dduhb8 https://app.clickup.com/t/868dduhd7 | a2r, wbt | Development | [7 empty] | 507 hours |  | 0 | 2025-06-30 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-07-03 | Overdue | [8 empty] | 2025-04-29 | 2025-08-04 | [5 empty] | A2R | Trish Cortez, Steve Hile
868ddj3nt | A2R CLRP Capital: Managing Project Performance | OUTLINES |  |  | URGENT | @Veronica Massey VS QA complete and file copied to SME review folder for approval. TY | 6 | 0 | 2025-09-26 | 2025-06-19 | 2025-04-07 09:35 | 2025-08-24 22:38 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddud71 868ddud9x 868ddudfn 868ddudm5 868ddudpe 868ddudra 868ddudtm | https://app.clickup.com/t/868ddud71 https://app.clickup.com/t/868ddud9x https://app.clickup.com/t/868ddudfn https://app.clickup.com/t/868ddudm5 https://app.clickup.com/t/868ddudpe https://app.clickup.com/t/868ddudra https://app.clickup.com/t/868ddudtm | a2r, wbt, mfc | Development | [7 empty] | 1610 hours |  | 0 | 2025-06-19 | [6 empty] | Beta Revision (ISG) |  |  |  | ITC3B | CLRP | Execute CLRP (Manage Project Performance L4) |  | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddj4ay | A2R CLRP Overhead: Manage Project Performance | DEVELOPMENT |  | Kris Thayer | URGENT | @Shannon Bagent thanks! @Steve Hile , this is ready for VS Lead QA. | 11 | 0 | 2025-08-31 | 2025-06-12 | 2025-04-07 09:36 | 2025-08-24 23:48 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddueem 868dduepf | https://app.clickup.com/t/868ddueem https://app.clickup.com/t/868dduepf | a2r, wbt | Development | [7 empty] | 98 hours |  | 0 | [6 empty] | Kris Thayer | Alpha Review (SME) |  |  |  | ITC3B | CLRP | Execute CLRP (Manage Project Performance L4) |  | WBT |  | 2025-09-26 | Due | - Start date was set by [@Veronica Massey](#57129402) on 06/12/2025. - No additional updates or progress have been made yet. | [7 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddjhtw | A2R CLRP Capital: Reset Decision Points | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready for LMS upload. Final SL file and URL are located in the LM Teams > Deliverables > WBT subfolders. | 14 | 0 | 2025-07-07 | 2025-06-19 | 2025-04-07 09:49 | 2025-08-13 08:24 |  | 2025-08-04 12:26 | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddv1ma | https://app.clickup.com/t/868ddv1ma | a2r, wbt | Development | [7 empty] | 507 hours |  | 0 | 2025-07-01 | [6 empty] | Hand off to OCM Team |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-07-07 | Overdue | [8 empty] | 2025-04-29 | 2025-08-04 | [5 empty] | A2R | Trish Cortez, Steve Hile
868ddm192 | A2R CLRP Overhead: Create Plan Item and Enter Financial and Labor Plan | DEVELOPMENT |  | Veronica Massey | URGENT | QA complete @Steve Hile | 11 | 0 | 2025-09-05 | 2025-06-16 | 2025-04-07 10:44 | 2025-08-24 23:40 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddpkh0 868ddpk9r 868ddpjw4 | https://app.clickup.com/t/868ddpkh0 https://app.clickup.com/t/868ddpk9r https://app.clickup.com/t/868ddpjw4 | a2r, wbt, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Pending SIMs |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-09-26 | Due | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddm5wf | A2R CLRP Capital: Capital Upload Plan Items in Bulk | PREDEVELOPMENT |  | Veronica Massey | LOW | Per SMEs F2F meeting 7/21. Keep this course. It is normal priority so dev can happen after all high-priority tasks are completed. | 3 | 0 |  |  | 2025-04-07 10:48 | 2025-08-24 22:17 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddv64p 868ddv663 | https://app.clickup.com/t/868ddv64p https://app.clickup.com/t/868ddv663 | a2r, wbt | Development | [7 empty] | 1828 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-09-26 | On-time | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ddm6f3 | A2R CLRP Overhead: Overhead Upload Plan Items in Bulk | PREDEVELOPMENT |  |  | LOW | @Steve Hile this shows as possible to descope? In the OH data staging spreadsheet the two tasks for this show as content only. Can we ask overhead if this needs to be completely descoped or if the tasks should be combined/moved into a different course. I am having @Kris Thayer hold off on developing this outline until we get an answer. | 1 | 0 |  |  | 2025-04-07 10:49 | 2025-08-24 23:57 |  |  | Kris Thayer | Lockheed Martin | Course Development | Development | 868ddv6hq 868ddv6kb | https://app.clickup.com/t/868ddv6hq https://app.clickup.com/t/868ddv6kb | a2r, wbt | Development | [7 empty] | 1828 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC3B | CLRP | Develop CLRP |  | WBT |  | 2025-09-26 | On-time | [8 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868de3f75 | SUS Obsolescence Management: Validating DMS Alerts | COMPLETED |  |  | NORMAL |  | 0 | 0 | 2025-07-01 | 2025-07-01 | 2025-04-08 05:40 | 2025-08-25 07:54 |  | 2025-08-12 16:03 | Brice LeBlanc | Lockheed Martin | Course Development | Development |  |  | qrg, sus | Development | [7 empty] | 312 hours |  | 0 | [7 empty] | Sign off Received |  |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | QRG |  | 2025-08-12 | On-time |  |  |  | Brenda Mayfield | [5 empty] | 2025-08-12 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868decc09 | A2R Asset Management: Asset Transfers | COMPLETED |  |  | URGENT | @Trish Cortez the final What's Changing in 1LMX slide is added and required triggers and settings per Mike were applied. Republished to R360 with Restricted menu and tested. | 24 | 0 | 2025-06-06 | 2025-04-18 | 2025-04-08 11:05 | 2025-08-13 08:22 |  | 2025-05-27 10:09 | Steve Hile | Lockheed Martin | Course Development | Development | 868decfxe 868decgh2 | https://app.clickup.com/t/868decfxe https://app.clickup.com/t/868decgh2 | a2r, wbt, mfc | Development | [7 empty] | 2165 hours |  | 0 | 2025-05-23 |  |  |  | 2025-05-27 |  |  | Hand off to OCM Team |  |  |  | ITC3B | Asset Management | Disposition Asset | TRUE | WBT |  | 2025-06-06 | Overdue | [8 empty] | 2025-04-08 | 2025-05-27 | [5 empty] | A2R | Trish Cortez, Steve Hile
868dfz666 | A2R Controlled Tooling: Hard/Durable Tooling: Maintenance Part B | COMPLETED | / |  | URGENT | @Trish Cortez this course is ready to upload to the LMS. Final SL file and URL are located in Teams Deliverables > WBT subfolders. | 19 | 0 | 2025-06-10 | 2025-04-24 | 2025-04-11 09:12 | 2025-08-13 08:23 |  | 2025-08-07 12:38 | Steve Hile | Lockheed Martin | Course Development | Development | 868dfz66d 868dfz66w | https://app.clickup.com/t/868dfz66d https://app.clickup.com/t/868dfz66w | a2r, mfc, wbt | Development | [7 empty] | 435 hours |  | 0 | 2025-05-28 |  |  |  | 2025-06-04 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Hard/Durable Tooling or Functional Test Equipment L4) |  | WBT |  | 2025-06-10 | Overdue | [8 empty] | 2025-04-10 | [6 empty] | A2R | Trish Cortez, Steve Hile
868dfzm17 | A2R Controlled Tooling: Perishable Tooling | COMPLETED |  |  | URGENT | @Trish Cortez , this course is ready to upload to the LMS. The final SL file and URL are in the Teams Deliverables > WBT subfolders. | 23 | 0 | 2025-06-13 | 2025-04-23 | 2025-04-11 09:29 | 2025-08-13 08:23 |  | 2025-08-07 12:38 | Steve Hile | Lockheed Martin | Course Development | Development | 868a2v7rr | https://app.clickup.com/t/868a2v7rr | a2r, wbt, mfc | Development | [7 empty] | 435 hours |  | 0 | 2025-05-26 |  |  |  | 2025-06-04 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Controlled Tooling | Controlled Tooling (Perishable Tooling L4) |  | WBT |  | 2025-06-13 | Overdue | [8 empty] | 2025-04-21 | [6 empty] | A2R | Trish Cortez, Steve Hile
868dh617q | O2C Sales Orders: Create Sales Order | DEVELOPMENT |  | Ashley Parker | HIGH | @Angie Paxton CW complete and updates made | 4 | 0 | 2025-08-04 | 2025-05-09 | 2025-04-14 14:32 | 2025-08-24 23:38 |  |  | Renee Barnes | Lockheed Martin | Course Development | Development | 868dj7c2q | https://app.clickup.com/t/868dj7c2q | mfc, o2c, ilt | Development | [7 empty] | 606 hours |  | 0 | [5 empty] | High |  | Final Review & Sign off (SME) | 2025-08-21 |  |  | ITC3 | Sales Orders | Capture, Process, and Track End Item Deliverable Sales Orders Capture, Process and Track Sustainment Spares |  | ILT |  | 2025-09-12 | Overdue | - ILT outline alpha draft was completed and reviewed with [@Angie Paxton](#81508310). - Initial QA by [@Angie Paxton](#81508310) is done; SME agreed to update Sales Order courses in the master curriculum. - Content outline was sent to [@Angie Paxton](#81508310) on 6/12/25. | [14 empty] | O2C | Angie Paxton
868dh6a78 | O2C Sales Orders: Validate Sales Order | DEVELOPMENT |  | Ashley Parker | HIGH | @Angie Paxton sent cw | 2 | 0 | 2025-08-24 | 2025-06-11 | 2025-04-14 14:44 | 2025-08-25 08:29 |  |  | Renee Barnes | Lockheed Martin | Course Development | Development | 868dh6d1h | https://app.clickup.com/t/868dh6d1h | ilt, o2c | Development | [7 empty] | 412 hours |  | 0 | 2025-08-14 | 2025-08-14 |  |  |  | High | Ashley Parker | Pending SIMs |  |  |  | ITC3 | Sales Orders | Capture, Process, and Track End Item Deliverable Sales Orders Capture, Process and Track Sustainment Spares |  | ILT |  | 2025-09-12 | Overdue | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868dh6g2m | O2C Sales Orders: Update Sales Order | PREDEVELOPMENT |  | Ashley Parker | HIGH | Bringing simulations out of paused status per Isaiah Calanche | 2 | 0 |  |  | 2025-04-14 14:50 | 2025-08-24 23:43 |  |  | Renee Barnes | Lockheed Martin | Course Development | Development | 868dh6mm2 868dh6mmb 868dh6mp5 868dh6mpa 868dh6mpk 868dh6mpy 868dh6mqd | https://app.clickup.com/t/868dh6mm2 https://app.clickup.com/t/868dh6mmb https://app.clickup.com/t/868dh6mp5 https://app.clickup.com/t/868dh6mpa https://app.clickup.com/t/868dh6mpk https://app.clickup.com/t/868dh6mpy https://app.clickup.com/t/868dh6mqd | ilt, o2c | Development | [7 empty] | 627 hours |  | 0 | 2025-07-02 |  |  |  |  | High | Ashley Parker | Ready for OL Draft |  |  |  | ITC3 | Sales Orders | Capture, Process, and Track End Item Deliverable Sales Orders Capture, Process and Track Sustainment Spares |  | ILT |  | 2025-09-19 | Overdue | [15 empty] | O2C | Angie Paxton
868dpxftj | PTP SCM Requisition to Procure: Lean Request Approval - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-04-28 07:19 | 2025-08-24 22:39 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868c04phn 868dpxfu7 868dpxfu6 868dpxfu2 868dpxfu3 868dpxktr | https://app.clickup.com/t/868c04phn https://app.clickup.com/t/868dpxfu7 https://app.clickup.com/t/868dpxfu6 https://app.clickup.com/t/868dpxfu2 https://app.clickup.com/t/868dpxfu3 https://app.clickup.com/t/868dpxktr | lean request, ptp, wbt | Development | [7 empty] | 463 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Purchase Requisition Mgmt (MRP/Non-MRP) & Approval |  | WBT |  | 2025-09-05 | [5 empty] | TRUE |  |  |  | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868dpzyte | PTP SCM Requisition to Procure: Schedule Management - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-04-28 08:47 | 2025-08-25 10:52 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dpzyw6 868dpzywc | https://app.clickup.com/t/868dpzyw6 https://app.clickup.com/t/868dpzywc | wbt, ptp | Development | [7 empty] | 442 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Supplier PO Communication, Acknowledgement, & Schedule Mgmt. |  | WBT |  | 2025-09-26 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq07hc | PTP SCM Requisition to Procure: Government/Customer Furnished Property - OL | DEVELOPMENT |  |  | NORMAL | @Jessica Visser Matt has completed his review of this L3 | 10 | 0 | 2025-07-18 | 2025-07-02 | 2025-04-28 08:56 | 2025-08-18 08:23 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 175 hours |  | 0 | [7 empty] | Beta Revision (ISG) |  |  |  | ITC3 | Supply Chain | Non-Consumable Property: Drop Shipping, BFM, GFE, CFE | TRUE | WBT |  | 2025-09-12 | Overdue | [7 empty] | Matt Berinato | 2025-05-23 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq4jmp | PTP SCM PTP Foundational: Creating & Maintaining Text Keys & Clauses - OL | PREDEVELOPMENT |  |  | LOW | Per Matt today, this is now a Low-priority course | 2 | 0 |  |  | 2025-04-28 11:26 | 2025-08-24 22:12 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dq4jnf 868dq4jnh 868dq4jne | https://app.clickup.com/t/868dq4jnf https://app.clickup.com/t/868dq4jnh https://app.clickup.com/t/868dq4jne | wbt, ptp | Development | [7 empty] | 2860 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC4 | Supply Chain | PTP Strategy, Policies, & Operating Models |  | WBT |  | 2025-09-26 | [16 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq5038 | PTP SCM Process Agreements: Long Term Agreements (Outline Agreements) - OL | OUTLINES |  |  | HIGH | L3/Course added by Matt Berinato 4.24.25 | 1 | 0 |  |  | 2025-04-28 11:42 | 2025-08-25 11:28 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dq503k 868dq503n 868dq503m 868dq51je | https://app.clickup.com/t/868dq503k https://app.clickup.com/t/868dq503n https://app.clickup.com/t/868dq503m https://app.clickup.com/t/868dq51je | wbt, ptp | Development | [7 empty] | 4 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC4 | Supply Chain | Contract Initiation & Setup |  | WBT |  | 2025-09-05 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq51yw | PTP SCM: Returning Hardware to Suppliers - OL | OUTLINES |  |  | HIGH | L3/Course added by Matt Berinato 4.24.25 | 1 | 0 |  |  | 2025-04-28 11:45 | 2025-08-25 11:29 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dq51z8 868dq51z9 868dq51z6 | https://app.clickup.com/t/868dq51z8 https://app.clickup.com/t/868dq51z9 https://app.clickup.com/t/868dq51z6 | wbt, ptp | Development | [7 empty] | 4 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | ITC4 | Supply Chain | Return & Repair Purchase Order Processing |  | WBT |  | 2025-09-26 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq85zj | PTP SCM Requisition to Procure: Purchase Order Approval Delegation of Authority (Workflow Approvals) - OL | OUTLINES |  |  | URGENT | @Jessica Reed Matt approved changing this course to ILT as requested by Hala | 1 | 0 |  |  | 2025-04-28 13:38 | 2025-08-25 10:52 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dq85zv 868dq85zp | https://app.clickup.com/t/868dq85zv https://app.clickup.com/t/868dq85zp | ptp, ilt | Development | [7 empty] | 441 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | Purchase Requisition Mgmt (MRP/Non-MRP) & Approval |  | ILT |  | 2025-09-12 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868dq87bb | PTP SCM PTP Foundational: Creating an Acquisition Compliance Folder (ACF) - OL | OUTLINES |  |  | URGENT | Per Matt today, this is a complex topic and can change to ILT as requested by Hala | 1 | 0 |  |  | 2025-04-28 13:41 | 2025-08-24 22:13 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868dq87bx | https://app.clickup.com/t/868dq87bx | ptp, ilt | Development | [7 empty] | 463 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC4 | Supply Chain | PO Folder Documentation |  | ILT |  | 2025-09-05 | [5 empty] | TRUE | [10 empty] | PTP | Jenn Cooke, Shannon Bagent
868drcrh0 | O2C Billing: Work with Manual Invoices | DEVELOPMENT |  |  | HIGH | FG & CW approved by Hayden 7/19 | 7 | 0 | 2025-07-30 | 2025-06-04 | 2025-04-30 09:00 | 2025-08-24 23:33 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868drcy5m | https://app.clickup.com/t/868drcy5m | ilt, o2c | Development | [7 empty] | 311 hours |  | 0 | [7 empty] | Pending SIMs |  |  |  | ITC3 | Billing | Issue Output Manage Billing Documents |  | ILT |  | 2025-09-19 | Overdue | - [@Angie Paxton](#81508310) requested the content outline be sent on 6/9/25. - Task was reassigned from [@Kristin Grappone](#81485796) to [@Ashley Parker](#42484518) on 6/12/25. - Developer field was cleared by [@Angie Paxton](#81508310) on 6/12/25. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868dud951 | SUS Obsolescence Management Introduction to CDATS | COMPLETED |  |  | HIGH | Tech review revisions for LMS readiness are complete. Course link to Review 360 & .story file are saved to Teams folder(s) on the LM side. This course is ready for hand off @Trish Cortez @Brice LeBlanc | 7 | 0 | 2025-07-04 | 2025-05-05 | 2025-05-05 12:06 | 2025-08-14 13:53 |  | 2025-07-15 09:24 | Brice LeBlanc | Lockheed Martin | Course Development | Development |  |  | cdats, sus, wbt | Development | [7 empty] | 990 hours |  | 0 | [7 empty] | Hand off to OCM Team | 2025-07-03 |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | WBT |  | 2025-07-04 | Overdue | [15 empty] | SUS | Brice LeBlanc
868dy5a5y | O2C Billing: Costing Sheets and Burdening | PAUSED |  |  | HIGH | Tasks in Paused status because we are awaiting passed test scripts. Moving forward with course outline and wrapper development. | 1 | 0 |  |  | 2025-05-13 10:34 | 2025-08-24 22:49 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868dy5ddz | https://app.clickup.com/t/868dy5ddz | wbt, o2c | Development | [7 empty] | 1973 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3B | Billing | No L3 Custom Content |  | WBT |  | 2025-09-19 | Overdue | - [@Angie Paxton](#81508310) assigned the task to [@Ashley Parker](#42484518) on 06/12/2025. - No other recent updates or progress reported. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868dy5ekr | O2C Billing: Previously Billed Process | PAUSED |  |  | HIGH | Tasks in Paused status because we are awaiting passed test scripts. Moving forward with course outline and wrapper development. | 1 | 0 |  |  | 2025-05-13 10:42 | 2025-08-24 23:28 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868dy5h9h | https://app.clickup.com/t/868dy5h9h | wbt, o2c | Development | [7 empty] | 1973 hours |  | 0 | [7 empty] | Paused |  |  |  | ITC3B | Billing | No L3 Custom Content |  | WBT |  | 2025-09-19 | Overdue | - [@Angie Paxton](#81508310) assigned the task to [@Ashley Parker](#42484518) on 06/12. - No other updates or progress have been reported since the reassignment. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868dy5jw9 | O2C Billing: Planned Version Upload | DEVELOPMENT |  | Kaye Perrota, Ashley Parker | HIGH | Sent over first rough draft of WBT to @Angie Paxton and @Ashley Parker | 4 | 0 | 2025-09-01 | 2025-06-18 | 2025-05-13 10:46 | 2025-08-25 08:29 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868dy5p18 | https://app.clickup.com/t/868dy5p18 | o2c, wbt | Development | [7 empty] | 1616 hours |  | 0 | 2025-08-07 |  |  |  | 2025-08-25 |  |  | Beta Revision (ISG) |  |  |  | ITC3B | Billing | No L3 Custom Content |  | WBT |  | 2025-09-19 | Overdue | - Outline draft was posted to the LM OCM VS folder and shared with [@Angie Paxton](#81508310) for review via email. - [@Ashley Parker](#42484518) is now assigned to the task; [@Kristin Grappone](#81485796) was unassigned. - Task status updated to 'Due'. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868dy5qb5 | O2C Billing: Legacy Rate Year Interface | DEVELOPMENT |  | Kaye Perrota, Ashley Parker | HIGH | Made corrections and sent it back to @Ashley Parker and @Angie Paxton | 5 | 0 | 2025-09-01 | 2025-06-18 | 2025-05-13 10:52 | 2025-08-25 08:29 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868dy5uum | https://app.clickup.com/t/868dy5uum | o2c, wbt | Development | [7 empty] | 1616 hours |  | 0 | 2025-08-07 |  |  |  | 2025-08-25 |  |  | Beta Revision (ISG) |  |  |  | ITC3B | Billing | No L3 Custom Content |  | WBT |  | 2025-09-19 | Overdue | - Outline draft was posted to the LM OCM VS folder and shared with [@Angie Paxton](#81508310) for review via email. - Task was reassigned from [@Kristin Grappone](#81485796) to [@Ashley Parker](#42484518). - Overdue status was updated to 'Due' on June 13. | [14 empty] | O2C | Angie Paxton, Shannon Bagent
868dzp4bq | PTP Supplier Quality: Run the ZPOR Report - QRG | COMPLETED |  |  | URGENT | Approved as a standalone QRG by Teresa Scanlan | 12 | 0 | 2025-08-10 | 2025-05-23 | 2025-05-16 05:50 | 2025-08-21 11:15 |  | 2025-08-05 06:15 | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, qrg | Development, ✍ Risk Register | [7 empty] | 489 hours |  | 0 | [7 empty] | Development Complete |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | QRG |  | 2025-08-08 | Overdue | [8 empty] | 2025-05-13 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868e0z8p7 | PTP Supplier Quality: Managing Text Keys - OL | DEVELOPMENT |  | Jessica Reed | URGENT | Approved by SMEs for development 7.1.25 | 4 | 0 | 2025-06-06 | 2025-05-22 | 2025-05-20 05:39 | 2025-08-14 07:23 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868a2v8tw 868e0z8pj 868e0z8ph 868e0z8pg | https://app.clickup.com/t/868a2v8tw https://app.clickup.com/t/868e0z8pj https://app.clickup.com/t/868e0z8ph https://app.clickup.com/t/868e0z8pg | wbt, ptp | Development | [7 empty] | 1324 hours |  | 0 |  |  | TRUE |  |  |  | Jessica Reed | Ready for Development |  |  |  | ITC3 | Supplier Quality | Supplier Quality Integration | TRUE | WBT |  | 2025-08-29 | Overdue | [8 empty] | 2025-05-02 | [6 empty] | PTP | Jenn Cooke, Shannon Bagent
868e1aqzq | R2R Financial Accounting: General Ledger Account Reports | COMPLETED | 6/5 sent out for final review following tiny wordsmithing edits requested by Billy in the previous day's call. Requested approval by EOD 6/9 NOTE ON AT-RISK STATUS: Should be only a few days later than planned sprint end. Week of sprint end date is the first week we have not had the additional Financial Accounting calls instituted by Chris Applegate. We got only one hour with the SMEs for this area and it was Misty, not Billy, who we need for this process. 6/11 Billy signed off full WBT! Screenshot capture of his signoff in Teams in validation folder |  | URGENT | Final updates made. Should be approved monday. | 2 | 0 | 2025-06-11 |  | 2025-05-20 14:17 | 2025-08-14 13:58 |  | 2025-06-11 12:43 | Sarah Griffis | Lockheed Martin | Course Development | Development | 868c6q5kx 868c6q67b 868c6q7f7 868c6q8k9 868c6q9g9 | https://app.clickup.com/t/868c6q5kx https://app.clickup.com/t/868c6q67b https://app.clickup.com/t/868c6q7f7 https://app.clickup.com/t/868c6q8k9 https://app.clickup.com/t/868c6q9g9 | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 1803 hours |  | 0 |  |  | TRUE |  |  |  |  | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | GL Close (Run Preliminary Reports L4) |  | WBT |  | 2025-06-11 | On-time | [15 empty] | R2R | Sarah Griffis, Trish Cortez
868e1aw82 | R2R Financial Accounting: Order and Backlog Adjustments | COMPLETED | SMEs added this course W/E 5/16. The L3 it's in (Update Project Finance Master Data) is currently located in ITC3B, but SMEs are unsure whether it will stay there and leaning toward it moving to ITC4. Pending a final decision 6/5 SG outline QA and returned to Dan for light revision; Dan made them; ready for SME review NOTE ON AT-RISK STATUS: This course's corresponding L3 was moved to ITC4, so it is lower priority in terms of timeline now. This means its sprint can move. As of 6/6, SG can't move sprints due to Clickup access issue, so kept as "high risk" since still reflecting 6/13 deadline. 6/13 Billy Cambers assembled a spreadsheet with all review items in backlog to distribute to appropriate SMEs for review. Since he is sending this out, all items are technically in Alpha review since handed off. Working with Billy to implement a signoff protocol with reviews being done this way. 7/1 Misty signed off outline in call! FOR DEVELOPMENT: note that we are pending an accurate process flow 7/2 WBT created and sent to SG for QA 7/2 SG WBT QA and returned for light revision 7/2 presented to SME, who made one small edit. Dan will make and we will get back to him to review it, also prompting him to get us the process flow, if available 7/7 SG WBT QA and returned for just 1 edit; edit made 7/7 placed in pause: entire course is complete and has been through one review with the SME, whose single change we reflected. The process flow is outstanding. Note that two internal deliverables are also on pause due to defect. 7/16 NOTE: course is fully verbally approved by Billy preceding the two sims inside that were paused for defect (Book Manual Adjustments/Orders) because we determined any changes to those would not have implications for full course. (7/17 those sims are now approved.) NOTE: this course needs the final process flow link in the course when it is published. The flow is approved formally but as of 7/17 not published. Dan is checking back weekly on its publishing status. 7/17 sent to SMEs requesting review/approval by EOD 7/21 7/17 got tiny requests for edits from Misty that Dan will implement 7/22 Billy and Misty signed off in call! NOTE "pending" status is not due to change impacts but to publishing the finalized flow. Update: correct flow is updated and linked; course is complete. |  | HIGH |  | 0 | 0 | 2025-07-22 | 2025-06-06 | 2025-05-20 14:26 | 2025-08-14 13:55 |  | 2025-07-30 08:01 | Sarah Griffis | Lockheed Martin | Course Development | Development | 868e1awgx 868e1awr3 868e1awwg 868e1ax2z | https://app.clickup.com/t/868e1awgx https://app.clickup.com/t/868e1awr3 https://app.clickup.com/t/868e1awwg https://app.clickup.com/t/868e1ax2z | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 632 hours |  | 0 | 2025-07-22 |  | TRUE |  |  |  |  | Hand off to OCM Team | 2025-07-17 |  |  | ITC4 | Financial Accounting | Collect & Process Actuals (Update Project Finance Master Data L4) |  | WBT |  | 2025-07-22 | Overdue | [9 empty] | 2025-07-22 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868e1p7kj | R2R Financial Accounting: Create Recurring Document | COMPLETED | 5/21 course signed off by Billy; screenshot saved in validations folder |  | LOW |  | 0 | 0 | 2025-05-21 |  | 2025-05-21 10:00 | 2025-08-14 13:58 |  | 2025-05-21 12:47 | Sarah Griffis | Lockheed Martin | Course Development | Development | 868djc0vm | https://app.clickup.com/t/868djc0vm | r2r, wbt | Development | [7 empty] | 2307 hours |  | 0 | 2025-05-21 | [6 empty] | Hand off to OCM Team |  |  |  | ITC2 | Financial Accounting | Create Automated Journal Criteria |  | WBT |  | 2025-05-21 | On-time | [9 empty] | 2025-05-21 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868eakb9n | PTS Prod Ops: Resolve Issues - OL | OUTLINES |  | Alisha Khan | NORMAL | Email from SME Travis on 8.18: Both John and I are in a face to face meeting for the next two days and travel on Wednesday. I have cutover over task on Thursday, Friday and Saturday all day. We will need to schedule something for next week | 4 | 0 | 2025-08-01 | 2025-07-14 | 2025-06-10 13:17 | 2025-08-25 00:37 |  |  | Eugene Deloatch | Lockheed Martin | Course Development | Development | 868eakd6z 868eakdd8 868eakdk9 868eakdpq 868eake0j 868eakeap 868b466gk 868ec0yc9 | https://app.clickup.com/t/868eakd6z https://app.clickup.com/t/868eakdd8 https://app.clickup.com/t/868eakdk9 https://app.clickup.com/t/868eakdpq https://app.clickup.com/t/868eake0j https://app.clickup.com/t/868eakeap https://app.clickup.com/t/868b466gk https://app.clickup.com/t/868ec0yc9 | p2s, ilt | Development | [7 empty] | 484 hours |  | 0 |  |  |  |  | 2025-08-12 |  | Alisha Khan | Beta Revision (ISG) |  |  |  | ITC4 | Prod Ops | Warehouse Inbound Processing |  | ILT |  | 2025-09-26 | Overdue | - Task was renamed and relevant tags (ilt, p2s) were added by [@Eugene Deloatch](#81458171). - Modalities field set to ILT and task added to Sprint 14 (7/14 - 8/8) by [@Trish Cortez](#50219539). - Assignees updated: [@Eugene Deloatch](#81458171) assigned and then unassigned; [@Shannon Bagent](#32129693) unassigned. - Subtask 'Grief Resolution Process - QRG' was created. No issue resolution progress yet. | [14 empty] | PTS | Shannon Bagent, Eugene Deloatch
868ebjdy3 | PTS Prod Ops: Generate and Release STO - QRG | STORYBOARD |  |  | NORMAL |  | 0 | 0 |  | 2025-07-14 | 2025-06-12 10:38 | 2025-08-24 23:59 |  |  | Eugene Deloatch | Lockheed Martin | Course Development | Development |  |  | p2s, qrg | Development | [7 empty] | 826 hours |  | 0 | 2025-07-14 | [6 empty] | Ready for SB draft |  |  |  | ITC3 | Prod Ops | Fulfillment Management |  | QRG |  | 2025-09-26 | On-time | [15 empty] | PTS | Shannon Bagent, Eugene Deloatch
868ecejng | PTS Prod Ops: Resolve Cycle Count Discrepancies - OL | DEVELOPMENT |  |  | NORMAL | @Eugene Deloatch @Shannon Bagent , I have begun the storyboards for the QRGs. We need someone to work on the SL portion. Thank you! | 9 | 0 | 2025-08-04 |  | 2025-06-14 12:33 | 2025-08-25 00:35 |  |  | Eugene Deloatch | Lockheed Martin | Course Development | Development | 868ecejxq 868ecek0z 868ecek47 868ecek6y 868ecekc6 | https://app.clickup.com/t/868ecejxq https://app.clickup.com/t/868ecek0z https://app.clickup.com/t/868ecek47 https://app.clickup.com/t/868ecek6y https://app.clickup.com/t/868ecekc6 | p2s, ilt | Development | [7 empty] | 604 hours |  | 0 | [6 empty] | Mary Beth Finigan | Ready for Development |  |  |  | ITC4 | Prod Ops | Warehouse Inbound Processing | TRUE | ILT |  | 2025-09-26 | Overdue | [8 empty] | 2025-08-06 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868echkqg | PTS SIOP: 1LMX SIOP Overview - OL | OUTLINES |  | Mary Beth Finigan | LOW | @Eugene Deloatch This is ready for VS review. Please refer to Ashley's comment regarding the structure of the online training. It can be adjusted to fit the necessary information. A few updates from Subject Matter Experts (SMEs) are needed to align the role names in our curriculum with theirs. Thank you. | 6 | 0 | 2025-08-11 | 2025-08-04 | 2025-06-15 12:03 | 2025-08-25 00:45 |  |  | Eugene Deloatch | Lockheed Martin | Course Development | Development | 868ed3ndx | https://app.clickup.com/t/868ed3ndx | p2s, wbt | Development | [7 empty] | 442 hours |  | 0 | 2025-08-07 | [5 empty] | Mary Beth Finigan | QA Revision |  |  |  | Not part of ITC | SIOP | Financial Risk & Impact Analysis | TRUE | WBT |  | 2025-09-26 | Overdue | [8 empty] | 2025-08-07 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868ecvmyn | O2C AR: Apply Cash | PREDEVELOPMENT |  | Ashley Parker | URGENT |  | 0 | 0 |  |  | 2025-06-16 09:31 | 2025-08-06 12:49 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868ecwa1a 868ecw9uy 868ecw9mu 868ecw99j 868ecw92c 868ecw8e8 868ecw8km 868ecvpff | https://app.clickup.com/t/868ecwa1a https://app.clickup.com/t/868ecw9uy https://app.clickup.com/t/868ecw9mu https://app.clickup.com/t/868ecw99j https://app.clickup.com/t/868ecw92c https://app.clickup.com/t/868ecw8e8 https://app.clickup.com/t/868ecw8km https://app.clickup.com/t/868ecvpff | ilt, o2c | Development | [7 empty] | 1636 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Accounts Receivable | Application of Cash |  | ILT |  | 2025-09-19 | On-time | [15 empty] | O2C | Angie Paxton
868ecw4x2 | O2C AR: Introduction to S4 HANA for Accounts Receivable | PREDEVELOPMENT |  | Ashley Parker | URGENT |  | 0 | 0 |  |  | 2025-06-16 09:52 | 2025-08-06 12:51 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868ecwdn0 868ecwdg0 868ecwdb6 868ecwd76 868ecwd2v 868ecwcvn | https://app.clickup.com/t/868ecwdn0 https://app.clickup.com/t/868ecwdg0 https://app.clickup.com/t/868ecwdb6 https://app.clickup.com/t/868ecwd76 https://app.clickup.com/t/868ecwd2v https://app.clickup.com/t/868ecwcvn | o2c, ilt | Development | [7 empty] | 1636 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | Not part of ITC | Accounts Receivable | No L3 Custom Content |  | ILT |  | 2025-09-19 | On-time | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868edp74m | O2C Contracts: Introduction to S4 HANA for Contract Analysts | DEVELOPMENT |  | Angie Paxton | NORMAL | @Angie Paxton Converted document to WBT content outline and made revisions to topic title, objectives, and sims (added SL design notes). | 1 | 0 | 2025-08-14 | 2025-07-02 | 2025-06-17 13:17 | 2025-08-24 23:35 |  |  | Angie Paxton | Lockheed Martin | Course Development | Development | 868eubmq5 868eubmzj | https://app.clickup.com/t/868eubmq5 https://app.clickup.com/t/868eubmzj | wbt, o2c | Development | [7 empty] | 1153 hours |  | 0 | 2025-07-17 | 2025-08-04 |  |  | 2025-08-19 |  | Angie Paxton | Beta Revision (ISG) |  |  |  | Not part of ITC | Contracts | No L3 Custom Content |  | WBT |  | 2025-09-26 | Overdue | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868edqv4w | A2R CLRP Overhead: Project Approval Request Submission (Non-Stat) | DEVELOPMENT |  | Bailey Petty | URGENT | @Steve Hile Ready for VS - Link sent to both your emails | 23 | 0 | 2025-09-26 | 2025-06-13 | 2025-06-17 13:56 | 2025-08-25 00:15 |  |  | Veronica Massey | Lockheed Martin | Course Development | Development | 868edqv5c | https://app.clickup.com/t/868edqv5c | a2r, wbt, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Bailey Petty | Pending SIMs |  |  |  | ITC3B | CLRP | Execute CLRP (Project Approval L4) |  | WBT |  | 2025-09-26 | Overdue | - [@Brice LeBlanc](#75334455) completed the draft for this item. - [@Veronica Massey](#57129402) performed internal QA and confirmed it is ready for VS Lead QA. - The item is now marked as 'In QA' and is available in the designated folder for review. - [@Steve Hile](#81539658) has been notified that the item is ready for VS Lead QA. | [7 empty] | 2025-04-29 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ee5z49 | R2R Tax Accounting: Indirect Tax Corrections (PO and SD Invoices): Overview | COMPLETED | 2/19 level set call with Adrienne: for all Indirect items, Ankine should review and sign off first, and then Adrienne 2/27 Ankine confirmed movement of this L3 to ITC3, descoped some current lessons, and added 3 new 4/4 assigned Brenda creation of shell 4/14 assigned outline and WBT to Dan after Ankine made really specific requests for WBT content 4/24 reviewed with Ankine in Tax call; made some progress; sent it to her for offline review of lessons 1 and 3 only--so not out for full review as content is still being drafted 5/1 reviewed again in Tax call and made progress on all lessons; still need offline review with them then check in NOTE ON AT-RISK STATUS: This course is taking a long time. We have gone back and forth with the two SMEs on contents and they often undo one another's work because one or another of them can't attend a call, we make decisions, and the other will undo what we decided. 6/6 update: we are getting closer but reviews are still taking a long time. In 6/5 call Ankine agreed to review the remaining 2 lessons of the outline over the weekend and hopefully she will sign off. Note that there is still some instability with the park/post items that we will need to firm up with SMEs. 6/12 Ankine reviewed offline over previous weekend, gave verbal signoff after final review in call, and asked Katie to do one last review and signoff; we're waiting for it 6/17 Katie signed off outline after Ankine's verbal signoff last week NOTE: all the above is from the former parent item that has now been archived; retained here for record0keeping. 6/18 broke out this course from the previously larger Indirect Tax Corrections course following 6/16 call with Hala and Ankine regarding course modality (conclusion: no ILT, but breaking up this course into the overview plus a series of courses, each of which is a different scenario). Now 1 Overview course (this one) plus individual Scenario courses 7/10 SG full QA 7/10 presented in SME call; Ankine made several requests for revision Dan and Jade worked hard at revisions--they were a lot and confusing. 7/11 SG WBT QA and sent back for light revision 7/11 sent back out to Ankine and Katie for review 7/17 a Beta review with Ankine + Katie present too. Substantial edits requested, some involving design. 7/21 after the changes were made QA complete; ready for another SME review 7/22 final review with SMEs in call; received verbal approval; sent formal email requesting signoff 7/22 Katie and Adrienne both signed off via email NOTE for future development: this course will need to be updated as material becomes available. We need to attach a Service Central ticket guide and it will not be ready until December. We also need to attach a Service Central Workflow guide. We do not have confirmation on when it will be ready. Because of this the course is marked as pending but not for change impacts, for the service central items. If we do not receive them in time we will need to delete the placeholder slides. |  | URGENT |  | 0 | 0 | 2025-07-22 | 2025-06-18 | 2025-06-18 08:35 | 2025-08-14 13:55 |  | 2025-07-22 11:42 | Sarah Griffis | Lockheed Martin | Course Development | Development | 868d45h1z 868d45mm6 | https://app.clickup.com/t/868d45h1z https://app.clickup.com/t/868d45mm6 | r2r, wbt | Development, ✍ Risk Register | [7 empty] | 820 hours |  | 0 |  |  | TRUE | 2025-07-11 |  |  |  | Pending Change Impacts |  |  |  | ITC3 | Tax Accounting | Consolidations & Tax (Indirect Tax Data Error Correction L4) |  | WBT |  | 2025-07-22 | Overdue | [9 empty] | 2025-07-22 | [5 empty] | R2R | Trish Cortez, Sarah Griffis
868egh98k | SUS Supply Chain Network Reservation Request | COMPLETED |  |  | HIGH | Ian update and lockdown complete 8/22 | 2 | 0 |  |  | 2025-06-24 11:55 | 2025-08-22 09:58 |  | 2025-08-12 16:06 | Brice LeBlanc | Lockheed Martin | Course Development | Development |  |  | sus, wbt | Development | [7 empty] | 312 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | Not part of ITC | Supply Chain |  |  | WBT |  | 2025-08-12 | On-time | [9 empty] | 2025-08-12 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868etue16 | A2R CLRP Overhead: Overhead Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:13 | 2025-08-24 23:54 |  |  | Steve Hile | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | CLRP | No L3 Custom Content |  | WBT |  | 2025-09-26 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etug2e | A2R Asset Management: Asset Management Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:16 | 2025-08-24 21:39 |  |  | Steve Hile | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Asset Management | No L3 Custom Content |  | WBT |  | 2025-09-19 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etugan | A2R Controlled Tooling: Controlled Tooling Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:17 | 2025-08-25 00:27 |  |  | Steve Hile | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Controlled Tooling | No L3 Custom Content |  | WBT |  | 2025-09-19 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etuhab | A2R Metrology and Calibration: Metrology and Calibration Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:17 | 2025-08-25 00:32 |  |  | Steve Hile | Lockheed Martin | Course Development | Development | 868agv0xr 868agv09p | https://app.clickup.com/t/868agv0xr https://app.clickup.com/t/868agv09p | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Metrology | No L3 Custom Content |  | WBT |  | 2025-09-26 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etuhr4 | A2R Asset Accounting: Asset Accounting Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:18 | 2025-08-24 20:58 |  |  | Steve Hile | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Asset Accounting | No L3 Custom Content |  | WBT |  | 2025-09-05 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etuj67 | A2R LLM: Lease Lifecycle Management Overview | PREDEVELOPMENT |  | Veronica Massey | URGENT |  | 0 | 0 |  |  | 2025-07-16 09:19 | 2025-08-25 00:31 |  |  | Steve Hile | Lockheed Martin | Course Development | Development |  |  | a2r, wbt | Development | [7 empty] | 966 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Lease Lifecycle Management | No L3 Custom Content |  | WBT |  | 2025-09-05 | [16 empty] | A2R | Trish Cortez, Steve Hile
868etz6h5 | PTP SCM Requisition to Procure: 1LMX Requisition to Procure Overview - OL | PREDEVELOPMENT |  |  |  | Supply Chain Mgmt SMEs indicated during the original curriculum development that overview courses were not necessary. Matt Berinato also did not feel these were needed when we rewrote the curriculum earlier this year. Furthermore, it is unclear whether Buyers in this L2 would be assigned multiple overview courses, as they carry out tasks across Supply Chain Mgmt and Accounts Payable. This would add significant additional training time to a role that already has a large number of planned courses. | 1 | 0 |  |  | 2025-07-16 12:52 | 2025-08-24 22:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 963 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Supply Chain | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etz74k | PTP SCM PTP Foundational: 1LMX Procure to Pay Foundational Overview - OL | PREDEVELOPMENT |  |  |  | Supply Chain Mgmt SMEs indicated during the original curriculum development that overview courses were not necessary. Matt Berinato also did not feel these were needed when we rewrote the curriculum earlier this year. | 1 | 0 |  |  | 2025-07-16 12:53 | 2025-08-24 22:08 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt, ptp | Development | [7 empty] | 963 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Supply Chain | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etz7mr | PTP SCM Process Agreements: 1LMX Process Agreements Overview - OL | PREDEVELOPMENT |  |  |  | Supply Chain Mgmt SMEs indicated during the original curriculum development that overview courses were not necessary. Matt Berinato also did not feel these were needed when we rewrote the curriculum earlier this year. | 1 | 0 |  |  | 2025-07-16 12:54 | 2025-08-24 21:58 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Supply Chain | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etz8kq | PTP SCM Supplier Lifecycle Mgmt: 1LMX Supplier Lifecycle Mgmt Overview - OL | PREDEVELOPMENT |  |  |  | Supply Chain Mgmt SMEs indicated during the original curriculum development that overview courses were not necessary. Matt Berinato also did not feel these were needed when we rewrote the curriculum earlier this year. | 1 | 0 |  |  | 2025-07-16 12:55 | 2025-08-24 23:14 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt, ptp | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Supply Chain | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etza8b | PTP Accounts Payable: 1LMX Accounts Payable Overview - OL | PREDEVELOPMENT |  |  | LOW | Neither Blanca nor Gina felt that an overview course was needed when we wrote and later revised the curriculum. | 1 | 0 |  |  | 2025-07-16 12:58 | 2025-08-25 00:58 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Accounts Payable | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etze7k | PTP MCE: 1LMX Material Cost Estimating Overview - OL | PREDEVELOPMENT |  |  |  | Tori and Nelson did not feel that an overview course was necessary when we designed the curriculum. The major changes in MCE revolve around Twenty5, whereas the S/4HANA training component covers very minor technology changes only. | 1 | 0 |  |  | 2025-07-16 13:02 | 2025-08-24 21:58 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | MCE | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etzfh0 | PTP Supplier Quality: 1LMX Supplier Quality Overview - OL | PREDEVELOPMENT |  |  |  | Ed Newman did not feel that an overview course was necessary when we designed the curriculum. The more complicated changes in Supplier Quality seem to revolve around Apriso MES, whereas the S/4HANA training component mostly involves technology changes. | 1 | 0 |  |  | 2025-07-16 13:05 | 2025-08-24 23:24 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Supplier Quality | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PTP | Jenn Cooke, Shannon Bagent
868etzh1x | PLP Incurred Cost Claim: 1LMX Incurred Cost Claim Overview - OL | PAUSED |  |  | LOW | Neither Jason Lewis nor Dan Huynh felt that an overview course would be a value add for this area. We are only covering one part of the L2 they belong to. Technically, Incurred Cost Claim is an L3, but the other part of the L2, Forward Pricing, is not within our scope. This is a very small team of 25-30 super users who have asked us to focus on the technology changes around Cognitus. Jason Lewis indicated very early in the TNA process that they would not appreciate additional training that represented an inefficient use of their time. | 1 | 0 |  |  | 2025-07-16 13:07 | 2025-08-24 23:51 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt | Development | [7 empty] | 410 hours |  | 0 | [7 empty] | Paused |  |  |  | Not part of ITC |  |  |  | WBT |  | 2025-09-26 | On-time | [7 empty] | Dan Huynh | [7 empty] | PLP | Jenn Cooke, Trish Cortez
868etzjrn | PLP PS: 1LMX Project Systems Overview - OL | PREDEVELOPMENT |  |  | LOW | Dina Thomas and Bethany Lane did not feel that an overview course represented a value add when we designed and refined our curriculum. They are heavily focused on the PCID ILT training and already have PPTs that present a high-level overview of this new process. Moreover, Bethany has already expressed concerns about her people needing to access web-based training through an LMS. | 1 | 0 |  |  | 2025-07-16 13:11 | 2025-08-25 00:34 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC |  |  |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PLP | Trish Cortez, Anya Toms, Jenn Cooke
868etzmya | PLP MEV: 1LMX Manufacturing Earned Value Overview - OL | PREDEVELOPMENT | / |  | LOW | We have not yet finished developing the curriculum for this very new L3, but the remainder of the L2 they belong to is out of our scope. MEV is only facing minor technology changes in S/4HANA, and Tara did not feel that an overview course was needed. | 1 | 0 |  |  | 2025-07-16 13:15 | 2025-08-25 11:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | ptp, wbt | Development | [7 empty] | 912 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | On-time | [15 empty] | PLP | Trish Cortez, Anya Toms, Jenn Cooke
868eudgk0 | R2R Tax Accounting: Indirect Tax Corrections (PO and SD Invoices): Scenarios | COMPLETED | As of 7/16, we are back to one single course for Scenarios. We pitched a couple divisions to Ankine based on role division and she confirmed that she wants all roles taking one single course. Hence the odd configuration in Clickup of the tasks. 7/24 discussed organization of course with Katie in call; Dan has direction and we will present 7/29. Dan primarily developer and Brenda is pitching in. 7/29 SG QA full course and returned for some revision; edits made; QA again. Only a couple items outstanding and they need SME attention. 7/29 Katie reviewed and asked for a few minor changes and to review again offline; sent to both Katie and Ankine for offline review, to resume later this week Lots of comments from Ankine that Dan addressed offline 8/5 Beta review with Katie and Ankine; Ankine hunting down one more item on credit memo to see where it will be developed and will get back to us. Nearly ready to sign off. 8/11 SG finished another QA round; sent back for light revision; he and Brenda completed 8/13 sent to SMEs for final review and Ankine asked for changes again 8/18 changes made and sent back for review. Note there are two outstanding items linked inside course: a training on credit memo we are waiting for Ankine to give direction on (likely one slated to be completed in O2C) and Katie's edited FlexRFC job aid. 8/19 Ankine says the PTP Verify Credit Memo training is the right one to be linked in the course; it's in outline stage and need to review outline with Ankine 8/21. Ankine agreed to review FlexRFC update by EOD 8/19. Otherwise gave verbal approval on course. 8/20 both Katie and Ankine approve the FlexRFC updated job aid. Only outstanding item is credit memo training; will open 8/21 call with review of its outline. 8/21 Dan input FlexRFC job aid. Course is complete pending credit memo training. NOTE: This is not an easy lift. We are not finding what we need re credit memo. Ankine wants to train on creation of it; so far this training exists in O2C and she says it is not what we need. I sent her a list of all training on the Invoice & Credit Processing L3 and she is looking through to see if what she is looking for is there. Her concern is that there are 2 components required in that L3: credit memo and manual invoice, and they go together. If we link only credit memo, it won't go over the invoicing side and we need both. Jenn got in touch with Gina Garvey who confirmed PTP (AP) has the training it needs on this L3, so unclear if we have what Ankine is looking for/that it exists. 8/25 Ankine wrote to say 2 of PTP's trainings should cover what we need: 1) Submit Debit/Credit Request, a WBT with no sims, as of today in development. 2) Create Invoice Using Spreadsheet Upload, a WBT with 1 simulation, Post Invoice, both items as of today in development; asked Ankine if we need full WBT or just the sim. Either way, training will be incomplete till these pieces are completed in PTP and then linked in our course. NOTE: on our side we need to decide whether it's possible for us to link whole WBTs inside a WBT. Trish's response 8/25: "I dont think so - because it would go back to Atlas. You can refer to it or make it part of the "curriculum." So they complete it after they complete the course they are working on." Will need to let Ankine know--send to her when she emails back. |  | URGENT | @Daniel Die per our discussion, planning to present to Katie/Ankine 7/29. | 1 | 0 | 2025-08-18 | 2025-07-17 | 2025-07-17 11:28 | 2025-08-25 14:06 |  | 2025-08-25 14:06 | Sarah Griffis | Lockheed Martin | Course Development | Development | 868dt1ccj 868dt1axy 868dt1bdt 868dt1brr 868dt1cwe | https://app.clickup.com/t/868dt1ccj https://app.clickup.com/t/868dt1axy https://app.clickup.com/t/868dt1bdt https://app.clickup.com/t/868dt1brr https://app.clickup.com/t/868dt1cwe |  | Development, ✍ Risk Register | [7 empty] | 2 hours |  | 0 | 2025-07-29 | 2025-07-29 | TRUE | 2025-08-07 | 2025-08-05 |  |  | Hand off to OCM Team |  |  |  | ITC3 | Tax Accounting | Consolidations & Tax (Indirect Tax Data Error Correction L4) |  | WBT |  | 2025-08-29 | Overdue | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868euwdxw | O2C Billing: Overview | PREDEVELOPMENT |  | Angie Paxton | URGENT |  | 0 | 0 |  |  | 2025-07-18 12:50 | 2025-08-14 06:51 |  |  | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | o2c, wbt | Development | [7 empty] | 915 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | Not part of ITC | Billing | No L3 Custom Content |  | WBT |  | 2025-09-19 | On-time | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868euwy3c | O2C Sales Orders: Overview | PREDEVELOPMENT |  | Angie Paxton | HIGH |  | 0 | 0 |  |  | 2025-07-18 13:20 | 2025-08-24 23:40 |  |  | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | o2c, ilt | Development | [7 empty] | 914 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | Not part of ITC | Sales Orders | Capture, Process, and Track End Item Deliverable Sales Orders Capture, Process and Track Sustainment Spares |  | ILT |  | 2025-09-26 | On-time | [15 empty] | O2C | Angie Paxton, Shannon Bagent
868eux0r6 | PTS Prod Ops: Overview | OUTLINES |  | Jessica Visser, Shannon Bagent | URGENT | @Shannon Bagent I made extensive changes to the contents based on Shannon's comments. It is ready for the next review. | 4 | 0 |  | 2025-08-04 | 2025-07-18 13:27 | 2025-08-25 06:15 |  |  | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | p2s, wbt | Development | [7 empty] | 457 hours |  | 0 | 2025-08-04 | [5 empty] | Jessica Visser | In QA |  |  |  | Not part of ITC | Prod Ops | No L3 Custom Content |  | WBT |  | 2025-09-19 | On-time |  |  | 2025-08-25 | [12 empty] | PTS | Shannon Bagent, Eugene Deloatch
868eux5br | R2R Financial Accounting: Overview | PREDEVELOPMENT |  |  | URGENT |  | 0 | 0 | 2025-08-17 | 2025-08-13 | 2025-07-18 13:35 | 2025-08-25 00:52 |  |  | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | r2r, wbt | Development | [7 empty] | 294 hours |  | 0 | 2025-08-13 | [10 empty] | Not part of ITC | Financial Accounting | No L3 Custom Content |  | WBT |  | 2025-09-12 | Overdue | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868evkbzh | A2R CLRP Overhead: Overhead EPPM Administrative Tasks | PREDEVELOPMENT |  | Veronica Massey | LOW | Per SMEs F2F meeting 7/21. Keep this course. It is normal priority so dev can happen after all high-priority tasks are completed. | 1 | 0 |  |  | 2025-07-21 12:52 | 2025-08-24 23:53 |  |  | Steve Hile | Lockheed Martin | Course Development | Development | 868evkbzz 868evkc01 868evkc00 | https://app.clickup.com/t/868evkbzz https://app.clickup.com/t/868evkc01 https://app.clickup.com/t/868evkc00 | a2r, wbt | Development | [7 empty] | 843 hours |  | 0 | [7 empty] | Course Package Not Started |  |  |  | Not part of ITC | CLRP | No L3 Custom Content |  | WBT |  | 2025-09-26 | [16 empty] | A2R | Trish Cortez, Steve Hile
868eyh2kw | R2R Cost Accounting: Overview | OUTLINES | 7/28 call with Brent: added this course but see below notes TENTATIVE: Labor team may have no bandwidth to create this for R1 The topical need: labor; settlement; results analysis We would train on average labor rates; ADLR codes; etc. Slides exist around this but may not exist in a coherent training. SG will reach out to Dana Taulane to see where she has gotten on this and if we can take it off her plate--and if there is bandwidth to do so right now. Not filling in rest of Clickup data until confirmed. 7/29 discussion with Dana: she essentially wants there to be 1 broad Finance Overview course and 1 Cost Accounting-specific overview course. I think this is a good idea and we can assign the basic overview also in Tax and Financial Accounting as the overview course for those areas. The reason: Cost Accounting is mostly O&M. The tasks that are not (and thus require training) require some conceptual, non-step-based knowledge that they have no training for. We can meet a need here. ACTION: Dan and Sarah will analyze meeting notes and materials Dana provided to come up with 2 provisional outlines: Finance Overview; Cost Accounting Overview. Not adding to Clickup till confirmed with client. 8/5 confirmed this course alone for Cost Accounting. Sarah will start on OL while Dan is out later this week and we will present a provisional one to the client next week (8/12) 8/12 Dan presented a provisional outline to the client; they agreed it was a strong start and requested some changes. Dan implemented, SG QA, then 8/12 sent for offline review. Team is also going to look at Financial Accounting training on G/L to see if they want to include any of it in this course. Will resume and refine outline next week (8/19) as they said likelihood of offline review is low. (They didn't review offline) 8/19 continued Alpha review where we left off last time; still did not complete. Will send offline just in case, and then resume in our next call. In the meantime Dan and SG will discuss whether to recommend ILT as modality. |  | HIGH | @Brenda Mayfield as soon as we have an outline draft approved by the client (hopefully 8/18), we will have you start the shell. You and Dan can then go back and forth on development. We will have you work on this M; you and Dan will balance this alongside State and Federal. | 1 | 0 | 2025-08-29 | 2025-08-07 | 2025-07-28 13:51 | 2025-08-25 11:19 |  |  | Sarah Griffis | Lockheed Martin | Course Development | Development |  |  |  | Development | [7 empty] | 486 hours |  | 0 |  |  |  | 2025-08-14 |  |  | Daniel Die, Brenda Mayfield | Alpha Review (SME) |  |  |  | Not part of ITC | Cost Accounting | No L3 Custom Content |  | WBT |  | 2025-09-26 | On-time | [15 empty] | R2R | Sarah Griffis, Trish Cortez
868ez09bv | SUS Obsolescence Management: Program Part Tracking | COMPLETED |  |  | NORMAL |  | 0 | 0 |  | 2025-07-01 | 2025-07-29 09:41 | 2025-08-25 07:55 |  | 2025-08-12 16:04 | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | qrg, sus | Development | [7 empty] | 312 hours |  | 0 | [7 empty] | Sign off Received |  |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | QRG |  | 2025-08-12 | On-time |  |  |  | Brenda Mayfield | [5 empty] | 2025-08-12 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868ez09jc | SUS Obsolescence Management: Understanding DMS Case Resolutions | COMPLETED |  |  | NORMAL |  | 0 | 0 |  | 2025-07-01 | 2025-07-29 09:42 | 2025-08-25 07:55 |  | 2025-08-12 16:03 | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | qrg, sus | Development | [7 empty] | 312 hours |  | 0 | [7 empty] | Sign off Received |  |  |  | ITC3 | Obsolescence Management Using CDATS | Obsolescence Management |  | QRG |  | 2025-08-12 | On-time |  |  |  | Brenda Mayfield | [5 empty] | 2025-08-12 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868ez0a3c | SUS SCDS Theory & Tool Use | COMPLETED |  |  | NORMAL | Ian update and lockdown complete 8/22 | 2 | 0 |  | 2025-06-04 | 2025-07-29 09:42 | 2025-08-24 21:45 |  | 2025-08-21 15:17 | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | sus, wbt | Development | [7 empty] | 96 hours |  | 0 | [7 empty] | Hand off to OCM Team |  |  |  | ITC3 | SCDS Theory & Tool Use | SCDS |  | WBT |  | 2025-08-22 | On-time | [9 empty] | 2025-08-21 | [5 empty] | SUS | Brice LeBlanc, Shannon Bagent
868ez0a93 | SUS Perform Maintenance: Service Orders - EDE to AMS Interface | DEVELOPMENT |  |  | NORMAL |  | 0 | 0 |  | 2025-06-04 | 2025-07-29 09:43 | 2025-08-25 11:56 |  |  | lara.gorton@isg-one.com | Lockheed Martin | Course Development | Development |  |  | sus, qrg | Development | [7 empty] | 654 hours |  | 0 | [7 empty] | Final Review & Sign off (SME) |  |  |  | ITC3 | Perform Maintenance | Maintenance Performance |  | WBT |  | 2025-08-29 | On-time | [15 empty] | SUS | Brice LeBlanc, Shannon Bagent
868ez8jhj | A2R Metrology: IndySoft: Technicians | DEVELOPMENT |  | Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL dev. @Veronica Massey | 7 | 0 | 2025-09-05 | 2025-07-09 | 2025-07-29 15:02 | 2025-08-25 00:44 |  |  | Trish Cortez | Lockheed Martin | Course Development | Development | 868ez8jjk 868ez8jhw 868ez8jhv 868ez8jhy | https://app.clickup.com/t/868ez8jjk https://app.clickup.com/t/868ez8jhw https://app.clickup.com/t/868ez8jhv https://app.clickup.com/t/868ez8jhy | a2r, indysoft, wbt, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration |  | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-04-30 | [6 empty] | A2R | Trish Cortez, Steve Hile
868ez8kht | A2R Metrology: IndySoft: Procedures | DEVELOPMENT |  | Veronica Massey | URGENT | SME approved OL 8/5. Ready for SL dev. @Veronica Massey | 6 | 0 | 2025-09-05 | 2025-07-09 | 2025-07-29 15:04 | 2025-08-25 00:40 |  |  | Trish Cortez | Lockheed Martin | Course Development | Development | 868ez8khw 868a2vb2g | https://app.clickup.com/t/868ez8khw https://app.clickup.com/t/868a2vb2g | indysoft, wbt, a2r, mfc | Development | [7 empty] | 264 hours |  | 0 | [6 empty] | Veronica Massey | Ready for Development |  |  |  | ITC4 | Metrology | Metrology & Calibration | TRUE | WBT |  | 2025-09-12 | Overdue | [8 empty] | 2025-08-19 | [6 empty] | A2R | Trish Cortez, Steve Hile
868f2df17 | PTS Prod Ops: Managing Demand Management Activities - OL | DEVELOPMENT |  | Eugene Deloatch | URGENT | 8/11: SME reviewed outline in real time in a meeting and gave verbal approval. Ready for development | 5 | 0 |  | 2025-08-20 | 2025-08-05 12:38 | 2025-08-20 05:50 |  |  | Shannon Bagent | Lockheed Martin | Course Development | Development | 868f3fjhm 868f3fkkp 868f3fk1d 868f3fkcb 868f46te5 | https://app.clickup.com/t/868f3fjhm https://app.clickup.com/t/868f3fkkp https://app.clickup.com/t/868f3fk1d https://app.clickup.com/t/868f3fkcb https://app.clickup.com/t/868f46te5 | wbt, p2s | Development | [7 empty] | 130 hours |  | 0 | 2025-08-20 | [5 empty] | Eugene Deloatch | Alpha Draft (ISG) |  |  |  | ITC4 | Prod Ops | Complete & Manage Non-Complex Assembly Sales Orders | TRUE | WBT |  | 2025-09-19 | Overdue | [8 empty] | 2025-08-07 | [6 empty] | PTS | Shannon Bagent, Eugene Deloatch
868f302k0 | PLP MEV: Material Baseline - OL | OUTLINES |  |  | URGENT | @Anya Toms QA is complete. Tracked changes turn on, direct edits and comments added to the document. | 4 | 0 |  | 2025-08-19 | 2025-08-06 11:55 | 2025-08-25 00:16 |  |  | Anya Toms | Lockheed Martin | Course Development | Development | 868farx45 868farx7z 868farxbh 868farxe6 | https://app.clickup.com/t/868farx45 https://app.clickup.com/t/868farx7z https://app.clickup.com/t/868farxbh https://app.clickup.com/t/868farxe6 | wbt, plp | Development | [7 empty] | 460 hours |  | 0 | [6 empty] | Anya Toms | QA Revision |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868f306vf | PLP MEV: Material Performance - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-08-06 12:00 | 2025-08-06 12:04 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868fb40cx 868fb40qa | https://app.clickup.com/t/868fb40cx https://app.clickup.com/t/868fb40qa | plp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-19 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868f307g9 | PLP MEV: Material EAC - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-08-06 12:00 | 2025-08-25 00:16 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868fb46kx 868fb4707 868fb479t | https://app.clickup.com/t/868fb46kx https://app.clickup.com/t/868fb4707 https://app.clickup.com/t/868fb479t | plp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868f30862 | PLP MEV: Standards Remaining Report & Standards Earned Report - OL | OUTLINES |  |  | URGENT |  | 0 | 0 |  |  | 2025-08-06 12:01 | 2025-08-25 00:33 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868fb49ae 868fb49qr 868fb49zz 868fb4ae9 868fb4aw2 868fb4b6t | https://app.clickup.com/t/868fb49ae https://app.clickup.com/t/868fb49qr https://app.clickup.com/t/868fb49zz https://app.clickup.com/t/868fb4ae9 https://app.clickup.com/t/868fb4aw2 https://app.clickup.com/t/868fb4b6t | plp, wbt | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868f308r4 | PLP MEV: Identify & Verify Standard Hours by Part Number - OL | OUTLINES |  |  | HIGH |  | 0 | 0 |  |  | 2025-08-06 12:02 | 2025-08-06 12:05 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development | 868fb1yuc | https://app.clickup.com/t/868fb1yuc | wbt, plp | Development | [7 empty] | 460 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Jenn Cooke, Trish Cortez
868f309d4 | PLP MEV: Identify & Verify Work Center, Cost Center, Activity Type Mapping - OL | PREDEVELOPMENT |  |  | LOW |  | 0 | 0 |  |  | 2025-08-06 12:03 | 2025-08-25 00:15 |  |  | Jenn Cooke | Lockheed Martin | Course Development | Development |  |  | wbt, plp | Development | [7 empty] | 437 hours |  | 0 | [7 empty] | Ready for OL Draft |  |  |  | ITC3B | Project Systems | Create Accounting Work Breakdown Structure (Project Systems) |  | WBT |  | 2025-09-26 | [16 empty] | PLP | Trish Cortez, Anya Toms, Jenn Cooke
868f6vdd4 | R2R Tax Accounting: Vertex Accelerator: Indirect Tax Determination Engine | OUTLINES | 8/14 in demo of Vertex by Katie with Ankine and Ron present: 3 courses needed for R1, and not organized on the criterion of Americas/RoW as the L3s are organized (NOTE that this means the L3 identified as associated to the course is loose--we're not following L3 organization strictly speaking, but we're still in ITC4 because the Determination Engine L3 is). Instead organized by tool: SAP, Vertex O Series, Vertex Accelerator. Directive is to include components in all 3 courses of both Americas/Row. We will need to mark which items are international. These courses used to have roughly 15 individual step-based deliverables; Ankine and Katie agree that is too low-level and the course should be custom and higher level. In the future we may add simulations to show step-based tasks, and if we do that we will mark them individually as Americas or RoW. For R1, just ILTs with no step-based individual tasks. As we go through the outline with Katie we will add lessons; they are not finalized right now. Note that the courses will need to be delivered twice: to two different audiences (Americas, RoW), for a total of 6 deliveries (3 courses x 2 audiences). Note on Outline status: It's in this status because an outline has been started, but it's Katie's and Ankine's. Dan will enter a start date when he picks up their outline and starts to adapt it into deliverable format. | Daniel Die | NORMAL | @Brenda Mayfield Dan will create a facilitator guide for the O Series course first. Once that’s done, he’ll pass it to as an example, so Brenda can then create the Accelerator facilitator guide. This will probably happen on Monday or Tuesday. | 1 | 0 |  |  | 2025-08-14 10:01 | 2025-08-25 10:45 |  |  | Sarah Griffis | Lockheed Martin | Course Development | Development |  |  | r2r, row, ilt, americas, vertex | Development | [7 empty] | 269 hours |  | 0 | 2025-08-14 | [5 empty] | Daniel Die | Alpha Draft (ISG) |  |  |  | ITC4 | Tax Accounting | Consolidations & Tax (Indirect Tax Determination Engine) |  | ILT |  | 2025-09-12 | On-time | [15 empty] | R2R | Trish Cortez, Sarah Griffis
868fb41rf | PLP MEV: Material Performance: Display final material performance report: SB | STORYBOARD |  | Jade Brown |  | @Trish Cortez can you please help me move this as a subtask to the PLP MEV: Material Performance | 1 | 0 |  |  | 2025-08-25 13:55 | 2025-08-25 14:00 |  |  | Anya Toms | Lockheed Martin | Course Development | Development |  |  |  | Development | [7 empty] | 2 hours |  | 0 | [7 empty] | Course Package Not Started | [10 empty] | On-time